## Slide 1
April 30, 2001
Confidential & Proprietary
Presentation to the Enron Corp. Finance Committee
Las Vegas Cogeneration, L.L.C.
222MW Power Plant Expansion

## Slide 2: Las Vegas Cogeneration Overview
Existing Power Plant
Las Vegas Cogeneration (LVCI) is located in North Las Vegas in rapid-growth load center that is short energy
LVC1 began commercial operation in May 1994 as a qualifying facility (QF)
45 MW of on-peak capacity and energy provided to Nevada Power Company under a PPA through May 2024
ENA acquired LVC1 in August 1999
Funded by non-recourse project debt ($54.9MM) and Enron/JEDI equity ($24MM).
ENA repowered LVCI in December 1999, reducing heat rate and increasing capacity to 51MW
Excess energy is available for merchant sales
Proposed Expansion
Continued strong industry demand for merchant generation projects in Western Region
Proposal - LVCII:
  222MW gas-fired generating facility
  Two, two-on-one combined cycle units
  4 LM6000’s from Enron’s existing turbine portfolio
  LVCII is adjacent to LVCI using similar technology
  15 year, fixed price tolling agreement with Allegheny Energy Supply (rated BBB+)
ENA intends to finalize development, commence construction and divest prior to commercial operations.

## Slide 3: Development Status and Sources & Uses
Transaction Sources and Uses (in MM)
Sources Uses
JEDI II $ 99.55 Existing Turbines $ 62.0
ENA $ 99.55 Construction Costs $107.5
TOTAL: $199.10* Interest Costs $ 19.4
Contingency $ 10.2
TOTAL: $199.1
* Excludes $0.6 MM Letter of Credit temporarily required for interconnect agreement
Completed:
Site: Industrial zoning approved
Air: Permits issued
Water/Wastewater: Permits issued/authority granted
Engineering, procurement and construction contract executed with Modern Continental with fixed-price, date certain completion guaranteed by A-rated bonding and insurance
Firm Power Transmission arranged to liquid delivery point
Remaining:
Electrical Interconnect at Nevada Power’s 138kv substation
Gas Interconnect – Southwest Gas to design, build & operate lateral from the Kern River Pipeline to LVCII
Water/Wastewater Definitive Agreement
Notice to Proceed with Construction
Commercial Operations expected September, 2002

## Slide 4: Strategy
Finalize development, commence construction and then divest prior to commercial operations.
The expansion project, combined with the existing QF asset, will be attractive to numerous generation companies:
  Proven reliable technology
  100% controlling interest
  Location in fast-growing load pocket in short region
  15 year fixed-price tolling agreement
Pro-Forma economics are superior to those of Fountain Valley Power, which was recently sold to Black Hills Energy Capital.
  Equity IRR 18.9% - 21.6%
Expressions of interest from Black Hills, Northland Power, Delta Power, Energy Investors Fund, Calpine.
  Expected gain on sale in 2001: $25MM - $30MM

## Slide 5
Approve $199.1 MM to finance construction of Las Vegas Cogeneration expansion (LVCII) subject to completion of the following:
  Execution of definitive tolling agreement with Allegheny Energy Supply
  Receipt of Electrical Transmission Agreement Confirmation
  Execution of Southwest Gas Interconnection Agreement
  Execution of Water/Wastewater Agreement
  Execution of Nevada Power Interconnection Agreement
Recommendation