## Slide 1
Lender Presentation

## Slide 2
Remaining CP’s
Obtain Furnas Consent
Validate Eletrabras Guarantee
Revise Siemens EPC to maintain performance test standards on Gas and TAA
Finalize Budget and Model
New Action Plan for Ridges (elevate drilling level or implement micro-tunneling)
Obtain Petrobras consent (expected 1/26/01)
SIRESE approval of Andina transportation capacity Assignment
Tozzini Briefing on Interconnection Agreement liability

## Slide 3
Furnas Decision
30 day PPA Default extension for Furnas not providing the consent will expired on Jan 22, 01
Options
Discontinue default and begin negotiations to resolve conflicts with Furnas and Eletrabras
Extend Default period again
Issue Notice of intent to Terminate (in 30 days)
Arbitrate right to terminate
Arbitrate damages claim(legal costs, use of equity capital)
Arbitrate Furnas specific performance responsibility to provide Lender’s Consent
Litigate Furnas specific performance responsibility to provide Lender’s Consent
Submit Economic Equilibrium claim to compensate for extended use of Sponsor equity capital
Accept original Assumption Agreement consent and rely on a favorable legal interpretation prepared by a respected Brazilian academician

## Slide 4
Furnas/Eletrabras Issue -Divide & Conquer Strategy
Consider 3rd Party Legal Brief for Eletrabras Obligations (review similarities of situation for EXIM & IADB in Mexico)
Attempt to get Furnas to sign original Consent from Assumption Agreement
Utilize legal process involving registered notification to Furnas of lender consent required for EPE to revise documents and Golden Quota in lieu of Consent

## Slide 5
Siemens Proposed Contract Revisions
Schedule
will work to achieve Provisional Completion (480MW on oil)
definition of Milestone #9 revised to coincide with Provisional Completion (final contractual payment)
then, Siemens to stand down and come back to test on gas
no LD’s for delay on oil
Lump Sum of US$823,000 for gas commissioning
Siemens pays LD’s if don’t commission on gas in 60 days
Warranty
6 months from Provisional Completion
Can purchase additional 6 months for $175,000/mo
Heat Rate
Will use curves (if can agree) or will measure now and again at beginning of conversion on gas to determine degradation
TAA
Redefine coverage window on guaranteed availability as 12 months before Provisional Completion to 12 months after, but suspended during commissioning on gas
Sound
Will test now for performance guideline in contract and during gas commissioning to assure meets WB Guideline
Drop Dead
Siemens obligation to begin testing on gas expires 3/31/02

## Slide 6
Siemens Proposed Contract Revisions - contd.
Strong Legal Position
Owner has clear 15 month suspension right with Siemens (12 months in Superior Contract)
tile problem is pre-existing and predates delays on gas to the plant
F/M is a valid defense
Concept of acceptance and Substantial Completion only has context of 480MW on gas so obligations for specific performance (with liability up to full amount of contract) remain
Siemens claim stems from:
contracts never contemplated a prolonged fuel oil phase and the plant being dispatched as a peaker
Original performance testing obligations presumed new & clean condition

## Slide 7
Proposed Action Plan
Extend Commitments to 12/31/01
Stand down lenders’ legal counsel until all items can be delivered as a package
Lender consent to act as necessary with respect to Remaining CP items
Continue CTA Compliance (particularly adverse publicity covenants)
Continue weekly call with Barbara, Frank & Tom only
Continue close environmental monitoring
Continue Monitoring by S&W
Use Receipt of Furnas Consent as trigger for remobilization

## Slide 8
New Subjects for discussion
Revise GSA with YPF
Request 0% Enron and Shell ownership hold of EPE
  [net] 25% hold of GASMAT/GASBOL

## Slide 9
Status of GSA
Can be terminated for:
Failure of YPF to meet CP’s [their control]
  Need to provide Consent to Assignment and Opinion
Failure of Plant to achieve Completion (on gas) by May 4, 01[our control]
Failure of project to close non-recourse project financing by May 4, 01 [our control]
Seek new GSA with Bolivian Providers, or
Revise YPF GSA for:
  lower price
  eliminate WTI/CPI basis risk (& GPDA)
  5 year make-up period