## Slide 1
Metering Authorized by ABX1 29
..”Thirty-five million dollars ($35,000,000) shall be used to provide time-of-use or real time meters for customers whose usage is greater than 200 kilowatt.”
CEC Metering Status – CPUC Workshop 5-21-2001

## Slide 2
CEC Functional Specification
CEC Metering Status – CPUC Workshop 5-21-2001
Utilities make all technology and vendor selections
Meter / System requirements
  CPUC approved, DA compatible, billing quality meter
  Communications - collect meter data no less than daily
  Budget Target - $1,400 per meter
Customer Communication requirements
  WEB or other access to load profile, pricing, system notices
  Graphical and tabular usage data no less than daily
  Service options or direct meter access to obtain more frequent access

## Slide 3
Participants
CEC Metering Status – CPUC Workshop 5-21-2001
Utility | Meters | Cost per Meter | Contract Type | Contract Status | Issues Features
PG&E | 10,000 | UN | Outsource | UN | meter cost, ITCC, O&M, authorization
SCE | 12,000 | UN | -- | -- | meter cost, ITCC, O&M, authorization
SDG&E | 600 - 2,500 | UN | -- | -- | meter cost, ITCC, O&M, authorization
LADWP | 3,418 | $1,405 | Direct | In process | Cost include 3 years comm. + O&M
SMUD | 200 | UN | Direct | UN | 
MID | TBD | TBD | TBD | -- | 
NCPA | TBD | TBD | TBD | -- | 
SCAPA | TBD | TBD | TBD | -- | 
TBD – to be determined. UN – under negotiation

## Slide 4
Major UDC Metering Issues - Options
CEC Metering Status – CPUC Workshop 5-21-2001
Cost
Time
Capability
$1,400 / meter
Target
Legacy Approach
Outsource Service Provider
Meters by 9-30
Meet Specifications
Substantially greater than Budget Target
Extend by 1-2 months
Meets Target
Meets Target
Extend by 1 month
Close to Budget Target

## Slide 5
Major UDC Billing Issues - Options
CEC Metering Status – CPUC Workshop 5-21-2001
Cost
Time
Capability
Not Specified
Target
Legacy Approach
Outsource Service Provider
Interim - by Tariff
Final – < 90 days
Meet Specifications
Interim - NA
Final - 4-6 mos
Uncertain
Meets Specifications
Less than Legacy Approach
$100 - $300 / yr
Interim - NA
Final – 1-3 mos