## Slide 1
New Generation in WSCC
Presentation
December 29, 2000
Proprietary and Confidential 5/02

## Slide 2: California
High Probability Plants: (UC) Under Construction (AP) Approved by CEC
  Seawest, 16 MW, Mar 2001(UC)
  Sutter, 500MW, Jun 2001(UC)
  Los Medanos, 500 MW, Jul 2001 (UC)
  La Paloma, 1,043 MW, Nov 2001(UC)
  Delta, 880 MW, Jul 2002 (UC)
  Moss Landing, 1,090 MW, Sep 2002(UC)
  Elk Hills, 500 MW, Dec 2002
  High Desert, 720 MW, Jan 2003 (AP)
  Sunrise, 320 MW, Jan 2003
  Otay Mesa, 510 MW, Jun 2003
  Pastoria, 750 MW, Jun 2003
Medium Probability Plants
  Metcalf, 600 MW, Feb 2003
  Blythe, 520 MW, Mar 2003
  Midway-Sunset, 500 MW, Mar 2003
  Contra Costa, 530 MW, Apr 2003
  Mountainview, 1,056 MW, Apr 2003
California
  Rosarito(Tijuana, MX), 255 MW, Apr 2003

## Slide 3: California Electricity Updates
California
Chula Vista, 49 MW peaker, Jun 2001, SP15. Limited to 48,000 annual MW output.
Golden Gate Power Project, 51 MW, Jul 01, NP15. Approval received by the CEC on Dec 8th for the four month approval process.
Warnerville, 86.4 MW, Oct 01, NP15. This project was canceled by Calpine on Dec 10th.
An additional 350 MWs of peaker P&W turbines have been directed to meeting this RFP by an independent developer. These are sited throughout the state. It is unclear how and when these will be sited but many of these will probably not meet the CISO target date of June 2001.
City of Escondido (SP15) has an RFP offering a site for a peaker to be installed by June 2001.
Elk Hills, 500 MW, Jul 2002, ZP26. Final approval was received Dec 6th with construction to begin Q1 2001.
Pastoria, 750 MW, June 2003, SP15. Final approval was received Dec 20th with construction to begin June 2001.
PEAKERS
The CISO has issued an RFP for 2,000 MW of peaking power to come online by Summer 2001. They have indicated that only 800 MW has been submitted.
Sunrise, 320 MW, ZP26, Aug 2001. Mission Energy was granted fast track approval to build the first phase for peaking power next summer. The peaking permit will be effective until December 31, 2002 at which time the unit will begin a conversion to CC.
Notes: CISO has reset target pricing mechanism for the real time energy imbalance market. The price of the highest decremental bids is greater than the price for the lowest incremental bid. The new price is to be greater of zero or the lowest incremental bid.

## Slide 4: PNW Updates
PG&E has announced plans for a phased expansion of the Pacific Northwest pipeline system. The first phase will serve primarily the California market The second mainline expansion, between 2003-2004, will also target generation demand in the Pacific Northwest and California. In addition, the company has another pipeline in development that will connect with the PG&E GT–NW system to serve the Seattle region. In total the expansions could yield as much as 1 billion cfd of new capacity on the PG&E GT–NW system.
Washington
  Fredrickson, 249 MW, June 2002. Turbines(7FA-7241) are scheduled for delivery in December. Herzog is finished. There are plans for an expansion of this facility in Q3-4 2003.
  Chehalis, 550 MW, June 2003. Construction set to begin June 13, 2001. TIC has been chosen as the EPC for this project. Turbines have been lined up to begin construction.
Oregon
  Klamath Falls, 500 MW, July 2000. Because tax-exempt financing was used for the project, 250 MW were set to be sold to tax exempt entities. There is still 100 MW left for sale. The plant developer is currently looking at the possibility of 250 MW expansion.
Idaho
  Rathdrum, 270 MW, 6,900 HR CC, Construction delays have pushed this online date from June 2001 to August 2001.
  Idaho Power Co has issued an RFP for 250 MW of peaking power installed by June 2004.
PNW
Notes: Formerly (stalled) NWPE 220 MW project. FPL bought rights in 1/99. Construction to began 9/1/99 As of 4/25/00 Unit 1 not complete and gas line construction has been stalled.

## Slide 5: PNW New Generation Map

## Slide 6: Rockies Updates
Colorado Office of Consumer Counsel claims that PSCO wasted $567 million by not building generation.(MWD 11/14/00) This did not stop the PUC from approving these purchases on Dec 14th.
North American Power Group has announced plans to invest $175 million in a new power line that would connect Colorado's Front Range with coal-fired generation resources in Wyoming and northern Colorado. If approved, the plans call for the project to be completed in 2004 and predict that 30% more power could be delivered to electricity markets in Colorado. The lines would run from northeast of Douglas, Wyoming into Colorado near Ault and south into metro Denver, according to WAPA.
Ft. St. Vrain, 235 MW (UC), June 2001. Construction has begun on this 3rd unit of existing 2 7FA converted nuke site.
Ray Nixon (Phase 2), 460 MW, May 2003. Not short listed, but will probably be built(80%).
PSCo has issued its “Recommended Plan” which shows 739 MW for 2002, 334 MW for 2003 and 516 MW 2004 for a total of 1,589MW.
PSCo has a $4.5 million DSM Request for Proposal for Bid 2001 which is roughly 362 MW.
Midway, 225 MW, Jul 2001. 6 x LM6000 Peaker. PPA signed for 11 year toll on Oct 15th. Air Permits received Oct 31st. County commission approval received Dec 14th.
Rockies

## Slide 7: Rockies New Generation Map

## Slide 8: DSW Updates
Arizona
  Red Hawk, 1,060 MW, Pinnacle West(APS), June 2002. Broke ground on Dec 19th.
  Panda Gila, 1,000 MW, Oct 2002. Project entered public notice phase on Dec 15th. Project has become a joint venture with Teco.
  Mesquite, 1,250 MW, Sempra, Jan 2003. Approval received on Dec 7th. Construction commencement is scheduled for Q2 2001.
  West Phoenix 4, 120 MW, Aug 2001. Major equipment delivery expected Dec 2000.
DSW
  Kyrene Expansion, 250 MW, Jan 2002. Expansion capacity was revised from 825 MW to 250 MW to meet community pollution concerns. Plan has expanded to a retrofit for emissions of existing units and the acquisition of local emission offsets.
Nevada
  Tahoe-Reno Industrial Center, 350 MW, Sept 2001. Foundation pouring began Dec 15th. Project is being constructed by Morgan-Stanley and Kansai Electric.
A $230 million pipeline, which would run 215 miles from Arizona to Mexico has been filed with FERC in October. The pipeline would begin at an interconnection with El Paso Natural Gas near Ehrenberg, Ariz., and cross California into northern Baja California, Mexico.

## Slide 9: DSW New Generation Map

## Slide 10: Summary
Summary
RO: Rockies DSW: Desert Southwest PNW: Pacific Northwest

## Slide 11
Bold items are shown on the preceding graph
Sorted List By Date

## Slide 12
Sorted List By Region

## Slide 13
Summer Summary
WSCC Capacity Additions
I. Sunrise Peaker, ZP26, 320 MW, Aug 01. Note: Rosarito(Not included), 450 MW, CFE, Aug 01. Rosarito is not connected to the CFE main grid, but it can export to SP15 during an emergency.
II. Elk Hills, ZP26, 500 MW, Jul 02.
I
II
III
III. Pastoria, SP15, 750 MW, Jul 03. Midway-Sunset, SP15, 500 MW, Mar 03.
IV. Valmont Repower , 37 MW, May 01. Midway changed to 225 MW, Jun 01.
IV
V
V. Kyrene Expansion , changed from 825 to 250 MW, Jan 02. Redhawk 1&2, 1,060 MW, Jun 02.
VI
VI. Moapa, 750 MW, May 03. West Phoenix 5, 530 MW, Aug 03.