## Slide 1
New Generation in WSCC
Presentation
July 24, 2000
Proprietary and Confidential 5/02

## Slide 2: Contents
Section Page
Sources ………………….……………….…..………………………………………. 3
Criteria…………………….…….…….…..……………………………………………4
Region-by-Region Evaluation …….…..…………………………………………… 5

## Slide 3: Sources
State Siting Offices
  CEC: Siting Division
  Oregon Siting Dept.
  Washington Siting Dept
  State Utility Commissions
PIRA, RDI, CEC Publications
Air Quality Districts
EPA
Zoning Districts
WSCC
Origination
Future Henwood
Notes: The California Energy Commission has the statutory authority to site and license thermal power plants that are rated at 50 megawatts and larger and related transmission lines, fuel supply lines and other facilities.
Contact: Mignon Marks (916) 654-4732
San Diego Air Pollution Control District
Contact: Marcie (858) 694-3979
San Joaquin Valley Air Pollution Control District
Contact: Steve Roeder (559) 230-5888Everett Planning and Community Development
Contact: Paul Roberts (425) 257-8731, Jerry Irvin
Origination: Steve Thome, Ed Clark, Frank Vickers,Dave Parque, Jim Buerkl, Saji John
PIRA
Contact: Jimmy Kow (212) 686-6808
CEC Report - MARKET CLEARING PRICES UNDER ALTERNATIVE RESOURCE SCENARIOS 2000 — 2010 Appendix C

## Slide 4: Criteria
Under Construction or Completed
Regulatory Approval Received
Application Under Review
Starting Application Process
Air Permit Approval
Press Release
Word-of-Mouth
Verify with Government Agencies
Verify with Origination
Speak with people on-site or with development
Check publications
Notes: Hydrology includes consumptive and non-consumptive rights
Model Run-of-River, Storage and Pump storage
Les Nicholson, Nevada Irrigation District
PGAE typically spills mid May - June
FERC license mandates minimum pool for flood control, in stream minimum flows. Corps of Engineers sets limitations for reservoirs during certain times of the year
Folsom Dam kept low in Oct and March. 1996 unusually early flood event got up to river capacity. Modifications were made to Folsom in order to release more water
Set of scalars and prices for different water years (good, average, bad) 1-2 std
Algorithm to optimize production from top units to units downstream
PGAE indicates that power contracts arenot for sale

## Slide 5: California
High Probability Plants: (UC) Under Construction (AP) Approved by CEC
  Los Medanos(Pitt), 500 MW, Jul 2001 (UC)
  Sutter, 500MW, June 2001(UC)
  La Paloma, 1,048 MW, Aug 2001(UC)
  Delta, 880 MW, Jul 2002 (UC)
  High Desert, 720 MW, June 2002 (AP)
Medium Probability Plants
  Elk Hills, 500 MW, Sep 2002
  Moss Landing, 1,090 MW, Oct 2002
  Otay Mesa, 510 MW, Nov 2002
  Pastoria, 750 MW, Jun 2003
  Blythe, 520 MW, Mar 2003
  Midway-Sunset, 500 MW, Mar 2003
  Contra Costa, 530 MW, April 2003
  Mountainview, 1,056 MW, April 2003
  Nueva Azalea, 550 MW, Jan 2004
California

## Slide 6: California Electricity Updates
Sutter, 500 MW, NP15 (UC). The construction manager indicated that this project is on an accelerated schedule and start date should be June 2001 rather than Sept.
High Desert, 720 MW, Dec 2002, SP15. Approved by CEC. Water issues regarding access to SWP water. Strong local support of plant after loss of the airbase.
Otay Mesa, 510 MW, Nov 2002, SP15. Air quality issues are currently being addressed. It is unclear if this will affect the current projected start date of Nov 2002.
California
Sunrise, 320 MW, Aug 2002, ZP26. Environmental and legal issues with Texaco. Plant will probably not be built.
Metcalf, 600 MW, Dec 2002, NP15. CEC and local officials have suggested this not be sited in the Coyote Valley because of water quality and the existence of a rare local butterfly. Plant will probably not be built.
Moss Landing, 1,060 MW, NP15. Duke said that if reregulation occurs that this plant will not be built.
Notes: CISO has reset target pricing mechanism for the real time energy imbalance market. The price of the highest decremental bids is greater than the price for the lowest incremental bid. The new price is to be greater of zero or the lowest incremental bid.

## Slide 7: PNW Updates
Washington
  Everett Delta, 248 MW, Construction halted, this project has been mothballed by FP&L.
  Fredrickson, 249 MW, Engage Energy. Previous site of BPA’s Tenaska power project. Engage began siting process again in Jan 2000. They are expecting to receive final permits in the next few weeks. Unknown start date.
Oregon
  Klamath Falls, 500 MW, July 2001
  Vestas Wind 100 MW incremental capacity, Jan 2001, Umatilla County, 35% Capacity factor.
  Coyote Springs Phase 2, 231 MW, June 2002
  Hermiston, 536 MW, May 2002
Idaho
  Rathdrum, 270 MW, 6,900 HR CC, June 2001. Published start date is Dec 2000, developer had estimated Aug - Sept 2001. No weather delays means they now expect June 2002 startup.
Wyoming
  Foot Creek #4 Wind, 17 MW, June 2000
PNW
Notes: Formerly (stalled) NWPE 220 MW project. FPL bought rights in 1/99. Construction to began 9/1/99 As of 4/25/00 Unit 1 not complete and gas line construction has been stalled.

## Slide 8: Rockies Updates
Manchief (Brush), 265 MW (UC), Original on-line date June, 2000. Encountered testing delays on-line date now set to July, 20th 2000.
Ft. St. Vrain, 235 MW (UC), June 2001, Construction has begun on 3rd unit of existing 2 7FA converted nuke site.
Ray Nixon (Phase 2), 460 MW, January 2003. Not short listed, but will probably be built.
Powhatan 48, 150 MW, May 2002. This project was not short listed in PSC RFP and is not expected to be built.
PSCo has issued its “Recommended Plan” which shows 739 MW for 2002, 334 MW for 2003 and 516 MW 2004 for a total of 1,589MW.
PSCo has a $4.5 million DSM Request for Proposal for Bid 2001.
Source: PSCO 1999 Integrated Resource Plan
Rockies

## Slide 9: DSW Updates
Arizona
  South Point Power Plant (UC) [Mojave], 545 MW, construction manager indicated that this project is on an accelerated schedule Mar 2001 rather than May 2001
  Griffith Energy Project (UC), 520 MW, May 2001. The “absolute drop dead date” is July 2001
  Desert Basin Generating (UC), 560 MW, June 2001, 7,000 Heat Rate
  West Phoenix 4- Repower, 70 Incremental MW, August 2001
  West Phoenix 5- New Build, 500 MW, December 2001
  Arlington Valley, 550 MW, Duke, August 2002. They should receive permit approval in the next 2 weeks.
New Mexico
  Cobisa Person, 140 MW, On-line date listed of May 2000 was incorrect. Actual start date was July 10, 2000.
Nevada
  Las Vegas CoGen Expansion, 250 MW, June 2002
DSW

## Slide 10: Summary
Summary
RO: Rockies DSW: Desert Southwest PNW: Pacific Northwest

## Slide 11
Bold items are shown on the preceding graph
Sorted List By Date

## Slide 12
Sorted List By Region