## Slide 1: Next Steps
09/27/25 01:13 AM
This report is solely for the use of client personnel. No part of it may be circulated, quoted, or reproduced for distribution outside the client organization without prior written approval from McKinsey & Company. This material was used by McKinsey & Company during an oral presentation; it is not a complete record of the discussion.
CONFIDENTIAL
December 15, 2000

## Slide 2: ENRON ACCELERATOR – IMPLEMENTATION TIMELINE
Estimated timing
Activities
Put Accelerator implementation team in place
  Select membership (leadership, full time working team)
  Provide expectations (e.g., vision, timetable, ground rules)
Develop Accelerator’s charter
  Outline strategic intent/mission
  Establish focus of Accelerator – ground rules for what’s in and what’s out
  Define services provided
  Syndicate with key business unit leaders
  Establish internal funding parameters
Design architecture
  Seek agreement on legal structure
  Flesh-out Accelerator organization/roles
  Build appropriate linkages to other parts of the organization
Design governance model
  Define roles and responsibilities of the advisory board and investment committee
  Select membership
Create processes/decision rules for developing ideas:
  Collecting ideas
  Evaluating ideas
  Funding ideas
  Staffing ideas
  Divesting/spinning-out/reacquiring/ terminating ideas
January
February
March
April
May
Progress
review
Progress
review
DRAFT
Notes: <number>
txho/NextSteps06 ENX119.ppt
<header>

## Slide 3: ENRON ACCELERATOR – IMPLEMENTATION TIMELINE (CONTINUED)
Estimated timing
Activities
Create processes/decision rules for using internal resources and building linkages with other parts of the organization
Determine staffing and support services needs
  Venture management
  Portfolio management
  Administrative roles
    Recruiting
    Budgeting/financial/accounting
    Legal
    Other
  Secure physical location
Develop compensation structure for Accelerator participants/support
Develop budget
Formulate and execute communication strategy to the organization
Launch
January
February
March
April
May
Progress
review
Progress
review
DRAFT
Notes: <number>
txho/NextSteps06 ENX119.ppt
<header>

## Slide 4: TRANSITIONING TO THE PARTNERSHIP MODEL - IMPLEMENTATION TIMELINE
Estimated timing
Activities
Put partnership implementation team in place
  PRC leadership
  Support
Apply partnership architecture to existing organization
  Identify partnership tracks (on a role by role basis)
    Refine/finalize decision rules
    Apply decision rules across organization
  Highlight and justify any exceptions
Upgrade personnel evaluation tools
  Establish partnership election criteria to be applied to each track of candidates
  Develop performance criteria for each track and each level, with representative descriptions for each of the five levels of performance
  Determine systems requirements
Codify personnel processes
  Identify roles and responsibilities of personnel committees
  Outline criteria for committee membership
  Define personnel-related activities for all partners
    Personnel review requirements for each level (e.g., feedback collection forms, summary tools)
    Annual review/committee schedules
  Estimate time requirements for partners, including those on the personnel committees
January
February
March
April
May
Progress
review
Progress
review
DRAFT
Notes: <number>
txho/NextSteps06 ENX119.ppt
<header>

## Slide 5: TRANSITIONING TO THE PARTNERSHIP MODEL - IMPLEMENTATION TIMELINE (CONTINUED)
Estimated timing
Activities
Build PRC
  Identify number of PRC members required
  Select chairs
  Review current membership, determine whether there should be changes
  Identify potential members
  Finalize membership
Outline governance structure
  Codify roles and responsibilities for the:
    Corporate Policy Committee
    Executive Committee
  Outline criteria for governance committee membership
  Estimate time requirements for governance committee members
Evaluate/Implement compensation system consistent with partnership model
  Structure the deferred compensation program for all partners
  Determine how “share” of the partnership pool is determined/divided
Match people with roles
  Make determination on initial partner group (i.e., are all current VPs and MDs partners?)
  Populate all committees with individual names
Structure/execute communication strategy
Launch mid-year review cycle
  Revise evaluation tools as required
January
February
March
April
May
Progress
review
Progress
review
DRAFT
Notes: <number>
txho/NextSteps06 ENX119.ppt
<header>

## Slide 6: DEFERRED PARTNERSHIP COMPENSATION PROGRAM – IMPLEMENTATION TIMELINE
Estimated timing
Activities
Put team in place to implement a deferred partnership compensation program
Target size of total compensation at risk for partners, and share dedicated to the deferred compensation pool
Identify investment/divestment decision criteria and processes for deferred compensation pool
  Investment board
    Roles and responsibilities
    Membership
  Types of investments targeted
  Decision rules
Determine how participants will extract value
  Restricted stock/stock with caps
  Liquidity puts
Structure overall investment vehicle
  “Units” in pool vs literal options/stock
  Yearly investment “vintages” vs ongoing additions and management of entire pool
January
February
March
April
May
Progress
review
Progress
review
DRAFT
Notes: <number>
txho/NextSteps06 ENX119.ppt
<header>

## Slide 7: DEFERRED PARTNERSHIP COMPENSATION PROGRAM – IMPLEMENTATION TIMELINE (CONTINUED)
Estimated timing
Activities
Design/document valuation methodology and frequency
Resolve outstanding accounting/legal issues associated with:
  Creating many minority-interest stock holders
  Individuals continually entering and leaving the partnership
  Limitations of liquidity puts (e.g., may require individual to hold stock for 6 months after “divesting” from pool)
Structure/execute communication strategy
January
February
March
April
May
Progress
review
Progress
review
DRAFT
Notes: <number>
txho/NextSteps06 ENX119.ppt
<header>