## Slide 1
8/01 9 10 11 12 1/02 2 3 4 5 6 7 8 9 10 11 12 1/03 2 3
Most Probable
“4.0 BCF Date”
BHLP
Contractual
4.0 BCF Date
??
Inject 3.85 BCF Pad Gas
Into ENE #1
Inject 4.0 BCF Working Gas
Into ENE #1
Inject 3.0 BCF Additional
Working Gas (total 7.0)
BHLP
BHLP
BHLP
ENE Pays
Provide Brine “Takeaway”
Service for 3.0 BCF
ENE
Remove pad gas from Dow 13 & 14
Forward sale “hedge” for physical flow
2.8 BCF
Removal of remaining 1.08 BCF Pad
ENE
ENE
Here’s the Problem - - - Time to Re-Water
??
??
??
??
Completely exit Dow wells (Dow View)
Completely exit Dow wells (ENE View)
220
Pays
Dow Storage Agreement as Amended
303
Pad 111 Days
Working 114 “
Operational - 225
Interruptions 45 Days
270

## Slide 2
Assumptions:
1.) Primary ENE goal is to complete contribution to Bridgeline, which includes:
a.) 3.85 BCF pad gas in ENE #1
b.) 4.0 BCF working capacity (of
7.0 total in ENE #1)
c.) Construction of P/L and other
facilities (complete).
d.) Brine removal service for
Bridgeline’s 3.0 BCF working
capacity.
2.) All working gas from Dow 13/14 removed by 4.0 BCF date.
7.8 BCF
3.77
8/01 1/02 3/02 1/03 2/03

## Slide 3
Constraints/Contingencies:
1.) Bring “take-away capacity from ENE #1:
a.) If <2000 GPM, Dow 13/14
storage agreement extended
proportionately (Dow’s fault!).
2.) Provide 4.0 BCF working capacity at all times.
3.) Brine delivery rate to Dow 13/14.
a.) Best efforts.
b.) Conservative estimate = 2.8
BCF during 8 month period:
8/02 – 3/03.
Concerns:
1.) Does termination of Dow storage include removal of pad gas?
-- Dow = yes
-- ENE = no
I.E. – What does “Completely exit” mean?