## Slide 1
Vision Document
for
Project Green Light
Accurate, Complete and Efficient Risk Measurement and Reporting
10 September 2001
DRAFT FOR DISCUSSION ONLY

## Slide 2: Contents
Background
Objectives
Scope
Approach
Project Team Organization
Project Schedule

## Slide 3: Executive Summary

## Slide 4: Background
RiskTrac
VaR
Positions
Officialized ID’s
DPR reporting
Source systems
Other downstream systems (CAS, Infinity)
VaR reporting
Benchmarks
1
3
2
1
BA failed to officialize book
BA failed to mark book as Active
Incompatible book attributes (ERMS)
Spreadsheet / file load failure
Long processing times (ERMS)
4
3
Incomplete book / curve set-up
2
Timing difference (VaR runs later than CAS, Infinity)
Inconsistent rules on un- and re-officializations
4
Unmapped curve
Curve = 0
Wrong correlations
Incorrect portfolio aggregation
Book was officialized after VaR runs at 6:15AM
Potential Failures from Current Risk Systems and Processes
5
5
Lack of cross-checks and exception reporting across systems

## Slide 5: Background, continued
Key Issues
  Long RiskTrac loading times from ERMS and some spreadsheets (book admins waiting 2-3 hours to confirm RiskTrac loads)
  Manual, tedious and error-prone processes of creating books and managing book attributes
  Different cut-off times for VaR, credit (CAS) and Infinity
  Inconsistent system rules on un- and re-officialization
  Unreliable, Excel-based benchmark position reporting
  Limited VaR diagnostic capabilities
  “Over-centralized” maintenance of VaR inputs
  Limited exception reporting and reconciliation mechanisms
1
2
3
4
5

## Slide 6: Objectives
The main objective of Project Green Light is to enhance current risk controls systems and processes to ensure that risks are measured and reported in an accurate, complete and efficient manner
Work groups to address different components of this objective include:
  Source feeds processing: Enhancing the timeliness and accuracy of information flow from source into risk systems
  Data validation: Ensuring the correctness of current RiskTrac system configuration and developing processes to efficiently maintain system accuracy and reliability
  Business process: Documenting current business processes, identifying opportunities for improvement, and putting new processes in place to implement solutions identified by the other work groups

## Slide 7: Scope
Project Green Light will focus on resolving issues involving ERMS, EnPower and spreadsheet feeds into RiskTrac, Credit and Infinity for gas, power, EGM and UK groups. For purposes of completeness, the project will also identify any issues with all other groups
Project Green Light will focus on the flow of information from the source systems upon officialization. Issues on deal-entry, valuation and calculating of deals will be out of scope
Some of the solutions that will be implemented will be short- to medium-term “fixes” to address some of the more immediate issues (like long processing times and time-consuming issues resolution). The project assumes, however, that a longer term system solution like Enlighten and Global Valuation will eventually be implemented

## Slide 8: Project Team Organization
Steering Committee
Jeff Gossett Mike Jordan
Debbie Brackett Shona Wilson
Program Mgt. Office
Tom Victorio UK (James New?)
Source Feeds Processing
ERMS, EnPower, UK
Data Validation
Gas, Power, Global Products, UK
Business Process
Gas, Power, Global Products, UK
Source Systems IT (ERMS, EnPower, UK)
RiskTrac IT
Commodity Risk Groups (Gas, Power, Glob. Products, UK
Global Risk Ops
Project Sponsor
Sally Beck Rick Buy

## Slide 9: Approach
Gather requirements from business and system groups
Plan and initiate improvement projects
Implement and manage systems and process changes
Draft continuous and long term improvement plans
Source feeds processing
Data validation
Business process
ERMS
EnPower
UK
RiskTrac
CAS
Infinity
DPR

## Slide 10: Approach, continued
Source Feeds Processing
Success measures
Reduced waiting times to confirm information loads into RiskTrac
Capability to measure percentage of daily positions loaded / not loaded into RiskTrac
Identify positions not currently being captured in RiskTrac (and measure as a percentage of total Enron positions)
Plan for measuring and reporting risk for non-RiskTrac positions
Data Validation
Success measures
Achieve > 95% success rate of daily RiskTrac loads
Reduced time and effort spent on issues resolution
Efficient and reliable RiskTrac hierarchy structure that enables VaR reporting for all relevant portfolios
Reduce number of unused books, portfolios, curves
Business Process
Success measures
Definition of risk controls processes and responsibilities
Transition plan to new processes and roles

## Slide 11: Approach, continued
Source Feeds Processing
Initial list of projects
Faster ERMS post-ID resolution
Running parallel RiskTrac load processes
ERMS function to prevent officialization of empty books
Address inconsistent un- and re-officialization processes across risk systems
Address inconsistent processes when the system finds no post-ids (eg. Infinity takes previous day’s data, RiskTrac does not)
Determine impact of Enlighten
Resources
Project Manager – Greg Couch
RiskTrac IT
ERMS IT
Data Validation
Initial list of projects
Determine correctness of current RiskTrac set-up
  Confirm accuracy of portfolio / book structure (no duplicates, all positions captured)
  Check curve mappings
Develop efficient and reliable daily exception reporting and cross-checking
  Officialization loads
  VaR diagnostic report
  Business rules around exceptions (eg. materiality)
Enhance RiskTrac reporting capabilities
  Benchmark position reporting and DPR loads
  VaR reporting and DPR loads
Resources
Project Manager – Gary Stadler (?)
Global Risk Ops
RiskTrac IT
Business Process
Initial list of projects
Develop book archiving process
Re-define RiskTrac user roles and responsibilities
Re-define risk controls processes and and segregation of responsibilities
Document current RiskTrac set-up procedures and develop checklists
Improve RiskTrac user processes
  Moving sub-portfolios (drag-and-drop)
  Renaming books (for books with no trade history yet)
  Develop tool for assigning books to portfolios
  Online book request (online form with input validation, automatic table updates)
Resources
Project Manager (?)
Global Risk Ops
RiskTrac IT

## Slide 12: Project Schedule
Need to determine timeline for each project in each workgroup