## Slide 1: ERCOT QSE Project Manager Meeting Program Status and Purpose of the Meeting
November 15, 2000
Steve Grendel
Director of Information Technology

## Slide 2
ERCOT Project Organization

## Slide 3
Apr 30: Business Architecture Developed
7/00
10/00
4/01
1/01
Mar 1: Package 1, 2, 3 Integration Testing Completed
Mar 15: Cross Package Integration Test Completed
Jun 1: Pilot Cutover Completed
Apr 1: Mock Market Initiated
Mar 28: Business Test Completed
Aug 1: Package 1 and 2 Design Competed
Jun 1: Package 3 Requirements Completed
Oct 15: Package 3 Design Competed
Nov 30: Package 1 and 2 Build Competed
Jan 1: Package 3 Build Competed
May 25: Mock Market Test Completed
May 15: Package 2 Requirements Completed
May 1:
PMO Established
We Are Here
Jul 1:
Early Delivery of Frequency Control
Sep 1:
TCH Data Validation Tool Completed
QSE Project Manager Meeting Goals
Notes: There will have been an overview presentation given on Day 1 of the session that covers some of the high level topics including the application landscape (i.e. what are the major parts of the system, what packages are being used, what infrastructure is being developed, etc.)

## Slide 4
QSE Project Manager Meeting Goals
Notes: There will have been an overview presentation given on Day 1 of the session that covers some of the high level topics including the application landscape (i.e. what are the major parts of the system, what packages are being used, what infrastructure is being developed, etc.)

## Slide 5
    To establish a line of communications with QSE project managers
    Assure clear communication of QSE qualification activities and timelines
    To coordinate QSE system(s) and organizational readiness activities with ERCOT including testing and training activities.
    Provide a focused forum for QSE project managers to provide feedback and request information.
QSE Project Manager Meeting Goals
Notes: There will have been an overview presentation given on Day 1 of the session that covers some of the high level topics including the application landscape (i.e. what are the major parts of the system, what packages are being used, what infrastructure is being developed, etc.)

## Slide 6: QSE Project Manager Meeting Goals
    Facilitate readiness tracking of QSEs by ERCOT.
    Develop and maintain a QSE readiness presentation to the ERCOT Board of directors at each board meeting.
    Reach agreement of the format and schedule for future QSE project manager meetings.
    Identification of any additional focused implementation groups
Notes: There will have been an overview presentation given on Day 1 of the session that covers some of the high level topics including the application landscape (i.e. what are the major parts of the system, what packages are being used, what infrastructure is being developed, etc.)

## Slide 7: QSE Project Manager Meeting Goals
    This is not a PIW meeting (No gap analysis review)
    We are not here to change policies or market rules
    We are here to coordinate implementation
    This is not a MRS training session
Notes: There will have been an overview presentation given on Day 1 of the session that covers some of the high level topics including the application landscape (i.e. what are the major parts of the system, what packages are being used, what infrastructure is being developed, etc.)