## Slide 1: ERCOT QSE Project Manager Meeting ERCOT Organizational Readiness
November 15, 2000
Steve Grendel
Director of Information Technology

## Slide 2: QSE Project Manager Meeting
AC/Consortium activities
Additional ERCOT readiness activities
Notes: There will have been an overview presentation given on Day 1 of the session that covers some of the high level topics including the application landscape (i.e. what are the major parts of the system, what packages are being used, what infrastructure is being developed, etc.)

## Slide 3: AC/Consortium activities
Conduct biweekly project meetings with AC and ERCOT project leads
  Review high level schedule
  Scorecard Summary (Color Coded)
    Schedule
    Financials
    Program Team (Staffing)
    Quality & Satisfaction
    Risk Management
  Schedule Review – Milestones (47, 11 LD)
    April 10th , 2000 – June 1 ,2001
    Due Date and Signoff Condition
    Recently completed milestones
      Package 3 Design completed on October 15th
      Portal Release 2 commpleted on October 31st
    Next milestones
      Package 1 build complete
      Package 2 build complete
      POS Databases and 1-line displays converted December 31st.
      Overall Program Training Materials Developed – February 15th.

## Slide 4: AC/Consortium activities
Conduct biweekly project meetings with AC and ERCOT project leads
  Schedule Review – Activities
    Prime/Integration
    Package 1 – Operations Systems
    Package 2 – Commercial Operations
    Package 3 – Data Archive/Data Warehouse
  Risk Analysis
    Identification of risks and potential implications
    Document Mitigation Approach
    Color Coded Status
  Current risk issues
    Misalignment of Expectations between consortium and ERCOT
      Current status – “Yellow”
      Mitigation – Prime and Package 1,2 and 3 proactively and jointly document milestone sign-off forms and acceptance criteria with ERCOT.
    Lack of Market Participant Preparedness
      Current status – “Green”
      Mitigation – Provide clarity associated with preparedness expectations on the “Texaschoice” website and during MRS sessions.
      Track participant readiness individually following declaration.

## Slide 5: AC/Consortium activities
Conduct biweekly project meetings with AC and ERCOT project leads
  Current risk issues
    Misalignment of Expectations between consortium and ERCOT
      Current status – “Yellow”
      Mitigation – Prime and Package 1,2 and 3 proactively and jointly document milestone sign-off forms and acceptance criteria with ERCOT.
    Lack of Market Participant Preparedness
      Current status – “Green”
      Mitigation – Provide clarity associated with preparedness expectations on the “Texaschoice” website and during MRS sessions.
      Track participant readiness individually following declaration.
  Identify Key issues resolved since last meeting
  Identify Key open issues
  Review current tracking statics
    Activity on “Texaschoiceprogram.com”
    EDI Technical Connectivity Statistics.
    Request for NDA to gain access to design documents

## Slide 6: Additional ERCOT Readiness activities
ERCOT conducts biweekly project meetings
Staffing activities (currently 100 employees going to 238)
ERCOT Operation readiness timelines developed and tracked.
  Organizational design and staffing
  Facility construction and readiness
  WAN implementation
  Additional Market Readiness activities
  AC project supporting activities

## Slide 7
ERCOT Testing Organization

## Slide 8
ERCOT Project Organization