## Slide 1
Financing Update

## Slide 2
Monthly Progress
Shut down Lender’s counsel until CP’s can be delivered as package
Received Lender go ahead of Siemens EPC & TAA contract revisions
Obtained Lender’s go ahead on revising GSA
Progressed on getting Lenders to consider alternatives to the Furnas Consent
Lenders agreed that they would not unreasonably withhold right to sell down 100% of EPE subject to review of new sponsor’s credit and integrity

## Slide 3
Status of CP’s
Obtain Furnas Consent
Validate Eletrobras Guarantee
Revise Siemens EPC to maintain performance test standards on Gas and TAA
Finalize Budget and Model
New Action Plan for Ridges
Obtain Petrobras consent
SIRESE approval of Andina transportation capacity Assignment
Tozzini Briefing on Interconnection Agreement liability

## Slide 4
Furnas/Eletrabras Issue - New Lender Proposals
Proposal 1 - With Eletrobras Cooperation
Obtain Eletrobras consent and opinion of enforceability from counsel (perhaps broaden their guarantee somewhat)
Rely on strong Furnas obligation to sign original Consent from Assumption Agreement and Eletrobras performance guarantee under Clause 41 of PPA and Sections 6 & 7 of the Assumption Agreement
Utilize legal process involving registered notification to Furnas of lender consent required for EPE to revise documents and Golden Quota in lieu of Consent

## Slide 5
Furnas/Eletrabras Issue - New Lender Proposals
Proposal 2 - Without Eletrobras Cooperation
Consider “Expert” 3rd Party Legal Brief for Eletrobras Obligations (review similarities of situation for EXIM & IADB in Mexico)
Rely on strong Furnas obligation to sign original Consent from Assumption Agreement and Eletrobras performance guarantee under Clause 41 of PPA and Sections 6 & 7 of the Assumption Agreement
Utilize legal process involving registered notification to Furnas of lender consent required for EPE to revise documents and Golden Quota in lieu of Consent

## Slide 6
Reason for Lenders to Consider New Proposals
Failure of the Lenders to consider alternatives will force us to pursue litigation or arbitration to resolve the conflict with consequent delay and acrimony
Forcing Furnas to sign through arbitration and litigation would only provide Lenders with the signature of an unwilling party
Tozzini does not feel that our right to a Furnas Consent under the Assumption Agreement have been altered by the negotiations and alternate versions
Furnas is using the consent as leverage to pursue its own agenda
The re-negotiation Furnas desires would introduce new liabilities to the project which would be unacceptable to the Lenders
OPIC’s mandate to provide an advantage for US Sponsors
Lenders are essentially imposing additional requirements on borrower because of concerns about off-taker
Eletrobras clearly provides guarantee for payment so if all situations which concern the lenders can be crystallized into damages then we would always have Eletrobras on the hook (problem is 90 days grace period)

## Slide 7
Structure of Enron Back-up Fuel Supply Agreement, put to Enron (“Agreement and Guarantee”), and Replacement Fuel Contract.
If the YPF contract is terminated Enron will be the interim fuel supplier under the “Back-up Agreement” from the Funding Date until March 31, 2002. This is a financial obligation and no demonstration of physical reserves or delivery capability is required. However, Enron pays LD’s for failure to provide gas with virtually identical performance terms to the YPF contract except Non-cover LD’s increased to US$12MM max (vs only $4MM under the YPF contract).
Jan 1, 2002 – Enron required to submit documentation evidencing satisfactory arrangement for physical delivery under a “Replacement Fuel Agreement” including details of reserves, transportation, and supplier creditworthiness. This is essentially an obligation to establish a new long-term gas supply arrangement similar to the YPF arrangement.
By March 31, 2002 Lenders to complete evaluation of Replacement arrangements and indicate acceptance or rejection.
If Replacement arrangements rejected, Enron debt guarantee is triggered and if acceptable Replacement arrangements not developed and submitted by Jan 1, 2003, then the Lenders may put the debt to Enron on March 31, 2003.