## Slide 1: Timeline for Federal Regulatory Approvals of PGE Sale
October 31, 2000

## Slide 2: Status of FERC Proceeding
We have been told that FERC is trying to issue an order by November
  FERC meetings on November 8 and November 22
  We will know by November 1 whether the proceeding is on the FERC agenda for November 8 – Most likely not on November 8 agenda
  FERC will either approve the merger or set it for additional proceedings (technical conference or hearing)

## Slide 3: Possible Outcomes (Assuming No Settlement)
FERC Approves Merger Without Requiring Technical Conference or Hearing (55% Likelihood)
FERC Sets Merger for Technical Conference (35% Likelihood)
FERC Orders a Hearing (10% Likelihood)
FERC Approves Merger For a May 5 Close After Technical Conference is Held (80% Likelihood)
FERC Sets the Merger for Hearing After Technical Conference if Material Issues of Fact Remain (Less than 10% likelihood, provided Sierra does not do anything new to alienate FERC)

## Slide 4: Settlement with TANC and SMUD
If we reach a settlement with TANC before FERC sets the proceeding for technical conference
  Remaining protests (provided Nevada Commission withdrawals) are RTO related and should not delay FERC approval
  FERC would be unlikely to schedule technical conference without TANC opposition
FERC would likely issue an order approving the merger within 6-9 weeks after settlement is filed

## Slide 5: No Settlement with TANC and SMUD
FERC approves merger in its November 22 order without additional proceedings
  55% Likelihood
FERC sets the proceeding for technical conference (35% Likelihood)
  Order issued November 22
  Technical conference in first week of December, FERC order on the merits by late January to mid-February
  Less than 10% likelihood that FERC will set for hearing after technical conference
  FERC sets the proceeding for hearing without technical conference first (10% likelihood)

## Slide 6: Settle with TANC After FERC Orders Technical Conference
If a settlement is reached, parties would request FERC to defer technical conference (more than 90% likelihood that FERC would grant this request)
  Order on the merits should be issued 6-9 weeks after settlement is filed)
If technical conference is held, the timing of an order on the merits should not change much from timing without a settlement
  Order on the merits should be issued late January to mid-February

## Slide 7: Timeline for FERC Hearing
If FERC sets the proceeding for hearing in its November 22 order, and establishes an aggressive timeline, FERC should issue an order on the merits by September, 2001.

## Slide 8: SEC Action
SEC will likely take 60-90 days to approve the merger after FERC issues its order on the merits
If FERC conditions the merger on Sierra doing additional mitigation, these conditions should not delay SEC review of the application
SEC has indicated it intends to take up the application at the first of the year
SEC is targeting late February to end of first quarter to issue its order