## Slide 1
Define
Problem /
Issues
Design
Solution
Framework
Develop
Strawman
Charter
Complete
Draft
Deliverable
Steps
Actions
Who
Identify Council subgroup members
Develop process and timeline
Interview / phone call with key Council members
Document issues
Define problem
Review issues identified
Develop high level solution framework
Email framework and key questions to Council subgroup
Interview / conduct conference calls with Council subgroup
Develop draft strawman charter
Email draft strawman charter to the Council subgroup for feedback
Collect and analyze feedback
Incorporate feedback into strawman
Complete draft deliverable
K. Schwab, D. Redel
J. Schiro and selected council members
PwC Team
PwC Team
PwC Team
Council subgroup
K. Schwab, D. Redel
PwC Team
Council subgroup
28 Sep
2 Oct
9 Oct
19 Oct
Process Framework

## Slide 2: Key Questions
A few questions to consider:
  What are some of the key pressures confronting the WEF?
  What is the value of creating a Global Business Council?
  What will the GBC do (ie role/function)?
  How should the GBC be positioned within the WEF?
  How will we practically implement the GBC?