## Slide 1
October 3, 2000
Confidential & Proprietary
Management Presentation
Enron Generation Overview - Pastoria

## Slide 2
Pastoria Energy Facility

## Slide 3: Project Overview
750 MW (nominal) natural gas-fired, combined cycle plant
Site, located in Kern County, 30 miles south of Bakersfield, will be leased from Tejon Ranchcorp (“Tejon”)
Electrical interconnection with Southern California Edison (“SCE”) at the 230 kV Pastoria Substation
Gas interconnection with Kern/Mojave pipeline
Water will be supplied by the Wheeler Ridge Maricopa Water Storage District (“Water District”) and Azurix (an Enron affiliate)
Merchant plant will sell its output into the power markets of the California Power Exchange (“PX”) and the California Independent System Operator (“ISO”)
In advanced stage of development
California Energy Commission (“CEC”) declared the Application for Certification (“AFC”) “Data Adequate” on January 26, 2000 and is expected to issue its final decision in November 2000
Pastoria Overview

## Slide 4: Development Strengths
Attractive location
  SCE power transmission
  SP-15 pricing zone
  Kern/Mojave gas pipeline
    Avoids intrastate transportation charges
  San Joaquin Valley Unified Air Pollution Control District
    No impact from South Coast Air Quality Management District reclaim issues
Additional value from potential contract with California Department of Water Resources (“CDWR”), expansion and reliability-must-run (“RMR”) contract
Power islands have been secured
EPC contract has been negotiated but not signed
ERCs have been obtained
Significant barriers to entry by competitors
Pastoria Overview

## Slide 5: Additional Value Opportunities
Pastoria Overview
Additional value being pursued by ENA
  Expansion of Pastoria to 1,000 MW and a possible RMR contract
  Bilateral contract with CDWR re: Edmonston Pumping Station
Each opportunity must be priced in addition to the base offer

## Slide 6: Expected Timeline
Pastoria Overview

## Slide 7: Permitting/Approval Process
Pastoria Overview

## Slide 8: Williamson Act
Pastoria Overview
Site is currently subject to the Williamson Act (the “Act”)
The Act is a land-use policy enacted to preserve land and agricultural purposes
Implemented through a contract between the landowner and the county
To remove land from the Act
  Approval of County Board of Supervisors
  Expiration of appeal period
  Pay cancellation fee
ENA has
  Obtained Kern County Board of Supervisors’ approval
  Reduced the appeal period through passage of legislation
California Assembly Bill 2698, signed into law by the Governor on September 29, 2000, reduces the 180-day appeal period to same time frame as the rehearing period for the CEC final decision

## Slide 9: Interconnections
Electrical
  Interconnect to the SCE Pastoria Substation – 1.38 miles
  Double circuit, 230 kV
  Impact study has been completed; facility study to be issued in mid-October
  Negotiations on Interconnect Agreement to begin upon issuance of facility study
Gas Transportation
  Interconnect with the 42-inch Kern/Mojave pipeline – 11.65 miles
    Possible gas sources include Canada, Rocky Mountains, California and Permian Basin
  24-inch pipeline
  700-900 psig
  LOI currently under negotiation
Pastoria Overview

## Slide 10: Site Overview
Pastoria Overview

## Slide 11: Equipment Overview
Two power islands in a “two-on-one” and “one-on-one” configuration comprised of:
  three GE 7FA combustion gas turbines
  one GE D11 steam turbine
  one GE A11 steam turbine
  three HRSGs
Emissions will be minimized through the use of Best Available Control Technology
  Pastoria will have the option to utilize
    XONON technology
    SCRs
Cooling towers
Zero discharge wastewater system
Pastoria Overview

## Slide 12: Key Project Agreements
Tejon Agreements
  Transaction Agreement
  Option Agreement
  Ground Lease
  Easement Agreement
Agreement for Combined Cycle Power Islands
Engineering Procurement and Construction Turnkey Contract
Water Supply Agreements
  Water District
  Azurix
Labor Agreements
Pastoria Overview

## Slide 13: Tejon Agreements
Pastoria Overview
Transaction Agreement
  Outlines relationship between Pastoria and Tejon (site lessor)
Option Agreement
  Grants Pastoria the option to lease the site and acquire easements
  Six-year option term
Ground Lease
  25-year term
  Options to extend for three five-year terms
  Fixed rent
  Variable rent based on spark spread
Easement Agreement
  Establishes terms regarding laterals for access, transmission, gas and utilities

## Slide 14: Agreement for Combined Cycle Power Islands
Pastoria Overview
Pastoria has secured rights to two GE power islands
  Rights are assignable
Contains market-based terms, including performance and delivery guarantees
Deliveries will support a June 2003 commercial operations date

## Slide 15: Engineering, Procurement and Construction Turnkey Contract
Pastoria Overview
Contract between PEF and NEPCO (an Enron affiliate) has been completely negotiated, but not executed
Contains market-based terms, including performance and completion guarantees
Purchaser and NEPCO each will have the option to execute
If NEPCO contract is pursued, signing cannot occur earlier than 14 days after closing of the Pastoria transaction

## Slide 16: Water Supply Agreements
Water District
  Will provide primary supply of up to 5,000 acre-feet per year
  Judgment validating contract became final September 30, 2000
Azurix
  Will provide a guaranteed back-up supply and scheduling services
  Pastoria must exercise an option in 2001 and pay $6,500,000 to acquire rights to 40,000 acre-feet of water and trigger Azurix’s obligations
  Payments of $500,000 per year and $550 per acre-foot will cover purchases from the Water District and Azurix
  Pastoria will have option to terminate Azurix at any time and keep the Water District contract and the back-up water supply, subject to paying the applicable termination fee
Pastoria Overview

## Slide 17: Labor Agreements
Pastoria has entered into contracts to construct, operate and maintain the plant with union labor
The unions include:
  IBEW Local #47, AFL-CIO
  Southern California Pipe Trades Council 16
  State Building & Construction Trades Council of California
  Building and Construction Trades Councils of Kern, Inyo and Mono Counties
  United Association of Plumbers & Steamfitters
Pastoria Overview

## Slide 18: Performance Assumptions
Pastoria Overview

## Slide 19: Capital Costs Assumptions
Pastoria Overview

## Slide 20: Annual Operations & Maintenance Cost Assumptions
Pastoria Overview

## Slide 21: Legal Structure
Pastoria Energy Facility, L.L.C. is a single member, Delaware limited liability company wholly-owned by ENA
Purchaser will acquire all of ENA’s member interest in Pastoria
Pastoria Overview

## Slide 22: Continuing Involvement
ENA desires to maintain continuing involvement with Pastoria
Continuing involvement could include:
  Scheduling coordination
  Fuel supply
  Power marketing
Any arrangement must be mutually beneficial
Pastoria Overview

## Slide 23: California Power Market - Overview
Has experienced numerous energy and capacity shortages and reliability problems
  The California Energy Commission (“CEC”) estimates 6,000 to 11,000 MW of additional capacity required in five years
  Transmission imports are limited
  Increasing load demands in adjacent states are reducing resources available to satisfy California demand
Demand is growing by 1,250 MW per year according to the ISO
CEC expects reliability problems from 2001 to 2005
60% of generation base has been in service for at least 30 years
Pastoria Overview

## Slide 24: California Power Market – Recent Developments
California experienced significantly higher energy prices than expected this summer
According to ISO, high prices were result of:
  Unexpectedly high load growth exacerbated by unseasonably high temperatures
  Higher gas prices
  Larger number of scheduled and forced outages than expected
  Lack of new plants built in recent years
To address the power crisis, ISO and others are recommending:
  Acceleration of permitting and siting of projects
  Focus on developing load responsive programs
Pastoria Overview

## Slide 25: Summary
Pastoria Overview
  Pastoria has secured rights to much of the major equipment and is in the most advanced stages of the CEC permitting process
  Pastoria has been strategically located, designed and developed to give it a competitive edge over other plants and optimize its optionality and opportunities to extract additional value
  ENA desires to maintain some form of continuing involvement with the project