## Slide 1
Pastoria Energy Facility, L.L.C.
September 27, 2000
Pastoria Overview

## Slide 2: Generation Overview
750 MW (nominal) natural gas-fired, combined cycle plant
Merchant plant will sell its output into the power markets of the California Power Exchange (“PX”) and the California Independent System Operator (“ISO”)
Additional value being pursued by ENA (each to be price separately by bidder)
  Bilateral contract with California Department of Water Resources (“CDWR”) re: Edmonston Pumping Station
  Expansion of Pastoria to 1,000 MW and a possible reliability-must –run (“RMR”) contract
Pastoria Overview

## Slide 3: California Power Market Overview
Has experienced numerous energy and capacity shortages and reliability problems
  The California Energy Commission (“CEC”) estimates 6,000 to 11,000 MW of capacity will be required in five years
  Transmission imports are limited
  Increasing load demands in adjacent states are reducing resources available to satisfy California demand
Demand is growing by 1,250 MW per year according to the ISO
CEC expects reliability problems from 2001 to 2005
60% of generation base has been in service for at least 30 years
Pastoria Overview

## Slide 4: California Power Market – Recent Developments
This summer, California has experienced significantly higher energy prices than expected
According to ISO, the high prices were the result of:
  High demand due to unexpectedly high load growth exacerbated by unseasonably high temperatures
  Higher gas prices
  A larger number of scheduled and forced outages than expected
  Lack of new plants built in recent years
To address the power crisis, ISO and others are recommending:
  Acceleration of the permitting and siting of projects
  A focus on developing load responsive programs
Pastoria Overview

## Slide 5: Key Investment Merits
Attractive location
  SCE power transmission
  SP-15 pricing zone
  Kern/Mojave gas pipeline
  San Joaquin Valley Unified Air Pollution Control District
    No impact from South Coast Air Quality Management District reclaim issues
Additional value from CDWR and expansion
ERCs have been obtained
Project is in the advanced stages of development
Power islands have been secured
EPC contract has been negotiated but not signed
Significant barriers to entry by competitors exist
Pastoria Overview

## Slide 6: Development Overview
Pastoria Energy Facility, L.L.C. is a wholly-owned subsidiary of ENA
CEC declared the Application for Certification (“AFC”) “Data Adequate” on 1/26/00
CEC is expected to issue its final decision in 11/00
Site, located in Kern County, 30 miles south of Bakersfield, will be leased from Tejon Ranchcorp
Electrical interconnection with Southern California Edison at the 230 kV Pastoria Substation
Gas interconnection with Kern/Mojave pipeline
Water will be supplied by the Wheeler Ridge Maricopa Water Storage District (“Water District”) and Azurix
Pastoria Overview

## Slide 7: Development Timeline
Date Milestone
4Q00 Obtain CEC Permit & Air Permit
4Q00 Financial Closing
2Q01 Begin Construction
4Q02 Start-Up Testing
2Q03 Commercial Operation
Pastoria Overview

## Slide 8: Permitting/Approval Process
Date Milestone
11/30/99 AFC filed with CEC
1/26/00 CEC declares AFC “Data Adequate”
3/13/00 Information hearing and site visit
7/26/00 Air District issues Final Determination of Compliance
9/1/00 CEC Final Staff Assessment
9/18/00-9/19/00 Final CEC hearings; record now closed
10/00 (est) CEC issues presiding members’ report
11/00 (est) CEC issues final decision
12/31/00 (est) Expiration of 30-day rehearing period and Williamson Act appeal period
Pastoria Overview

## Slide 9: Williamson Act
Pastoria Overview
Site is currently subject to the Williamson Act (the “Act”)
The Act is a land-use policy enacted to preserve open space and agricultural land and prevent commercial development
Implemented through a contract between the landowner and the county
To remove land from the Act
  County Board of Supervisors must approve
  180-day appeal period must expire
  Pay cancellation fee
To free the Site from the Act, ENA has
  Obtained the approval of the Kern County Board of Supervisors
  Sought to have the appeal period reduced by legislation
California Assembly Bill 2698, passed by the Assembly and Senate and awaits the governor’s signature, reduces the appeal period to the same time frame as the rehearing period for the CEC final decision

## Slide 10: Interconnections
Electrical
  Interconnect at the SCE Pastoria Substation – 1.38 miles
  Double circuit, 230 kV
  Impact study has been completed; facility study to be issued in mid-October
  Negotiations on Interconnect Agreement will begin soon
Gas Transportation
  Interconnect with the 42-inch Kern/Mojave pipeline – 11.65 miles
  24-inch pipeline
  700-900 psig
  LOI currently under negotiation
Pastoria Overview

## Slide 11: Equipment Overview
Two power islands in a “two-on-one” and “one-on-one” configuration comprised of:
  three GE 7FA combustion gas turbines
  one GE D11 steam turbine
  one GE A11 steam turbine
  three HRSGs, including XONON or SCRs
Emissions will be minimized through the use of Best Available Control Technology
  XONON technology
  SCRs
Cooling towers
Zero discharge wastewater system
Pastoria Overview

## Slide 12: Key Project Agreements
Tejon Agreements
  Transaction Agreement
  Option Agreement
  Ground Lease
  Easement Agreement
Equipment Purchase Agreement
Engineering Procurement and Construction Turnkey Contract
Water Supply Agreements
  Water District
  Azurix
Labor Agreements
Pastoria Overview

## Slide 13: Tejon Agreements
Pastoria Overview
Transaction Agreement
  Outlines relationship between Pastoria and Tejon
  Intertwined with other Tejon agreements
Option Agreement
  Grants Pastoria the right to lease the Site and acquire easements
  Six-year option term
Ground Lease
  25-year term
  Options to extend for three five-year terms
  Fixed rent
  Variable rent based on spark spread
Easement Agreement
  Establishes terms regarding laterals for access, transmission, gas and utilities

## Slide 14: Engineering, Procurement and Construction Turnkey Contract
Pastoria Overview
Contract between PEF and NEPCO (an Enron affiliate) has been completely negotiated, but not executed
Contains market-based terms including performance and completion guarantees
Purchaser and NEPCO each will have the option to execute
Cannot be executed earlier than 14 days after closing

## Slide 15: Water Supply Agreements
Water District
  Will provide primary supply of up to 5,000 acre-feet per year
  Default judgment validating the agreement was entered on 8/31/00; judgment to expected become final 9/30/00
Azurix
  Will provide a guaranteed back-up supply and scheduling services
  Pastoria must exercise an option in 2001 and pay $6,500,000 to acquire rights to 40,000 acre-feet of water and trigger Azurix’s obligations
  Payments of $500,000 per year and $550 per acre-foot will cover purchases from the Water District and Azurix
  Pastoria will have the right to terminate Azurix at any time and keep the Water District contract and the back-up water supply
Pastoria Overview

## Slide 16: Labor Agreements
Pastoria has entered into contracts with unions to construct, operate and maintain the plant with union labor
The unions include:
  IBEW Local #47, AFL-CIO
  Southern California Pipe Trades Council 16
  State Building & Construction Trades Council of California
  Building and Construction Trades Councils of Kern, Inyo and Mono Counties
  United Association of Plumbers & Steamfitters
Pastoria Overview

## Slide 17: Operations & Maintenance Costs
Pastoria Overview

## Slide 18: Capital Costs
Pastoria Overview

## Slide 19: Plant Assumptions
Pastoria Overview

## Slide 20: Summary
Pastoria Overview
Pastoria has been strategically located, designed and developed to give it a competitive edge over other plants and optimize its optionality and upside potential
Pastoria has secured rights to much of of the major equipment and is in the most advanced stages of the CEC permitting process
ENA desires to maintain some form of continuing involvement with the project