## Slide 1: Fountain Valley Power
225 MW Peaking Station
for
Public Service of Colorado

## Slide 2: Public Service of Colorado
IOU serving Denver metro area and large parts of Colorado
Parent New Centuries Engeries recently merged with Northern States Power to form Xcel Energy
Combined company has 3 million electric customers and 1.5 milllion natural gas customers in 14 states
Total revenue in excess of $7 billion
Xcel market capitalization: $4,345 million, credit rating: BBB+
PSCo credit rating: A-
PSCo is experiencing rapid load growth within Front Range load pocket.
Projected 2001 peak load of 5,402 MW achieved in July 2000.
Colorado PUC has restricted ability of PSCo or its affiliates to build new generation until resource pool reaches 50% external ownership (est. 2010)

## Slide 3: PSCo RFP
January 2000 RFP requested bids totaling 1500 MW of new generation
Enron’s April 2000 bid offered six LM6000’s (225MW)
Plant Site located at Midway Substation near Colorado Springs
Bid for a May 1, 2002 COD with 10 year PPA
ENA agreed to fast-track for July 1, 2001 with 11 year PPA
PSCo must demonstrate strict adherence to process to put contracts into the rate base.

## Slide 4: Fountain Valley Power
Will employ six LM6000’s from the West LB facility
  Simple cycle operation
  Inlet chilling to 50 F
  AGC control (for PSCo), remote start
73 acre site optioned adjacent to the Midway Substation
Midway interconnects to PSCo, WAPA, West Plains, CSU
PSCo will build interconnect into 230 kV bus
Colorado Interstate Gas is contracting to build 5.6 m lateral
Improved gas infrastructure to be added in late 2002
Water provided by Midway Ranch from nearby well

## Slide 5: Development Schedule
Site:
  Option agreement in place with Midway Ranch owners
    3 six month option periods with $5,000 premium
    $219,000 strike price
  Phase I Environmental complete (Phase I). No Phase II required
  Closing late NOV.
Permits
  Draft air permit issued. Final permit anticipated 9 NOV.
  Rezoning hearing with El Paso County scheduled for 23 NOV.
Contracts:
  PPA fully negotiated, anticipate signing 13 OCT
  PSCo Facilities Agreement under review
  Executed gas interconnect backstop authorizing development of gas spur prior to signing of gas interconnect
  Water supply agreement pending final supply tests
  O&M estimate provided by Enron’s OEC subsidiary

## Slide 6: Timeline

## Slide 7: Interconnect Status
Water:
  Finalization of water administrative process.
  Well pumping tests performed 6 October.
  Water delivered by 1 April.
Gas:
  Agreement with CIG for lateral executed.
  CIG acquiring easement.
  Completion scheduled for 1 April.
Electrical Interconnect:
  Technical planning for interconnect in progress.
  PSCo guarantee backfeed power 1 May.
  Earlier date is likely.

## Slide 8: PSCo PPA
Tolling arrangement:
  gas received at CIG meter, balancing provided by PSCo
  power delivered at plant’s revenue meters.
11 year Power Purchase Agreement
  100% of plant capacity: 230 MW
  $9.50 per kW-month (inclusive of fixed O&M).
  Additional $0.50 fixed revenue for VAr support and AGC.
  Variable charge adjusted to account for variation in heat rate.
  Start power/gas and facility fees are pass through to PSCo.
Capacity payment based on availability with 5% allowance for scheduled maintenance.
Replacement power provision permits capacity make-whole option in the event of forced outage or Force Majeure.

## Slide 9: Plant Economics
PSCo payments fully amortize plant capital costs in initial 11 years of operation, assuming:
  No NEPCo promote
  11% discount rate
  Unlevered, pre-tax cash flows
Fully leveraged plant provides sizeable margin for Enron Corp over the life of the project.
  $12 m NEPCo profit and contingency
  $18.7 m ENA NPV11
  Assumes 9% state tax, $350 per kW terminal value, 75% leverage

## Slide 10: Risks and Mitigants

## Slide 11: Risk and Mitigants

## Slide 12: Financing
Off Balance Sheet Development
  Major equipment purchased through West LB
  “Enron Friend” needed to fund soft-costs between LNTP and commencement of Turbo-Park ($4-5 million)
  Turbo-Park facility will assume full ownership of project from “Enron Friend” and West LB at beginning of 2001.
Post-COD Strategy
  Post COD cash flows support 75% debt structure with 1.4 DSCR
  Buyer with strategic interest in Colorado Front Range currently assessing project purchase for purchase prior to COD.

## Slide 13: Decision Point
PSCo PPA signing scheduled for 13 OCT
  PPA is binding document
  Enron outs for development risks and board approval
    1 DEC - Last date for termination for Board Approval and site development issues
    31 JAN - Last date for termination for unforeseen obstacles
  PSCo out for PUC ruling
    21 DEC - Last date for PSCo to terminate for failure of PUC to support inclusion of PPA in rate base
Enron commitment of $2 million by 1 DEC