## Slide 1
Dabhol Power Company
Presentation to Oman LNG
July 19, 2001
Dubai
Notes: 2
2

## Slide 2: Presentation Agenda
Project Status Update
  Phase I Update/Current Status
  Phase II Update/Construction Status
  LNG Ship Update
MSEB / GoM / GoI Update
  MSEB Actions & Concerns
  MERC Update
  GoI Update
DPC Actions & GoM / GoI Response
  DPC Efforts to find a solution
  Response from GoM / GoI
  Response from MSEB
The Road Ahead
  Asset Preservation
  Renegotiation Schedule

## Slide 3
Project Status Update

## Slide 4: Phase I Operations Update & Current Status
728 MW operational since May 1999
Average Availability
  Since May 1999 : 86%
Average Baseload PLF
  Since May 1999 : 46%
  Last 8 months : 22%
Despatch stopped by MSEB since May 29 2001
  DPC continues availability declarations per PPA
Pre-preservation activities initiated by DPC & OPO
Regular operating permit not yet issued by Maharashtra Pollution Control Board (MPCB)
  Interim approval to operate Phase I granted on March 31 2001

## Slide 5: Phase II Construction Update
Actual
Plan
Balance
91% Plan
Phase II Construction 93% Complete
(As of 31 May, 2001)

## Slide 6: Phase II Current Status
Overall 93% complete (as on May 31 2001)
Contractors have terminated Phase II Construction Contracts
  All construction works stopped at site since June 17 2001
Custody, care and control of Phase II works assumed by DPC
  Removing combustible construction debris and hazardous materials
  Secured site to prevent vandalism and theft
  Pre-preservation activities and preliminary investigation of balance works initiated by DPC & OPO
  Asset Preservation Plan giving detailed scope of work, schedules and budget submitted to Lenders for approval
Construction Permit expired on June 30 2001
  Renewal pending with MPCB

## Slide 7: LNG Ship Update
Ship construction on schedule
  98% complete; sea trials expected in August 2001
  Scheduled Delivery Date: November 15 2001
Vessel Lenders have suspended disbursements
  Greenfield shareholders meeting current payment obligations
Greenfield and Vessel Lenders met on June 11 & July 2
  DPC providing Greenfield with regular updates on project status
  Closely monitoring & assessing DPC’s situation
  To meet again on July 23
  Vessel Lenders examining various options
DPC Lenders have the opportunity to cure DPC default
  Greenfield required to give notice
  Cure period varies depending upon the nature of DPC default

## Slide 8
MSEB / GoM / GoI Update

## Slide 9: MSEB Position
Projections by CEA (15th Electric Power Survey) forecasted demand in MSEB system to increase by ~ 8% p.a.
  Industrial Demand in Maharashtra has actually declined
  Demand in subsidized sector has increased significantly
Lack of Tariff Reform
  Nine out of ten power consumers pay a price which is below MSEB’s cost of supply
Increasing amount of T&D losses (~ 40%), theft and subsidies
Arrears from consumers have increased from ~ $ 800 MM (Mar’99) to ~ $ 1100 MM (Mar’01)
From May’99 to Apr’01
  Worldwide fuel prices have increased, raising DPC tariff by 28%
  Rs/$ exchange rate has devalued 9%, increasing DPC tariff by 9%
  Result – Phase I tariff (@ 90% PLF) has gone from Rs.3.09/kwh to Rs.4.50/kwh

## Slide 10: MSEB Payment History
* May bill amount reduced by 54 Crs in rebates.
1999
2000
2001
Bars represent total bill payment in Rs. Crs. Bars represent amount of bill paid on due date
Line represents # of days until final payment received

## Slide 11: MSEB Update
MSEB actions adversely impact DPC, Sponsors and Lenders
  Payment Defaults
    Prompt payment from MSEB until Dec. 1999
    From Dec 1999 until Dec 2000, delays in payment increased
    DPC started invoking State and Central Government guarantees in early 2001
    Dec 2000, Jan 2001, Feb 2001, April 2001 & May 2001 bills still unpaid due to ongoing dispute
  L/C Default
    Value of Payment L/C not enhanced by MSEB
  Escrow Default
  Despatch manipulation and engineered misdeclaration claims
MSEB’s Principal Concerns
  Can not afford Phase II power
    Demand in paying consumer sector insufficient to absorb Phase II power
    Thus, MSEB revenue increase does not match cash outflow to DPC
  Consequences of Escrow reactivation
  Inability to enhance L/C

## Slide 12: Godbole Committee
Energy Review Committee, with Dr. Madhavrao Godbole as the Chairman, appointed by GoM to address the present MSEB crisis
Terms of Reference
  To review overall demand-supply situation of power in Maharashtra
    Special reference to MSEB’s purchase from IPPs with which PPAs signed / proposed
  To examine the cost of power supplied by DPC and distribution losses
    Examine implications on MSEB finances
  To review and reconsider provisions of DPC PPA,
    Suggest measures to purchase DPC power by others, including GOI or its agencies
  To suggest future course of action for State’s power sector reforms
  Any other matter referred by GOM in the above context
Terms of Reference expanded later to direct the Committee to negotiate the PPA & related documents

## Slide 13: Godbole Committee Report
Energy Review Committee, with Dr. Madhavrao Godbole as the Chairman, appointed by GoM to address the present MSEB crisis (Feb, 2001)

## Slide 14: Godbole Committee Report

## Slide 15: Renegotiation Committee Meetings
GoM appointed new committee for renegotiating PPA and tariff
  Two meetings held with DPC (May 11, May 29, June 19 & June 30)
MSEB wants to restrict its off take to only one power block (740 MW)
Committee, including GoI representative, unclear about the purchaser of power for the remaining two power blocks (1444 MW)
  But GoI says it will not be NTPC or GoI
Committee seeking unilateral tariff reductions by DPC to equal ~ Rs. 2.5/kWh @ 30% PLF (current LNG tariff @ 30% PLF ~ Rs. 9/kWh)
DPC has maintained that any tariff reduction can only be considered with MSEB, GoM and GoI buying 90% power
  DPC will not take marketing risk
Tariff reduction involves concessions from stakeholders, including lenders
  DPC has indicated a potential reduction in tariff up to ~10%, subject to 90% PLF, creditworthy security and acceptability by all stakeholders

## Slide 16: PPA Rescission
On May 24, MSEB faxed rescission letter dated May 23
  Repudiation based on alleged misrepresentation
  Without prejudice to rescission, agreeable to continue purchase of power and make payments till disputes are resolved by the appropriate forum
  Such payments to be on the basis of reasonable compensation as determined by a competent forum
MSEB’s Plan
  Conditioned April payment on DPC acknowledgement of PPA rescission
  Seek refuge with MERC
  Weeks in planning stage
    Evidenced by over 600 page MERC filing
MSEB’s Only Solution : Avoid PPA

## Slide 17: MSEB Repudiation: MERC Actions
MERC Petition
  On May 25, MSEB filed petition before MERC for, inter alia,
    MERC adjudication of disputes between MSEB and DPC under PPA;
    Confirmation of MSEB’s rescission of PPA;
    Enjoin DPC from taking further legal recourse available under PPA; and
    Move jurisdiction from international arbitration to Indian legal system
MERC Hearing
  On May 29, MERC was prima facie of the view that it had jurisdiction to adjudicate disputes between MSEB and DPC. On the basis of this view, MERC issued ad-interim orders restraining DPC from
    Pursuing arbitration proceedings
    Reactivating the Escrow Account

## Slide 18: Mumbai High Court Order: MERC Jurisdiction
Mumbai High Court Hearing (June 27)
  DPC challenged the jurisdiction of the MERC over disputes between MSEB and DPC as asserted by MSEB in its petition filed with MERC
  Summary of High Court order:
    The High Court refused to exercise its writ jurisdiction on the basis that DPC’s petition was premature and was not a fit case for interference
    The High Court stayed its own order for a period of two weeks and also adjourned proceedings before the MERC for the same period
    The High Court also directed the MERC to determine its own jurisdiction and pass orders within six weeks
    The High Court left the issue of jurisdiction open and made no determination on the issue
    The High Court maintained that the MERC’s ad-interim orders that prevent DPC from pursing the arbitration against MSEB and re-activation of the escrow would continue to remain valid pending the MERC’s final determination
  DPC examining all the options available, including appealing to the Supreme Court challenging the High Court order

## Slide 19: Chronology of Apr-01 Conditional Payment
May 24 (one day prior to April invoice due date)
  MSEB called DPC to collect the cheque
  Within minutes thereafter, MSEB’s rescission letter faxed to DPC
  DPC elected not to collect cheque until legal analysis of rescission letter
    DPC will not compromise its position vis-à-vis validity of PPA
May 25
  DPC wrote letter to MSEB asking them to clarify their intent, and informing that:
    DPC’s position is that no rescission of PPA is possible
    DPC will collect check from MSEB on next business day (Monday, May 28)
  As DPC letter being finalized, MSEB messenger arrived with cheque
    First time ever MSEB has delivered cheque to DPC
  DPC requested MSEB messenger to return with the cheque
  DPC sent letter via fax in response to MSEB’s rescission letter
  DPC received MSEB letter via fax asking DPC to collect cheque at MSEB

## Slide 20: Chronology of Apr-01 Conditional Payment
May 25 (contd.)
  MSEB tried to force deposit of cheque at Bank of America
  DPC requested its banker not to accept cheque until MSEB accepts DPC letter
  MSEB refused to accept DPC’s hand-delivered letter at MSEB office (already received via fax)
  MSEB Chairman agreed to accept letter at public announcement of MERC petition filing, in exchange for DPC acceptance of MERC hearing notice; exchange takes place later in evening
May 28 (next business day)
  DPC sent messenger to collect cheque from MSEB
    Told no cheque available
May 29
  MSEB clarified their position stating that
    MSEB had rescinded the PPA
    No further payments would be made
    No further power to be dispatched from noon of May 29
    No further Phase II testing allowed

## Slide 21: Escrow Update
Overview
  Escrow mechanism tested successfully and placed under suspension in April 2000
  Notice to terminate suspension of escrow mechanism sent to MSEB and Canara Bank (as Escrow Bank) on March 22 2001
    MSEB did not respond and they also advised Canara Bank not to reactivate the Escrow
    DPC wrote directly to collection banks to reactivate Escrow, which has not been responded to by the banks till date
    DPC followed up the matter rigorously with MSEB and Canara Bank
Recent Developments
  On May 25 2001, MSEB filed petition before MERC to restrain DPC from reactivating the Escrow account
  MSEB rescinded the PPA on May 29, 2001
  MERC issued orders on May 29, 2001 restraining DPC from reactivating the Escrow account
MSEB failed to meet its contractual obligation to reactivate Escrow

## Slide 22: GoI Update
Defaults on GoI Guarantee
Appointed Representative to Renegotiating Committee
  To facilitate and listen
  No proposals
Directed CEA to ask power deficit states:
  How much power needed and at what price?
  CEA report indicates a price range of Rs.2.25-3.00 /kWh
  Only partial absorption of Phase II power
Offered to give DPC clearances to market power itself
Held several meetings and said all would be OK
  But GoI has repeatedly refused requests from DPC, MSEB, GoM, etc. to purchase Phase II power
GoI so far reluctant to become a key player

## Slide 23
DPC Actions

## Slide 24: DPC Efforts to Find a Solution
Qtr initiated
Third party sales discussion with MSEB 1Q - 2000
  Established 5 person team devoted full time to pursue third party sales
Held over 20 negotiations with potential customers for power sales 2Q - 2000
  Rajasthan, Karnataka, Delhi, Andhra Pradesh etc.
Assisted MSEB in its rate filing with MERC and made 2Q – 2000 available Enron’s regulatory experience and expertise
Met with various levels at MSEB/GOM/GOI 2Q – 2000 to focus on:
  MSEB’s poor financial health and need to accelerate reforms
  MSEB’s inability to absorb Phase II power
  Need for third parties to purchase Phase II power
  MSEB need to hedge fuel and $ exposure
  Covered various levels at MSEB, GOM and GOI including
    MSEB - Chairman, other Board members, and other MSEB officials
    State - Chief Minister, State Power Minister, Senior State Bureaucracy
    GOI – PMO, Power Minister, Power Secretary and other MOP officials
  50 meetings yielded no progress

## Slide 25: DPC Efforts to Find a Solution (cont.)
Qtr Initiated
Interest rate reduction on Phase I Rs. Loans 2Q - 2000
Discussions with MSEB/GOM on sharing 3rd LNG tank 3Q – 2000 with MetGas Project
Enron provided loan (with MSEB’s concurrence) 3Q - 2000 to MSEB’s Phase II transmission line contractors
Worked with lenders to permit extra 30 days for 4Q – 2000 MSEB to pay DPC bills
Proposed sale of power to GOI (NTPC or PTC) 4Q - 2000
Despite MSEB’s creeping delay in payment of DPC bills
  DPC continued to comply with the PPA
  Invoked GOM/GOI guarantee first time only in Jan 2001

## Slide 26: Response from the Government
GOM (CM, Power Minister and other Ministers) on various occasions, including floor of the Assembly, expressed a desire to cancel the project
GOM appointed the Godbole Committee with the intention to review the project (find loopholes) and renegotiate the PPA
Parties in power in the State (Congress - I, Left Parties and others) organized several anti project/anti Enron demonstrations to meet their political needs and call for cancellation of the project
GOM used its authority to cancel/change conditions in project clearances to frustrate DPC in performing its obligations under the PPA
GOM actively canvassed with GOI not to pay the Rs 102 cr unpaid December 2000 bill
GOI (notwithstanding DPC overtures) – no progress in the last 6 months
GOI in its most recent meeting with DPC offered to participate in discussions only if DPC ceases all legal action

## Slide 27: Response from MSEB
Deliberate failure to pay DPC
  MSEB Chairman announced intention to deliberately not pay DPC to precipitate a crisis
Fabrication of misdeclaration allegations
Failure to enhance Letter of Credit
Failure to implement the Escrow Agreement and actively canvassing Canara Bank not to implement the Escrow Agreement
Inadequate attention to completion of transmission lines
  Second circuit has been completed for over one year and still not energized

## Slide 28
The Road Ahead…..

## Slide 29: The Road Ahead…..
RENEGOTIATION
  Bid / ask is very wide
  Very difficult and complicated
  Requires creditworthy buyer for all power
  Tariff reduction requires material concessions from all stakeholders
  Significant transaction costs and delay costs
  Future renegotiation risk is high
TERMINATION
  Very difficult and complicated
  Cumbersome valuation process
  Legal proceedings necessary
  Transaction costs high
  MSEB / GoM capacity to pay Transfer Amount
  Enforcement of Arbitration Award is lengthy process
Best Option: Pursue both until ultimate path becomes clear

## Slide 30: The Road Ahead…..
Phase I and Phase II to be mothballed
  Preserves asset value for later use
  Phase II Construction to recommence after negotiation of new contracts
  Work with other counter parties to preserve other project contracts
DPC to Continue Renegotiation Efforts
  Utilize Godbole Committee forum for renegotiations
  Continue discussions with GoI
  Absent overt immediate action (not words) by GoI to buy at least 2 power blocks, renegotiation efforts will not succeed

## Slide 31: Enforce Contractual Rights
Resist MERC jurisdiction immediately and vigorously
Pursue arbitration / conciliation proceedings against MSEB / GoM / GoI
Remain available to despatch power
Continue to enforce rights
  Issue guarantee demands for payment defaults
  Issue Preliminary Termination Notices approved by Lenders
  Issue Transfer Notices when approved by Lenders
Likely to Increase GoI’s Active Involvement in Finding Solution

## Slide 32: Asset Preservation
Detailed plans are ready for preservation of
  Phase II power project: Blocks B & C
  LNG Regas facility
  Marine Works
  Balance of Plant
Implementation based on utilisation of DPC / OPO staff and selected contractors on a unit rate basis
Expected time required to accomplish initial preservation
  Block A : 30 days after reduced readiness
  Blocks B & C : Less than 30 days
  LNG facility : 45 to 60 days

## Slide 33: Possible Renegotiation Schedule
Move Phase II into Asset Preservation Mode July 2001
Finalize Blueprint of a Solution with all counter parties Q3, 2001
Renegotiation of Project Documents Q4, 2001
Financial Close Nov 2001
Commence Phase II Construction
  LNG Facility Q4, 2001
  Power Plant (don’t complete until LNG ready) Q3, 2002
Commence Phase II Operations Q1, 2003
Suspension Period for Phase II
  LNG Facility 4 Months
  Power Plant 12 Months