## Slide 1
March 12, 2001
Confidential
Pastoria Energy Facility
Continued Development
Natural Gas Transportation
Project Sale
Enron Corp. Board of Directors
Executive Committee

## Slide 2: Pastoria Energy Facility Overview
Project Overview
750 MW natural gas-fired, combined cycle merchant plant
Site, located in Kern County, 30 miles south of Bakersfield, will be leased from Tejon Ranchcorp (“Tejon”)
Electrical interconnection with Southern California Edison
Gas interconnection with Kern/Mojave pipeline
Water will be supplied by the Wheeler Ridge Maricopa Water Storage District, and the Kern Water Bank Authority
Final California Energy Commission (“CEC”) permit received January 20, 2001
Final federal permit, Prevention of Significant Deterioration, received February 15, 2001
  Value Proposition
  Continued strong industry demand for properly developed merchant generation projects in Western System Coordinating Council
  Project is out of the money relative to EPMI curves but in the money ($50+MM) using consultant curves and standard industry finance assumptions
  “Develop and Sell” strategy enables ENA to monetize development at point of highest ROE with relatively low capital risk
  Use of option payments and sharing agreements triggered by project success minimizes capital outlays during development process
  Development promote/sale gain is high relative to dollars spent, but low relative to overall project cost
Project Exposure ($MM)
        Current Proposed Total
Development Costs $48.2 $1.9 $50.1
Gas Transportation 0 34.0 34.0
TOTAL: $48.2 $36.9 $84.1
Assumes emission credits ($27.8MM) cannot be resold; turbines re-deployed

## Slide 3: Development/Gas Transportation
Continued Development
ENA seeks approval for
  Additional development expenses ($1.9MM)
    January 1, 2001 to May 31, 2001
    Option payments to landlord and legal, engineering and consultant fees
  Firm gas transportation contract (Value at risk = $34MM)
  Turbine purchase agreement with GE ($198MM)
    Two GE 7FA power islands
    $19.8MM approved and paid to date
On May 31, 2001, ENA will determine whether to continue development of project
Gas Transportation
Kern is currently holding an open-season for expansion of its pipeline
  Expansion capacity would be available May 2003
  Kern is only 11.5 miles from the project site
Pastoria will require 118,000 to 126,000 MMBtu/d
Pastoria seeks to acquire 100,000 MMBtu/d of firm capacity for a 15-year term
  Balance of capacity would be acquired on spot market
There are no other viable options for firm transportation n Kern County, CAy
  Other pipelines are either fully subscribed or have insufficient capacity
  Firm capacity is required to continue marketing project to Calpine or any third party
More than 1.5 Bcf/d of capacity was requested on February 15
  Requested capacity would more than double Kern’s current capacity
Open-season is being incrementally priced and all participating shippers must submit a binding bid on March 15
Value at risk is $34MM per RAC
  Assumes one year liquidation period that can be hedged in 45 days per ENA gas desk
Enron must provide credit support of either
    Guarantee of 15-year of demand charges (PV $48.2MM)
    Evergreen letter of credit covering three years of demand charges (PV $38.5MM)

## Slide 4: Sale to Calpine
  ENA began marketing the project in late 2000
  Calpine was highest of six bids, all requiring execution of backup water contract and receipt of final CEC and EPA permits as conditions precedent.
  Purchase price will reimburse ENA for its development costs and turbine payments and include a gain in excess of $30MM
  Additional value opportunities
    $6MM will be paid if project is expanded by more than 200MW
    Revenue sharing on certain power sales to California Department of Water Resources
  Purchase & Sale Agreement must be signed by March 14, prior deadline for firm commitment on Kern open-season
  Two major conditions precedent
    Execution of back-up water supply agreement with the Kern Water Bank Authority by April 30 required for Calpine to close
      Difficulty arranging back-up water through original Azurix management agreement.
      Agreement now in principle with Water Bank and Calpine; need definitive agreement by April 30, 2001.
    Calpine must provide credit support sufficient to fully release Enron of its guarantee obligations under the Kern gas transportation agreement, as a condition for ENA to close.
    Prior to the signing of the Purchase & Sale Agreement, ENA will ensure Kern and Calpine are in agreement as to the credit support required to release Enron.