## Slide 1: Proposed Sun Devil Project - Suggested Collaborative Approach
Begin Scoping
Notice Application
Staff Prepares NEPA Document
Develop
Study
Corridor
Identify
Stakeholders
Hold
Project
Info Mtgs
w/Officials
& Public
Hold
Public
Meetings
Complete follow-on
Surveys
File
At
FERC
Finalize
Route
Issue
Draft
NEPA Doc.
Resolve Issues, Respond To Comments
Issue
Final
NEPA Doc.
Issue
Construction
Release
Order
Proposed Time Line
Sept. 2001
Dec. 2002
Mar/Apr 2002
(7-8 months)
(8-9 months)
In-service
2003
Construction
ETS
The
FERC
Select
3rd Party
Contractor
Complete
surveys
Certificate
issuance