## Slide 1
Critical Timeline
02/07/02
Day 1 “Best case” 02/11/02
1st day Business will be operational with minor exceptions related to specific pieces of Gas & Power business/client base - Sign client master agreements - Determine client credit limit - client notifications
Canadian Capital, Funding, guarantees
Day 2 TBD
Business is completely separated (infrastructure, applications, systems, etc,)
Day 3 No earlier
than 02/06/05
Final Business/Legal structure in place
02/28/02
First payroll from UBSW Energy LLC
02/08/02
- Test/ validate internal infra-structure ready for start of business
- Receive Hart-Scott-Rodino approval - Real Estate lease signed for Houston, Portland, Toronto, Calgary - Third party consents to be obtained under software licenses - Canadian entity (legal structure) - HR Critical mass
Business Integration
Commercial integration
02/07/02
Meeting with EBK to review VaR model
3 buy out options starting 3 yrs from legal closing date
Day O
02/08/02
Mock Trading
- Develop test plan - Test and validate mock trade
03/04/02
IT release
- First major IT release
Legal Closing Date