## Slide 1
DRAFT - HPL Transition Plan
January 18, 2000
Strictly Confidential & Subject to Attorney Client Privilege

## Slide 2: Objectives
Satisfy Enron Conditions Precedent to Close:
  Accounts transferred
  Assets and liabilities transferred (A/S liabilities resolved)
  IT systems operational
Protect transaction value for Enron:
  Unforseen costs and liabilities
  Continued operation of the asset
  Optimize transaction structure
Protect key Enron employees, proprietary information/strategies
  Traders crucial to ongoing business in Texas
  Key accounting, risk management, and technical staff
Position Enron to compete in Texas market post-Close:
  Retain supplier/customer relationships
  Retain ability to offer products

## Slide 3
Transition team established representing each area of the deal:
  Team Lead: Jim Coffey Human Res: F. Mayes/K. Neal
  Deal Structure: P. Wade/A. Koehler Operations: S. Schnieder/K. Kaase
  Prod. Serves: J. Zivley/G. Weissman Field Ops. D. Pribble/B. Brasher
  Marketing: G. Brazatis Engineering: N. Cocavessis/M. Carriere
  Regulatory: T. Shelton Info Tech: T. Yanowski
  Trading: T. Martin/E. Gottlob Bus. Ops: B. Hall/R. Wynne/E. Terry
  Finance: R. Dutt Legal: B. Gray/S. Braband
  Tax: Rhett Jackson Acctg: S. Orsak/E. Shield/G. Whirtling
Kick off meeting held 1/16:
  Transition teams tasked with developing detailed action items for their areas
  Action items will be consolidated and a critical path will be established based on available resources
Ongoing status meetings to track action items from each area of the transition team:
  Resolve conflicts, prioritize resources, coordinate activities
  Develop common interface point with AEP
Strategy
Notes: <number>
Participant Guide
ENA Orientation
<date/time>

## Slide 4
Determine who is staying with Enron and who is going with AEP:
  Expedite AEP interview process according to an agreed protocol and schedule
  Gives AEP sufficient time to fill in employee gaps prior to Closing
  Provides Enron with certainty as to who is stay with Enron
Protect access to non-HPL information during the transition process
  Co-locate all HPL employees on 35th floor to control access to non-HPL information
  Will require current non-HPL occupants on 35 to re-locate
  Prevent access of HPL employees to trading floors
Manage trading positions to ensure no additional exposure
  Work to resolve Cushion Gas issue with AEP
  Continue to run simulation to ensure firm purchase/sale books remain flat
  Reserve against marked term deals to offset unwind cost at Closing
  Continue to run separate ENA book to ensure value of Texas Spec. trading remains with Enron
Immediate Needs & Actions
Notes: <number>
Participant Guide
ENA Orientation
<date/time>

## Slide 5
Provide guidance to Enron employees to comply with the Transaction Agreements: Legal drafting employee memos on the following:
  What can be said to employees
  Conduct of business prior to Closing
  Collection and transfer of HPL information
Obtain resources to support understaffed areas with increased transition workload (HR, business ops, accounting)
  HR will have to manage development of severence packages, interview processes, and employee concerns in addition to ongoing ENA activities.
  Accounting will have to create a clean balance sheet for HPL that will require significant transfer of ENA assets out of HPL.
  Business Ops will have to support the separation and set up of a separate HPL IT systems, and a duplication of HPL procedures.
Expedite A/S line repair and IT System set-up
  Enron must track and manage the completion of these activities to ensure they do not delay Closing.
Immediate Needs & Actions
Notes: <number>
Participant Guide
ENA Orientation
<date/time>

## Slide 6: Follow up Activities
Fully develop “To Do” list for each transition area
Develop critical path to reach Close while maximizing transaction value
Prioritize resources based on critical path
Implement and track ongoing status