## Slide 1: UNIFY Performance - Summary Plans
July 20, 2000

## Slide 2: Agenda
The Problem And Solution
Summary Solution Plans
Sybase 12.0 Upgrade
SQL Server Test
Middle Tier - Draft Invoice
Strategic Scoping & Tech Migration Planning

## Slide 3: The Problem And Solution
Good news
  Unify is functionally the best gas logistics and cross commodity settlements engine in the industry
  Unify supports rapid time to market for EOL
The problem
  The current Unify architecture will not scale to support current or future transaction volumes (EOL growth)
The solution
  The database platform must be replaced
  We must architect a ‘middle tier’ of system processes for performance and scaleability

## Slide 4: UNIFY - Summary Recommendations
Kick off 4 new projects. Mitigate immediate performance issues and develop a strategic plan
  Tactical Sybase 12.0 upgrade
  SQL Server database performance test
  Tactical Middle tier migration
  Strategic scoping & architecture migration planning
Hire and train new ENRON IT resources. Build the leadership and delivery team
Reduce reliance on contractors
Leverage consultants

## Slide 5: Sybase 12.0 Upgrade
Scope: Upgrade to Sybase 12.0 with more memory on the production server
Benefits:
  30-50% performance improvements due to the ability to address more memory
  Buys time for further tactical and strategic improvements to Unify
Delivery Date: August 15
Cost:
  Consultants: 0
  Internal: $50,000
  Hardware: $100,000

## Slide 6: SQL Server Performance Test
The Issue: We must change the DB platform. There are two choices.
  Oracle
    Strength: Most proven DB for high transaction volume systems
    Weakness: It essentially a re-write of the system. Significant cost, time and project risk.
  SQL Server
    Strength: Migration is easy and would only take a few months.
    Weakness: SQL Server has only recently become a viable platform for large enterprise class systems. Higher level of technology risk with this choice.
Scope:
  Test SQL Server to ensure it will support Enron business
  Test Microsoft middle tier technology to ensure it will scale

## Slide 7: SQL Server Performance Test
Benefits:
  Ensures that SQL Server will work
  Moves toward a strategic technology that aligns us with London
  Potentially allows us to fix Unify at far lower cost and risk than with the Oracle option
Delivery Date : A go / no-go decision by Sept 15
Cost:
  Consultants: $380,000
  Internal: $50,000
  Hardware: Free from Compaq and Microsoft. Part of the test will be done in Redmond at Microsoft test facilities.

## Slide 8: Tactical Middle Tier Effort
Scope: Migrate 2 large Unify processes to a middle tier.
Benefits:
  Improve current Unify performance as soon as possible
  Develop a proof of concept that helps to develop the strategic technical approach
Delivery Dates :
  Sept 15 -- Draft inovice process
  Sept 30 - Accounting reconciliation report
Cost:
  Consultants: $300,000
  Internal: $50,000
  Hardware: $250,000 for 2 new Unix application servers

## Slide 9: Strategic Scoping & Tech. Migration Planning
Scope: Define a scope, approach and architecture to make Unify scale. Deliver an RFP to select a partner.
Benefits:
  A detailed plan for fixing Unify
  Partnering with Global Systems and En-voice projects to deliver a strategic level of integration.
  Provides an empirically based plan for scope, approach, schedule and cost
Delivery Date: September 30
Cost:
  Consultants: $450,000
  Internal: $200,000