## Slide 1
PROJECT
Door Step
Confidential

## Slide 2
Stress test the internal controls environment surrounding Enron’s trading operations by deploying various audit teams which include both senior Enron and Arthur Andersen personnel to remote trading locations to perform substantive tests and tests of controls.
Provide Enron Senior Management with a comprehensive view of the current environment.
Provide recommendations to strengthen the controls environment.
Project Doorstep - Objectives

## Slide 3
Management and employee profile
Segregation of duties
Position capture and position management
Document preparation and retention
Material contract review
Physical settlement
Settlement and cash management
Credit acceptance and assessment (linkage to overall exposure monitoring)
Interoffice linkage and functional responsibilities
Management reporting
Systems environment and infrastructure
Project Doorstep - Areas of Emphasis

## Slide 4
Remote Trading Office Reporting
Natural Gas
Electricity
Products
Emerging Products
Other
Calgary
Portland
Houston
Mexico City
Panama City
Buenos Aires
London
Helsinki
Oslo
Singapore
Sydney
Traded
Commodity Legend
Initial Deployment
Sao Paulo

## Slide 5
Project Doorstep - Locations and Teams
Primary Destinations
Sao Paulo
Buenos Aires
Singapore
Sydney
Oslo
Calgary
Portland
Enron Team
Sally Beck
Ted Murphy
Brent Price
David Hardy
Scott Earnest
Brenda Herod
Arthur Andersen Team
Tom Bauer
Deb Cash
Tom Lewthwaite
John Sorrells
Mike Patrick
Jim Brown
Nic Swingler
Jennifer Stevenson
John Vickers
Kate Agnew

## Slide 6
Reconfirm understanding of Calgary and Portland operation ___________ - Mgr. ___________ - ?
Access activities of the Mexico City and Panama City offices ___________ - Mgr. ___________ - ?
Revisit findings from Houston and London trading projects
Consider visiting other operations - Continental Europe - Power - Korea - US Marketing offices - Other
Project Doorstep - Phase II

## Slide 7
Office analysis framework
Business information flow
Control gap analysis
Testing attributes matrix
Project Doorstep - Deliverables

## Slide 8
Project Doorstep - Office Analysis Framework
Environment
Key regulatory issues
Unique country characteristics
Language barriers
Management
Management team/ organization chart
Local vs. seasoned Enron personnel
Strategy
Origination vs. trading
Products traded
Expected growth
Owners
List of key reporting responsibilities
Competitors
List of key competitors
Counterparties
Listing of primary counterparties and related exposures
List of storage or transportation/ transmission capacity
Information
Types of documents (i.e. standard vs. non-standard)
List of key management reports and level of distribution
Business Processes
Key processes conducted in office
Key linkage of processes to other offices and centralized office hub
Systems
List of systems used for data processing

## Slide 9
Project Doorstep - Control Gap Analysis
Existing Controls
Suggested Controls

## Slide 10
Project Doorstep - Deal Test Matrix
Deal #A12
Counterparty XYZ Corp
Term 6/99 - 6/00
Commodity Natural Gas
Quantity 50,000 mmbtu/mo
50,000 mmbtu
50,000 mmbtu
50,000 mmbtu
60,000 mmbtu
40,000 mmbtu
45,000 mmbtu
Estimated Delivery
Actual Delivery
Cumulative
145,000 mmbtu
Aug
July
June
May
150,000 mmbtu
Deal Date

## Slide 11
Project Doorstep - Deal Test Attributes
1. Deal is supported by a complete deal ticket
2. Deal is supported by an executed contract
3. Counterparty is approved by Credit
4. Deal is supported by an executed confirmation agree
5. Confirmation properly references Contract
6. Terms per the Contract, Confirmation and Deal Ticket
7. Deal is properly captured for valuation and inclusion in DPR
8. Transaction is priced off the proper curve/model
9. Deal is properly nominated for scheduling
10. Terms per the scheduling mechanism equal the confirm
11. Volumes are properly confirmed with counterparty (i.e. Pipeline statement, Bill of Lading)
12. Terms per the Invoice agree with Pipeline Statement/Bill of Lading
13. Deal is properly booked to AR/AP and Sales/Purchases
14. Ensure wire transfer request/check is properly approved
15. Ensure information on wire transfer request/check is correct (i.e. bank account, counterparty)
16. Cash receipt/disbursement is applied correctly
17. AR/AP is properly removed
18. MTM value of transaction is properly recorded in MTM asset/ liability
IF BROKER APPLIES:
19. Broker is selected from approved lit
20. Broker confirmation agrees to deal ticket
21. Broker fees are properly recorded in the DPR
22. Broker fees are properly recorded in the G/L