## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2001 Through December 31, 2001
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted May 24, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Total | P/U | Pub | Ver
[12 empty] | (Mmcfd) | (Mmcf) |  |  |  |  | Hours
1 | 16730 | ALB | ATOKA 1 | 794 | RING GEAR | 2001-05-14 14:00 | 2001-05-25 16:00 | 11.1 |  | OPS |  | 5 | 55.4 | Pulled ring gear off of SV6. 440 HP |  | 2001-05-14 14:00 |  | 0 | U | N | N
2 | 16731 | ALB | ATOKA 3 | 761 762 | SERVICE | 2001-05-21 07:00 | 2001-05-23 16:00 | 2.4 |  | OPS |  | 5 | 11.9 | Pull #2 lines on unit 762 Replace head to block gaskets on unit 761 1100 HP |  | 2001-05-21 07:00 |  | 0 | P | N | N
3 | 16192 | ALB | STATION 1 | 101 | ANNUAL MAINTENANCE & COMPRESSOR VALVES | 2001-04-30 08:00 | 2001-05-23 16:00 | 23.3 |  | OPS |  | 50 | 1166.7 | Annual maintenance and compressor valves. Cam components will be inspected and replaced as needed. Repair all unloaders. Maintenance & compressor valve work is complete. 05/16 Compro has started on Camshaft work. |  | 2001-05-03 07:30 |  | 0 | P | N | N
4 | 16740 | ALB | STATION 1 | 103 | WORK ON TURBOCHARGER | 2001-05-24 08:00 | 2001-05-24 16:00 | 0.3 |  | OPS |  | 50 | 16.7 | The need to take a look at the Turbocharger on 103. |  |  |  | 0 | U | N | N
5 | 16765 | ALB | STATION 1 | 103 | AFTERCOOLER | 2001-05-29 08:00 | 2001-05-31 15:00 | 2.3 |  | OPS |  | 50 | 114.6 | Downtime required to change out aftercooler on Unit 103. Send to shop. Have it repaired and reinstated. 4000 HP |  |  |  | 0 | P | N | N
6 | 16748 | ALB | STATION 1 | 1 2 3 | DOWNLOAD OPTO | 2001-06-19 08:00 | 2001-06-19 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. |  |  | 0 | P | N | N
7 | 16749 | ALB | STATION 1 | 1 2 3 | DOWNLOAD OPTO | 2001-06-21 08:00 | 2001-06-21 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. |  |  | 0 | P | N | N
8 | 16194 | ALB | STATION 1 | 102 | SAFETY DEVICES | 2001-09-18 08:00 | 2001-09-20 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. |  |  |  | 0 | P | N | N
9 | 16195 | ALB | STATION 1 | 101 | SAFETY DEVICES | 2001-09-25 08:00 | 2001-09-27 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. |  |  |  | 0 | P | N | N
10 | 16716 | ALB | STATION 2 | 203 | MINOR REPAIRS | 2001-05-16 20:30 | 2001-05-18 16:00 | 1.8 |  | OPS |  | 70 | 128.3 | They needed to go back and do some minor repairs an clean up work. 05/21 minor repair are complete. They are working on the Turbocharger now. Should be complete 05/23. |  | 2001-05-16 20:30 |  | 0 | P | N | N
11 | 16746 | ALB | STATION 2 | 1 2 3 | DOWNLOAD OPTO | 2001-06-12 08:00 | 2001-06-12 18:00 | 0.4 |  | OPS |  | 70 | 29.2 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. |  |  | 0 | P | N | N
12 | 16747 | ALB | STATION 2 | 1 2 3 | DOWNLOAD OPTO | 2001-06-14 08:00 | 2001-06-14 18:00 | 0.4 |  | OPS |  | 70 | 29.2 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. |  |  | 0 | P | N | N
13 | 16745 | ALB | STATION 3 | 1 2 3 | DOWNLOAD OPTO | 2001-06-08 08:00 | 2001-06-08 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. |  |  | 0 | P | N | N
14 | 16751 | ALB | STATION 3 | 1 2 3 | DOWNLOAD OPTO | 2001-06-28 08:00 | 2001-06-28 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. 4000 HP |  |  | 0 | P | N | N
15 | 16521 | ALB | STATION 3 | 321 | OVERHAUL | 2001-11-05 08:00 | 2001-11-23 16:00 | 18.3 |  | OPS |  | 0 | 0 | Engine overhaul. |  |  |  | 0 | P | N | N
16 | 16744 | ALB | STATION 4 | 1 2 3 | DOWNLOAD OPTO | 2001-06-06 08:00 | 2001-06-06 18:00 | 0.4 |  | OPS |  | 120 | 50 | Downtime is required to download OPTO program changes ot obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. |  |  | 0 | P | N | N
17 | 16750 | ALB | STATION 4 | 1 2 3 | DOWNLOAD OPTO | 2001-06-26 08:00 | 2001-06-26 18:00 | 0.4 |  | OPS |  | 120 | 50 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. 4000 HP |  |  | 0 | P | N | N
18 | 16752 | ALB | STATION 8 | 2 | AUTOMATION | 2001-08-01 08:00 | 2001-10-01 16:00 | 61.3 |  | OPS |  | 0 | 0 | Station 8 automation project. 8000 HP |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2001 Through December 31, 2001
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted May 24, 2001 | [10 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Total | P/U | Pub | Ver
[11 empty] | (Mmcfd) | (Mmcf) |  |  |  |  | Hours
1 | 16730 | ATOKA 1 | 794 | RING GEAR | 2001-05-14 14:00 | 2001-05-25 16:00 | 11.1 |  | OPS |  | 5 | 55.4 | Pulled ring gear off of SV6. 440 HP |  | 2001-05-14 14:00 |  | 0 | U | N | N
2 | 16731 | ATOKA 3 | 761 762 | SERVICE | 2001-05-21 07:00 | 2001-05-23 16:00 | 2.4 |  | OPS |  | 5 | 11.9 | Pull #2 lines on unit 762 Replace head to block gaskets on unit 761 1100 HP |  | 2001-05-21 07:00 |  | 0 | P | N | N
3 | 16192 | STATION 1 | 101 | ANNUAL MAINTENANCE & COMPRESSOR VALVES | 2001-04-30 08:00 | 2001-05-23 16:00 | 23.3 |  | OPS |  | 50 | 1166.7 | Annual maintenance and compressor valves. Cam components will be inspected and replaced as needed. Repair all unloaders. Maintenance & compressor valve work is complete. 05/16 Compro has started on Camshaft work. |  | 2001-05-03 07:30 |  | 0 | P | N | N
4 | 16740 | STATION 1 | 103 | WORK ON TURBOCHARGER | 2001-05-24 08:00 | 2001-05-24 16:00 | 0.3 |  | OPS |  | 50 | 16.7 | The need to take a look at the Turbocharger on 103. |  |  |  | 0 | U | N | N
5 | 16765 | STATION 1 | 103 | AFTERCOOLER | 2001-05-29 08:00 | 2001-05-31 15:00 | 2.3 |  | OPS |  | 50 | 114.6 | Downtime required to change out aftercooler on Unit 103. Send to shop. Have it repaired and reinstated. 4000 HP |  |  |  | 0 | P | N | N
6 | 16748 | STATION 1 | 1 2 3 | DOWNLOAD OPTO | 2001-06-19 08:00 | 2001-06-19 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. |  |  | 0 | P | N | N
7 | 16749 | STATION 1 | 1 2 3 | DOWNLOAD OPTO | 2001-06-21 08:00 | 2001-06-21 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. |  |  | 0 | P | N | N
8 | 16194 | STATION 1 | 102 | SAFETY DEVICES | 2001-09-18 08:00 | 2001-09-20 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. |  |  |  | 0 | P | N | N
9 | 16195 | STATION 1 | 101 | SAFETY DEVICES | 2001-09-25 08:00 | 2001-09-27 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. |  |  |  | 0 | P | N | N
10 | 16716 | STATION 2 | 203 | MINOR REPAIRS | 2001-05-16 20:30 | 2001-05-18 16:00 | 1.8 |  | OPS |  | 70 | 128.3 | They needed to go back and do some minor repairs an clean up work. 05/21 minor repair are complete. They are working on the Turbocharger now. Should be complete 05/23. |  | 2001-05-16 20:30 |  | 0 | P | N | N
11 | 16746 | STATION 2 | 1 2 3 | DOWNLOAD OPTO | 2001-06-12 08:00 | 2001-06-12 18:00 | 0.4 |  | OPS |  | 70 | 29.2 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. |  |  | 0 | P | N | N
12 | 16747 | STATION 2 | 1 2 3 | DOWNLOAD OPTO | 2001-06-14 08:00 | 2001-06-14 18:00 | 0.4 |  | OPS |  | 70 | 29.2 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. |  |  | 0 | P | N | N
13 | 16745 | STATION 3 | 1 2 3 | DOWNLOAD OPTO | 2001-06-08 08:00 | 2001-06-08 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. |  |  | 0 | P | N | N
14 | 16751 | STATION 3 | 1 2 3 | DOWNLOAD OPTO | 2001-06-28 08:00 | 2001-06-28 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. 4000 HP |  |  | 0 | P | N | N
15 | 16521 | STATION 3 | 321 | OVERHAUL | 2001-11-05 08:00 | 2001-11-23 16:00 | 18.3 |  | OPS |  | 0 | 0 | Engine overhaul. |  |  |  | 0 | P | N | N
16 | 16744 | STATION 4 | 1 2 3 | DOWNLOAD OPTO | 2001-06-06 08:00 | 2001-06-06 18:00 | 0.4 |  | OPS |  | 120 | 50 | Downtime is required to download OPTO program changes ot obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. |  |  | 0 | P | N | N
17 | 16750 | STATION 4 | 1 2 3 | DOWNLOAD OPTO | 2001-06-26 08:00 | 2001-06-26 18:00 | 0.4 |  | OPS |  | 120 | 50 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. 4000 HP |  |  | 0 | P | N | N
18 | 16752 | STATION 8 | 2 | AUTOMATION | 2001-08-01 08:00 | 2001-10-01 16:00 | 61.3 |  | OPS |  | 0 | 0 | Station 8 automation project. 8000 HP |  |  |  | 0 | P | N | N