## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 7, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 16303 | ALB | BISTI | MAINTENANCE | MAINTENANCE | 2001-05-10 08:00 | 2001-05-11 16:00 | 1.3 |  | OPS |  | 100 | 133.3 | Maintenance on the unit. |  | 2001-05-10 08:00 | 2001-05-13 16:00 | 100 | 333.3 | P | N | N
2 | 17392 | ALB | BLOOMFIELD | 3 | REPAIR PIPING | 2001-08-30 08:00 | 2001-08-31 09:00 | 1 |  | OPS |  | 125 | 130.2 | They need to refrabricate some discharge piping on #3 unit that has some stress on it. |  | 2001-08-30 08:00 | 2001-08-31 09:00 | 125 | 130.2 | P | N | N
3 | 16304 | ALB | GALLUP | MAINTENANCE | ANNUAL MAINTENANCE | 2001-05-11 08:00 | 2001-05-13 08:59 | 2 |  | OPS |  | 50 | 100 | Maintenance on the unit. |  | 2001-05-11 08:00 | 2001-05-13 12:00 | 50 | 108.3 | P | N | N
4 | 17370 | ALB | GALLUP | 1 | STATOR DAMAGE | 2001-08-19 08:00 | 2001-09-25 16:00 | 37.3 |  | OPS |  | 80 | 2986.7 | The Stator is damaged and they are not sure of the the completion time just yet. Plans are being put together to get the unit back ASAP. |  | 2001-08-19 14:30 | 2001-09-24 08:00 | 80 | 2860 | U | N | N
5 | 16132 | ALB | LA PLATA | A1002 | EXCHANGE & RED CEDAR TIE-IN | 2001-04-02 08:00 | 2001-04-05 16:00 | 3.3 |  | OPS |  | 300 | 1000 | Exchange PT GP & AGB (We are also doing a Red Cedar tie-in at the Arkansas Loop as well as a hot tap at Laplata Red Cedar). |  | 2001-04-02 08:00 | 2001-04-05 16:00 | 300 | 1000 | P | N | N
6 | 16263 | ALB | SAN JUAN | PIG & DRAG REDUCER | PIGGING & DRAG REDUCER APPLICATION | 2001-03-06 11:00 | 2001-03-07 06:00 | 0.8 |  | OPS |  | 615 | 486.9 | Pigging and application of the drag reducer. It should take 18 hour to apply. |  | 2001-03-06 11:00 | 2001-03-07 05:00 | 0 | 0 | P | N | N
7 | 16301 | ALB | SAN JUAN | MAINT. 1002 &1004 | ESD & MAINTENACE | 2001-05-08 08:00 | 2001-05-09 16:00 | 1.3 |  | OPS |  | 200 | 266.7 | ESD and Maintenace on units 1002 & 1004. Will start maint. on unit 1001 when 1002 and 1004 are complete. |  | 2001-05-08 08:00 | 2001-05-09 16:00 | 200 | 266.7 | P | N | N
8 | 16302 | ALB | SAN JUAN | MAINTENANCE 1001 | MAINTENACE | 2001-05-08 08:00 | 2001-05-09 16:00 | 1.3 |  | OPS |  | 200 | 266.7 | Maintenace on unit 1001. |  | 2001-05-08 08:00 | 2001-05-09 16:00 | 200 | 266.7 | P | N | N
9 | 16190 | ALB | STATION 1 | 102 | ANNUAL MAINTENANCE & COMPRESSOR VALVES | 2001-04-18 08:00 | 2001-04-29 16:00 | 11.3 |  | OPS |  | 50 | 566.7 | Annual maintenance and compressor valves. Repair all unloaders. |  | 2001-04-18 08:00 | 2001-05-02 16:00 | 50 | 716.7 | P | N | N
10 | 16192 | ALB | STATION 1 | 101 | ANNUAL MAINTENANCE & COMPRESSOR VALVES | 2001-04-30 08:00 | 2001-05-23 16:00 | 23.3 |  | OPS |  | 50 | 1166.7 | Annual maintenance and compressor valves. Cam components will be inspected and replaced as needed. Repair all unloaders. Maintenance & compressor valve work is complete. 05/16 Compro has started on Camshaft work. |  | 2001-05-03 07:30 | 2001-05-23 15:30 | 50 | 1016.7 | P | N | N
11 | 16193 | ALB | STATION 1 | 103 | SAFETY DEVICES & COMPRESSOR VALVES | 2001-05-11 08:00 | 2001-05-15 16:00 | 4.3 |  | OPS |  | 50 | 216.7 | Safety devices and replacing compressor valves. Repair all unloders. |  | 2001-05-03 16:30 | 2001-05-15 16:00 | 50 | 600 | P | N | N
12 | 16740 | ALB | STATION 1 | 103 | HOT BEARINGS | 2001-05-24 16:00 | 2001-05-31 16:00 | 7 |  | OPS |  | 50 | 350 | They need to take a look at and change some of the bearings on unit 103. Ronnie Morse is trying to locate some new ones asap. |  | 2001-05-24 16:00 | 2001-05-31 16:00 | 50 | 350 | U | N | N
13 | 16765 | ALB | STATION 1 | 103 | AFTERCOOLER & TURBOCHARGER | 2001-05-29 08:00 | 2001-05-31 15:00 | 2.3 |  | OPS |  | 0 | 0 | Downtime required to change out aftercooler on Unit 103. Send to shop. Have it repaired and reinstalled. Also Turbocharger replacement. 4000 HP (There was no flow affect with this outage due to the unit being down already for hot bearings. The flow affec | t was caught in that outage entry). | 2001-05-24 08:00 | 2001-05-31 15:00 | 0 | 0 | P | N | N
14 | 16848 | ALB | STATION 1 | 101 | MAINTENANCE | 2001-06-07 08:00 | 2001-06-08 16:00 | 1.3 |  | OPS |  | 50 | 66.7 | Change out turbo 2 heads piston liner & 6 comp. valves. |  | 2001-06-07 08:00 | 2001-06-11 09:00 | 50 | 202.1 | U | N | N
15 | 16849 | ALB | STATION 1 | 102 | MAINTENANCE | 2001-06-09 08:00 | 2001-06-09 16:00 | 0.3 |  | OPS |  | 50 | 16.7 | Change out 6 compressor valves. 400 HP |  | 2001-06-11 07:00 | 2001-06-11 16:00 | 50 | 18.8 | U | N | N
16 | 16850 | ALB | STATION 1 | 103 | MAINTENANCE | 2001-06-10 08:00 | 2001-06-10 16:00 | 0.3 |  | OPS |  | 50 | 16.7 | Change out 6 comp. valves. 400 HP |  | 2001-06-11 08:00 | 2001-06-11 14:00 | 50 | 12.5 | U | N | N
17 | 16748 | ALB | STATION 1 | 1 2 3 | DOWNLOAD OPTO | 2001-06-19 08:00 | 2001-06-19 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. | 2001-06-19 08:00 | 2001-06-19 18:00 | 50 | 20.8 | P | N | N
18 | 16749 | ALB | STATION 1 | 1 2 3 | DOWNLOAD OPTO | 2001-06-21 08:00 | 2001-06-21 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. | 2001-06-21 08:00 | 2001-06-21 18:00 | 50 | 20.8 | P | N | N
19 | 16194 | ALB | STATION 1 | 102 | MAINTENANCE | 2001-09-10 12:00 | 2001-09-11 16:00 | 1.2 |  | OPS |  | 0 | 0 | Maintenance. |  | 2001-09-10 12:30 | 2001-09-11 15:00 | 0 | 0 | P | N | N
20 | 17355 | ALB | STATION 1 | 103 | MAINTENANCE | 2001-09-13 07:00 | 2001-09-14 16:00 | 1.4 |  | OPS |  | 0 | 0 | Maintenance. |  | 2001-09-13 07:00 | 2001-09-17 16:00 | 0 | 0 | U | N | N
21 | 15972 | ALB | STATION 2 | 202 | ACESSORY DRIVE GEAR | 2001-01-02 16:14 | 2001-01-03 20:00 | 1.2 |  | OPS |  | 60 | 70 | Working on the Acessory drive gear. |  | 2001-01-02 16:14 | 2001-01-03 20:00 | 0 | 0 | U | N | N
22 | 16119 | ALB | STATION 2 | 203 | REPLACING PISTON LINER | 2001-02-01 05:00 | 2001-02-01 16:00 | 0.5 |  | OPS |  | 60 | 27.5 | The had to replace a piston liner. (Power end) |  | 2001-02-01 05:00 | 2001-02-01 18:00 | 0 | 0 | U | N | N
23 | 16284 | ALB | STATION 2 | 202 | CRACKED HUB | 2001-02-26 19:00 | 2001-02-28 12:00 | 1.7 |  | OPS |  | 80 | 136.7 | Cracked hub between the aux. drive gear and the gear that drives the kidney. (Replacing hub). |  | 2001-02-26 19:00 | 2001-02-28 12:00 | 0 | 0 | U | N | N
24 | 16182 | ALB | STATION 2 | 203 | OVERHAUL POWER CYLINDERS | 2001-04-02 08:00 | 2001-04-24 16:00 | 22.3 |  | OPS |  | 70 | 1563.3 | Overhaul 16 power cylinders. Inspect rod bearings and bump mains.Inspect cam components and replace as needed. Replace compressor valves.Annual maintenance and safety devices. |  | 2001-04-02 08:00 | 2001-04-19 16:00 | 70 | 1213.3 | P | N | N
25 | 16186 | ALB | STATION 2 | 201 | ANNUAL MAINTENANCE & SAFETY DEVICES | 2001-04-25 08:00 | 2001-05-02 16:00 | 7.3 |  | OPS |  | 70 | 513.3 | Annual maintenance and safety devices. Replacing compressor valves. Replacing Turbocharger and repair unloaders. |  | 2001-04-19 08:00 | 2001-04-26 16:00 | 70 | 513.3 | P | N | N
26 | 16184 | ALB | STATION 2 | 202 | OVERHAUL POWER CYLINDERS | 2001-05-03 08:00 | 2001-05-25 16:00 | 22.3 |  | OPS |  | 70 | 1563.3 | Overhaul 11 power cylinders. Inspect rod bearings and bump mains. Inspect cam components and replace as needed. Repair all unloaders. Replace compressor valves. Annual maintenance and safety devices. |  | 2001-04-26 16:00 | 2001-05-12 16:00 | 70 | 1120 | P | N | N
27 | 16715 | ALB | STATION 2 | 202 | TURBO CHARGER REPAIRS | 2001-05-14 15:00 | 2001-05-16 16:00 | 2 |  | OPS |  | 70 | 142.9 | They needed to repair turbo and after cooler. |  | 2001-05-14 15:00 | 2001-05-16 16:00 | 70 | 142.9 | U | N | N
28 | 16716 | ALB | STATION 2 | 203 | MINOR REPAIRS | 2001-05-16 20:30 | 2001-05-18 16:00 | 1.8 |  | OPS |  | 70 | 128.3 | They needed to go back and do some minor repairs an clean up work. 05/21 minor repair are complete. They are working on the Turbocharger now. Should be complete 05/23. |  | 2001-05-16 20:30 | 2001-05-18 16:00 | 70 | 128.3 | P | N | N
29 | 16747 | ALB | STATION 2 | 1 2 3 | DOWNLOAD OPTO | 2001-06-14 08:00 | 2001-06-14 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. | 2001-06-14 08:00 | 2001-06-14 18:00 | 50 | 20.8 | P | N | N
30 | 16746 | ALB | STATION 2 | 1 2 3 | DOWNLOAD OPTO | 2001-06-18 08:00 | 2001-06-18 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. | 2001-06-15 08:00 | 2001-06-15 18:00 | 50 | 20.8 | P | N | N
31 | 17090 | ALB | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-11-12 08:00 | 2001-11-15 16:00 | 3.3 |  | OPS |  | 180 | 600 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  | 2001-11-12 08:00 | 2001-11-15 16:00 | 180 | 600 | P | N | N
32 | 17091 | ALB | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-15 16:00 | 2001-11-19 16:00 | 4 |  | OPS |  | 180 | 720 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  | 2001-11-15 16:00 | 2001-11-17 16:00 | 180 | 360 | P | N | N
33 | 16191 | ALB | STATION 3 | 301 | ANNUAL MAINTENANCE & SAFETY DEVICES | 2001-05-01 08:00 | 2001-05-04 16:00 | 3.3 |  | OPS |  | 70 | 233.3 | Annual maintenance and safety devices. Replace compressor valves. |  | 2001-05-02 12:40 | 2001-05-05 09:00 | 70 | 201.3 | P | N | N
34 | 16189 | ALB | STATION 3 | 302 | ANNUAL MAINTENANCE & SAFETY DEVICES | 2001-05-04 08:00 | 2001-05-07 16:00 | 3.3 |  | OPS |  | 70 | 233.3 | Annual maintenance and safety devices. Replace compressor valves. |  | 2001-05-05 18:00 | 2001-05-06 09:00 | 70 | 43.8 | P | N | N
35 | 16187 | ALB | STATION 3 | 303 | ANNUAL MAINTENANCE & SAFETY DEVICES | 2001-05-07 08:00 | 2001-05-11 16:00 | 4.3 |  | OPS |  | 70 | 303.3 | Annual maintenance and safety devices. Replacing compressor valves. |  | 2001-05-06 07:00 | 2001-05-11 16:00 | 70 | 376.3 | P | N | N
36 | 16745 | ALB | STATION 3 | 1 2 3 | DOWNLOAD OPTO | 2001-06-18 08:00 | 2001-06-18 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. | 2001-06-18 08:00 | 2001-06-18 18:00 | 50 | 20.8 | P | N | N
37 | 16751 | ALB | STATION 3 | 1 | DOWNLOAD OPTO | 2001-06-28 08:00 | 2001-06-28 09:00 | 0 |  | OPS |  | 50 | 2.1 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. 4000 HP | 2001-06-28 08:00 | 2001-06-28 09:00 | 50 | 2.1 | P | N | N
38 | 16208 | ALB | STATION 4 | 402 | SERVICE | 2001-02-05 07:00 | 2001-02-05 15:00 | 0.3 |  | OPS |  | 190 | 63.3 | Replace indicator valve #1 compressor crank end #2 compressor head-end 3 suction and 3 discharge valves #1 compressor HESL HEST. Inspect doghouse bolts #3 counterweight - bad oil leak. |  | 2001-02-05 07:00 | 2001-02-05 15:00 | 190 | 63.3 | U | N | N
39 | 16185 | ALB | STATION 4 | 401 | ANNUAL MAINTENACE & SAFETY DEVICES | 2001-04-02 08:00 | 2001-04-09 16:00 | 7.3 |  | OPS |  | 100 | 733.3 | Annual maintenance and safety devices.Also replacing compressor valves. Inspect main bearings. |  | 2001-04-02 08:00 | 2001-04-11 08:00 | 100 | 900 | P | N | N
40 | 16183 | ALB | STATION 4 | 402 | ANNUAL MAINTENANCE & SAFETY DEVICES | 2001-04-09 08:00 | 2001-04-13 16:00 | 4.3 |  | OPS |  | 100 | 433.3 | Annual maintenance and safety devices.Replacing compressor valves. |  | 2001-04-11 08:00 | 2001-04-14 16:00 | 100 | 333.3 | P | N | N
41 | 16181 | ALB | STATION 4 | 403 | ANNUAL MAINTENANCE & SAFETY DEVICES | 2001-04-14 08:00 | 2001-04-18 16:00 | 4.3 |  | OPS |  | 100 | 433.3 | Annual maintenance and safety devices. Replacing compressor valves. |  | 2001-04-14 16:00 | 2001-04-18 16:00 | 100 | 400 | P | N | N
42 | 16744 | ALB | STATION 4 | 2 3 | DOWNLOAD OPTO | 2001-06-06 08:00 | 2001-06-06 18:00 | 0.4 |  | OPS |  | 120 | 50 | Downtime is required to download OPTO program changes ot obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. | 2001-06-04 08:00 | 2001-06-06 18:00 | 120 | 290 | P | N | N
43 | 16750 | ALB | STATION 4 | 401 | DOWNLOAD OPTO | 2001-06-26 08:00 | 2001-06-26 18:00 | 0.4 |  | OPS |  | 120 | 50 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. 4000 HP | 2001-06-24 08:00 | 2001-06-24 18:00 | 120 | 50 | P | N | N
44 | 16938 | ALB | STATION 4 | 401 402 403 | ESD BLOW DOWN | 2001-06-27 09:00 | 2001-06-27 13:00 | 0.2 |  | OPS |  | 120 | 20 | Unscheduled ESD complete blow down reset ESD system restart unig. 4000 HP Each. |  | 2001-06-27 09:00 | 2001-06-27 13:00 | 120 | 20 | U | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 7, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 16303 | ALB | BISTI | MAINTENANCE | MAINTENANCE | 2001-05-10 08:00 | 2001-05-11 16:00 | 1.3 |  | OPS |  | 100 | 133.3 | Maintenance on the unit. |  | 2001-05-10 08:00 | 2001-05-13 16:00 | 100 | 333.3 | P | N | N
2 | 17392 | ALB | BLOOMFIELD | 3 | REPAIR PIPING | 2001-08-30 08:00 | 2001-08-31 09:00 | 1 |  | OPS |  | 125 | 130.2 | They need to refrabricate some discharge piping on #3 unit that has some stress on it. |  | 2001-08-30 08:00 | 2001-08-31 09:00 | 125 | 130.2 | P | N | N
3 | 16304 | ALB | GALLUP | MAINTENANCE | ANNUAL MAINTENANCE | 2001-05-11 08:00 | 2001-05-13 08:59 | 2 |  | OPS |  | 50 | 100 | Maintenance on the unit. |  | 2001-05-11 08:00 | 2001-05-13 12:00 | 50 | 108.3 | P | N | N
4 | 17370 | ALB | GALLUP | 1 | STATOR DAMAGE | 2001-08-19 08:00 | 2001-09-25 16:00 | 37.3 |  | OPS |  | 80 | 2986.7 | The Stator is damaged and they are not sure of the the completion time just yet. Plans are being put together to get the unit back ASAP. |  | 2001-08-19 14:30 | 2001-09-24 08:00 | 80 | 2860 | U | N | N
5 | 16132 | ALB | LA PLATA | A1002 | EXCHANGE & RED CEDAR TIE-IN | 2001-04-02 08:00 | 2001-04-05 16:00 | 3.3 |  | OPS |  | 300 | 1000 | Exchange PT GP & AGB (We are also doing a Red Cedar tie-in at the Arkansas Loop as well as a hot tap at Laplata Red Cedar). |  | 2001-04-02 08:00 | 2001-04-05 16:00 | 300 | 1000 | P | N | N
6 | 16263 | ALB | SAN JUAN | PIG & DRAG REDUCER | PIGGING & DRAG REDUCER APPLICATION | 2001-03-06 11:00 | 2001-03-07 06:00 | 0.8 |  | OPS |  | 615 | 486.9 | Pigging and application of the drag reducer. It should take 18 hour to apply. |  | 2001-03-06 11:00 | 2001-03-07 05:00 | 0 | 0 | P | N | N
7 | 16301 | ALB | SAN JUAN | MAINT. 1002 &1004 | ESD & MAINTENACE | 2001-05-08 08:00 | 2001-05-09 16:00 | 1.3 |  | OPS |  | 200 | 266.7 | ESD and Maintenace on units 1002 & 1004. Will start maint. on unit 1001 when 1002 and 1004 are complete. |  | 2001-05-08 08:00 | 2001-05-09 16:00 | 200 | 266.7 | P | N | N
8 | 16302 | ALB | SAN JUAN | MAINTENANCE 1001 | MAINTENACE | 2001-05-08 08:00 | 2001-05-09 16:00 | 1.3 |  | OPS |  | 200 | 266.7 | Maintenace on unit 1001. |  | 2001-05-08 08:00 | 2001-05-09 16:00 | 200 | 266.7 | P | N | N
9 | 16190 | ALB | STATION 1 | 102 | ANNUAL MAINTENANCE & COMPRESSOR VALVES | 2001-04-18 08:00 | 2001-04-29 16:00 | 11.3 |  | OPS |  | 50 | 566.7 | Annual maintenance and compressor valves. Repair all unloaders. |  | 2001-04-18 08:00 | 2001-05-02 16:00 | 50 | 716.7 | P | N | N
10 | 16192 | ALB | STATION 1 | 101 | ANNUAL MAINTENANCE & COMPRESSOR VALVES | 2001-04-30 08:00 | 2001-05-23 16:00 | 23.3 |  | OPS |  | 50 | 1166.7 | Annual maintenance and compressor valves. Cam components will be inspected and replaced as needed. Repair all unloaders. Maintenance & compressor valve work is complete. 05/16 Compro has started on Camshaft work. |  | 2001-05-03 07:30 | 2001-05-23 15:30 | 50 | 1016.7 | P | N | N
11 | 16193 | ALB | STATION 1 | 103 | SAFETY DEVICES & COMPRESSOR VALVES | 2001-05-11 08:00 | 2001-05-15 16:00 | 4.3 |  | OPS |  | 50 | 216.7 | Safety devices and replacing compressor valves. Repair all unloders. |  | 2001-05-03 16:30 | 2001-05-15 16:00 | 50 | 600 | P | N | N
12 | 16740 | ALB | STATION 1 | 103 | HOT BEARINGS | 2001-05-24 16:00 | 2001-05-31 16:00 | 7 |  | OPS |  | 50 | 350 | They need to take a look at and change some of the bearings on unit 103. Ronnie Morse is trying to locate some new ones asap. |  | 2001-05-24 16:00 | 2001-05-31 16:00 | 50 | 350 | U | N | N
13 | 16765 | ALB | STATION 1 | 103 | AFTERCOOLER & TURBOCHARGER | 2001-05-29 08:00 | 2001-05-31 15:00 | 2.3 |  | OPS |  | 0 | 0 | Downtime required to change out aftercooler on Unit 103. Send to shop. Have it repaired and reinstalled. Also Turbocharger replacement. 4000 HP (There was no flow affect with this outage due to the unit being down already for hot bearings. The flow affec | t was caught in that outage entry). | 2001-05-24 08:00 | 2001-05-31 15:00 | 0 | 0 | P | N | N
14 | 16848 | ALB | STATION 1 | 101 | MAINTENANCE | 2001-06-07 08:00 | 2001-06-08 16:00 | 1.3 |  | OPS |  | 50 | 66.7 | Change out turbo 2 heads piston liner & 6 comp. valves. |  | 2001-06-07 08:00 | 2001-06-11 09:00 | 50 | 202.1 | U | N | N
15 | 16849 | ALB | STATION 1 | 102 | MAINTENANCE | 2001-06-09 08:00 | 2001-06-09 16:00 | 0.3 |  | OPS |  | 50 | 16.7 | Change out 6 compressor valves. 400 HP |  | 2001-06-11 07:00 | 2001-06-11 16:00 | 50 | 18.8 | U | N | N
16 | 16850 | ALB | STATION 1 | 103 | MAINTENANCE | 2001-06-10 08:00 | 2001-06-10 16:00 | 0.3 |  | OPS |  | 50 | 16.7 | Change out 6 comp. valves. 400 HP |  | 2001-06-11 08:00 | 2001-06-11 14:00 | 50 | 12.5 | U | N | N
17 | 16748 | ALB | STATION 1 | 1 2 3 | DOWNLOAD OPTO | 2001-06-19 08:00 | 2001-06-19 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. | 2001-06-19 08:00 | 2001-06-19 18:00 | 50 | 20.8 | P | N | N
18 | 16749 | ALB | STATION 1 | 1 2 3 | DOWNLOAD OPTO | 2001-06-21 08:00 | 2001-06-21 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. | 2001-06-21 08:00 | 2001-06-21 18:00 | 50 | 20.8 | P | N | N
19 | 16194 | ALB | STATION 1 | 102 | MAINTENANCE | 2001-09-10 12:00 | 2001-09-11 16:00 | 1.2 |  | OPS |  | 0 | 0 | Maintenance. |  | 2001-09-10 12:30 | 2001-09-11 15:00 | 0 | 0 | P | N | N
20 | 17355 | ALB | STATION 1 | 103 | MAINTENANCE | 2001-09-13 07:00 | 2001-09-14 16:00 | 1.4 |  | OPS |  | 0 | 0 | Maintenance. |  | 2001-09-13 07:00 | 2001-09-17 16:00 | 0 | 0 | U | N | N
21 | 15972 | ALB | STATION 2 | 202 | ACESSORY DRIVE GEAR | 2001-01-02 16:14 | 2001-01-03 20:00 | 1.2 |  | OPS |  | 60 | 70 | Working on the Acessory drive gear. |  | 2001-01-02 16:14 | 2001-01-03 20:00 | 0 | 0 | U | N | N
22 | 16119 | ALB | STATION 2 | 203 | REPLACING PISTON LINER | 2001-02-01 05:00 | 2001-02-01 16:00 | 0.5 |  | OPS |  | 60 | 27.5 | The had to replace a piston liner. (Power end) |  | 2001-02-01 05:00 | 2001-02-01 18:00 | 0 | 0 | U | N | N
23 | 16284 | ALB | STATION 2 | 202 | CRACKED HUB | 2001-02-26 19:00 | 2001-02-28 12:00 | 1.7 |  | OPS |  | 80 | 136.7 | Cracked hub between the aux. drive gear and the gear that drives the kidney. (Replacing hub). |  | 2001-02-26 19:00 | 2001-02-28 12:00 | 0 | 0 | U | N | N
24 | 16182 | ALB | STATION 2 | 203 | OVERHAUL POWER CYLINDERS | 2001-04-02 08:00 | 2001-04-24 16:00 | 22.3 |  | OPS |  | 70 | 1563.3 | Overhaul 16 power cylinders. Inspect rod bearings and bump mains.Inspect cam components and replace as needed. Replace compressor valves.Annual maintenance and safety devices. |  | 2001-04-02 08:00 | 2001-04-19 16:00 | 70 | 1213.3 | P | N | N
25 | 16186 | ALB | STATION 2 | 201 | ANNUAL MAINTENANCE & SAFETY DEVICES | 2001-04-25 08:00 | 2001-05-02 16:00 | 7.3 |  | OPS |  | 70 | 513.3 | Annual maintenance and safety devices. Replacing compressor valves. Replacing Turbocharger and repair unloaders. |  | 2001-04-19 08:00 | 2001-04-26 16:00 | 70 | 513.3 | P | N | N
26 | 16184 | ALB | STATION 2 | 202 | OVERHAUL POWER CYLINDERS | 2001-05-03 08:00 | 2001-05-25 16:00 | 22.3 |  | OPS |  | 70 | 1563.3 | Overhaul 11 power cylinders. Inspect rod bearings and bump mains. Inspect cam components and replace as needed. Repair all unloaders. Replace compressor valves. Annual maintenance and safety devices. |  | 2001-04-26 16:00 | 2001-05-12 16:00 | 70 | 1120 | P | N | N
27 | 16715 | ALB | STATION 2 | 202 | TURBO CHARGER REPAIRS | 2001-05-14 15:00 | 2001-05-16 16:00 | 2 |  | OPS |  | 70 | 142.9 | They needed to repair turbo and after cooler. |  | 2001-05-14 15:00 | 2001-05-16 16:00 | 70 | 142.9 | U | N | N
28 | 16716 | ALB | STATION 2 | 203 | MINOR REPAIRS | 2001-05-16 20:30 | 2001-05-18 16:00 | 1.8 |  | OPS |  | 70 | 128.3 | They needed to go back and do some minor repairs an clean up work. 05/21 minor repair are complete. They are working on the Turbocharger now. Should be complete 05/23. |  | 2001-05-16 20:30 | 2001-05-18 16:00 | 70 | 128.3 | P | N | N
29 | 16747 | ALB | STATION 2 | 1 2 3 | DOWNLOAD OPTO | 2001-06-14 08:00 | 2001-06-14 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. | 2001-06-14 08:00 | 2001-06-14 18:00 | 50 | 20.8 | P | N | N
30 | 16746 | ALB | STATION 2 | 1 2 3 | DOWNLOAD OPTO | 2001-06-18 08:00 | 2001-06-18 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. | 2001-06-15 08:00 | 2001-06-15 18:00 | 50 | 20.8 | P | N | N
31 | 17090 | ALB | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-11-12 08:00 | 2001-11-15 16:00 | 3.3 |  | OPS |  | 180 | 600 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  | 2001-11-12 08:00 | 2001-11-15 16:00 | 180 | 600 | P | N | N
32 | 17091 | ALB | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-15 16:00 | 2001-11-19 16:00 | 4 |  | OPS |  | 180 | 720 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  | 2001-11-15 16:00 | 2001-11-17 16:00 | 180 | 360 | P | N | N
33 | 16191 | ALB | STATION 3 | 301 | ANNUAL MAINTENANCE & SAFETY DEVICES | 2001-05-01 08:00 | 2001-05-04 16:00 | 3.3 |  | OPS |  | 70 | 233.3 | Annual maintenance and safety devices. Replace compressor valves. |  | 2001-05-02 12:40 | 2001-05-05 09:00 | 70 | 201.3 | P | N | N
34 | 16189 | ALB | STATION 3 | 302 | ANNUAL MAINTENANCE & SAFETY DEVICES | 2001-05-04 08:00 | 2001-05-07 16:00 | 3.3 |  | OPS |  | 70 | 233.3 | Annual maintenance and safety devices. Replace compressor valves. |  | 2001-05-05 18:00 | 2001-05-06 09:00 | 70 | 43.8 | P | N | N
35 | 16187 | ALB | STATION 3 | 303 | ANNUAL MAINTENANCE & SAFETY DEVICES | 2001-05-07 08:00 | 2001-05-11 16:00 | 4.3 |  | OPS |  | 70 | 303.3 | Annual maintenance and safety devices. Replacing compressor valves. |  | 2001-05-06 07:00 | 2001-05-11 16:00 | 70 | 376.3 | P | N | N
36 | 16745 | ALB | STATION 3 | 1 2 3 | DOWNLOAD OPTO | 2001-06-18 08:00 | 2001-06-18 18:00 | 0.4 |  | OPS |  | 50 | 20.8 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. | 2001-06-18 08:00 | 2001-06-18 18:00 | 50 | 20.8 | P | N | N
37 | 16751 | ALB | STATION 3 | 1 | DOWNLOAD OPTO | 2001-06-28 08:00 | 2001-06-28 09:00 | 0 |  | OPS |  | 50 | 2.1 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. 4000 HP | 2001-06-28 08:00 | 2001-06-28 09:00 | 50 | 2.1 | P | N | N
38 | 16208 | ALB | STATION 4 | 402 | SERVICE | 2001-02-05 07:00 | 2001-02-05 15:00 | 0.3 |  | OPS |  | 190 | 63.3 | Replace indicator valve #1 compressor crank end #2 compressor head-end 3 suction and 3 discharge valves #1 compressor HESL HEST. Inspect doghouse bolts #3 counterweight - bad oil leak. |  | 2001-02-05 07:00 | 2001-02-05 15:00 | 190 | 63.3 | U | N | N
39 | 16185 | ALB | STATION 4 | 401 | ANNUAL MAINTENACE & SAFETY DEVICES | 2001-04-02 08:00 | 2001-04-09 16:00 | 7.3 |  | OPS |  | 100 | 733.3 | Annual maintenance and safety devices.Also replacing compressor valves. Inspect main bearings. |  | 2001-04-02 08:00 | 2001-04-11 08:00 | 100 | 900 | P | N | N
40 | 16183 | ALB | STATION 4 | 402 | ANNUAL MAINTENANCE & SAFETY DEVICES | 2001-04-09 08:00 | 2001-04-13 16:00 | 4.3 |  | OPS |  | 100 | 433.3 | Annual maintenance and safety devices.Replacing compressor valves. |  | 2001-04-11 08:00 | 2001-04-14 16:00 | 100 | 333.3 | P | N | N
41 | 16181 | ALB | STATION 4 | 403 | ANNUAL MAINTENANCE & SAFETY DEVICES | 2001-04-14 08:00 | 2001-04-18 16:00 | 4.3 |  | OPS |  | 100 | 433.3 | Annual maintenance and safety devices. Replacing compressor valves. |  | 2001-04-14 16:00 | 2001-04-18 16:00 | 100 | 400 | P | N | N
42 | 16744 | ALB | STATION 4 | 2 3 | DOWNLOAD OPTO | 2001-06-06 08:00 | 2001-06-06 18:00 | 0.4 |  | OPS |  | 120 | 50 | Downtime is required to download OPTO program changes ot obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. | 2001-06-04 08:00 | 2001-06-06 18:00 | 120 | 290 | P | N | N
43 | 16750 | ALB | STATION 4 | 401 | DOWNLOAD OPTO | 2001-06-26 08:00 | 2001-06-26 18:00 | 0.4 |  | OPS |  | 120 | 50 | Downtime is required to download OPTO program changes to obtain volumes above 1090 mmscfd. One unit at a time will be shut down. The first unit may be up and down 4-5 times; once the program is proven the other two units will be shutdown long enough to do | wnload the unit control program. 4000 HP | 2001-06-24 08:00 | 2001-06-24 18:00 | 120 | 50 | P | N | N
44 | 16938 | ALB | STATION 4 | 401 402 403 | ESD BLOW DOWN | 2001-06-27 09:00 | 2001-06-27 13:00 | 0.2 |  | OPS |  | 120 | 20 | Unscheduled ESD complete blow down reset ESD system restart unig. 4000 HP Each. |  | 2001-06-27 09:00 | 2001-06-27 13:00 | 120 | 20 | U | N | N