## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2001 Through December, 2001
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted July 20, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | (Mmcf)
1 | 16194 | ALB | STATION 1 | 102 | SAFETY DEVICES | 2001-09-18 08:00 | 2001-09-20 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. |  |  |  | 0 | P | N | N
2 | 16195 | ALB | STATION 1 | 101 | SAFETY DEVICES | 2001-09-25 08:00 | 2001-09-27 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. |  |  |  | 0 | P | N | N
3 | 17090 | ALB | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-10-22 08:00 | 2001-10-26 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
4 | 17091 | ALB | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-05 08:00 | 2001-11-07 16:00 | 2.3 |  | OPS |  | 130 | 303.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
5 | 16521 | ALB | STATION 3 | 321 | OVERHAUL | 2001-11-05 08:00 | 2001-11-23 16:00 | 18.3 |  | OPS |  | 0 | 0 | Engine overhaul. |  |  |  | 0 | P | N | N
6 | 16900 | ALB | STATION 8 | MAINLINE | MAINLINE BLOCK | 2001-07-23 08:00 | 2001-08-03 16:00 | 11.3 |  | OPS |  | 0 | 0 | Remove 1 section of mainline from service for 4 days. Block pipeline for 2 hours to use station compression to lower section pressure by transferring gas from mainline west of station to mainline east of station then reestablish bypass conditions. |  |  |  | 0 | P | N | N
7 | 16752 | ALB | STATION 8 | 2 | AUTOMATION | 2001-09-04 08:00 | 2001-10-31 16:00 | 57.3 |  | OPS |  | 0 | 0 | Station 8 automation project. 8000 HP |  |  |  | 0 | P | N | N
8 | 17089 | ALB | STATION 9 | CHECK VALVE | REPLACE CHECK VALVE | 2001-07-20 09:00 | 2001-07-20 13:00 | 0.2 |  | OPS |  | 0 | 0 | They need to replace leaking check valve on the surge valve. |  |  |  | 0 | U | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2001 Through December, 2001
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted July 20, 2001 | [10 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[11 empty] | (Mmcfd) | (Mmcf)
1 | 16194 | STATION 1 | 102 | SAFETY DEVICES | 2001-09-18 08:00 | 2001-09-20 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. |  |  |  | 0 | P | N | N
2 | 16195 | STATION 1 | 101 | SAFETY DEVICES | 2001-09-25 08:00 | 2001-09-27 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. |  |  |  | 0 | P | N | N
3 | 17090 | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-10-22 08:00 | 2001-10-26 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
4 | 17091 | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-05 08:00 | 2001-11-07 16:00 | 2.3 |  | OPS |  | 130 | 303.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
5 | 16521 | STATION 3 | 321 | OVERHAUL | 2001-11-05 08:00 | 2001-11-23 16:00 | 18.3 |  | OPS |  | 0 | 0 | Engine overhaul. |  |  |  | 0 | P | N | N
6 | 16900 | STATION 8 | MAINLINE | MAINLINE BLOCK | 2001-07-23 08:00 | 2001-08-03 16:00 | 11.3 |  | OPS |  | 0 | 0 | Remove 1 section of mainline from service for 4 days. Block pipeline for 2 hours to use station compression to lower section pressure by transferring gas from mainline west of station to mainline east of station then reestablish bypass conditions. |  |  |  | 0 | P | N | N
7 | 16752 | STATION 8 | 2 | AUTOMATION | 2001-09-04 08:00 | 2001-10-31 16:00 | 57.3 |  | OPS |  | 0 | 0 | Station 8 automation project. 8000 HP |  |  |  | 0 | P | N | N
8 | 17089 | STATION 9 | CHECK VALVE | REPLACE CHECK VALVE | 2001-07-20 09:00 | 2001-07-20 13:00 | 0.2 |  | OPS |  | 0 | 0 | They need to replace leaking check valve on the surge valve. |  |  |  | 0 | U | N | N