## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through March 31, 2002
NORTHERN & TRANSWESTERN Regions Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 8, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17144 | ALB | ATOKA 1 | 719 | HEAD EXCHANGE | 2002-03-05 08:00 | 2002-03-07 16:00 | 2.3 |  | OPS |  | 0 | 0 | Complete UX head exchange. Contractor will remove all power heads. Inspect combustion chambers clean and reinstall new heads. (Flow affect is zero, but suction comes up some). |  |  |  | 0 | P | N | N
2 | 17142 | ALB | ATOKA 1 | 719 | OVERHAUL | 2002-03-12 08:00 | 2002-03-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul replace rings packing R&R all valves inspect cylinders for wear and check rod and main bearings. (Flow affect is zero, but suction comes up some). |  |  |  | 0 | P | N | N
3 | 17145 | ALB | ATOKA 1 | 737 | OVERHAUL | 2002-03-18 08:00 | 2002-03-22 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. (Flow affect is zero, but suction comes up some). |  |  |  | 0 | P | N | N
4 | 17146 | ALB | ATOKA 3 | 761 | OVERHAUL | 2002-03-25 08:00 | 2002-03-29 16:00 | 4.3 |  | OPS |  | 3 | 13 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. |  |  |  | 0 | P | N | N
5 | 18242 | ALB | ATOKA 3 | 761 | REALIGN EXHAUST HEADER | 2002-01-08 07:00 | 2002-01-10 08:00 | 2 |  | OPS |  | 3 | 6.2 | Cooper pulling all heads gaskets and realign exhaust header & intake. Changing #6 head with new one. |  |  |  | 0 | U | N | N
6 | 17148 | ALB | CRAWFORD | 751 | OVERHAUL | 2002-03-11 08:00 | 2002-03-13 16:00 | 2.3 |  | OPS |  | 30 | 60.3 | Complete UX turbine exchange. Contractor will remove old turbine and install and align new reconditioned turbine. (Flow affect depends on total noms. The flow affect is from the total capacity). |  |  |  | 0 | P | N | N
7 | 18243 | ALB | CRAWFORD | CONTROL VALVE | INSTALL CONTROL VALVE | 2002-03-12 08:00 | 2002-03-12 16:00 | 0.3 |  | OPS |  | 60 | 15 | Installing two elbows in the 16" line in order to put in the flow control valve for existing Duke I/C inside the Crawford compressor station. |  |  |  | 0 | P | N | N
8 | 17092 | ALB | STATION 1 | MAINLINE | RED ROCK TIE-IN | 2002-03-04 08:00 | 2002-03-08 16:00 | 4.3 |  | OPS |  | 0 | 0 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. (The flow affect is captured in the Stati | on 4 overhaul Outage). |  |  | 0 | P | N | N
9 | 17093 | ALB | STATION 1 | LOOP LINE | RED ROCK TIE-IN | 2002-03-11 08:00 | 2002-03-13 16:00 | 2.3 |  | OPS |  | 0 | 0 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. (The flow affect is captured in the Stati | on 4 overhaul Outage). |  |  | 0 | P | N | N
10 | 17095 | ALB | STATION 3 | MAINLINE | RED ROCK TIE-IN | 2002-03-18 08:00 | 2002-03-22 16:00 | 4.3 |  | OPS |  | 0 | 0 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. (The flow affect is captured in the Stati | on 4 overhaul Outage). |  |  | 0 | P | N | N
11 | 17096 | ALB | STATION 3 | LOOP LINE | RED ROCK TIE-IN | 2002-03-25 08:00 | 2002-03-27 16:00 | 2.3 |  | OPS |  | 0 | 0 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. (The flow affect is captured in the Stati | on 4 overhaul Outage). |  |  | 0 | P | N | N
12 | 17128 | ALB | STATION 4 | 401 | OVERHAUL | 2002-03-01 08:00 | 2002-04-09 16:00 | 39.3 |  | OPS |  | 200 | 7866.7 | Contractor will disassemble unit all the way to the lower block. Compressor will be overhauled with new rods packing ring and all new compressor valves unit realigned and rechocked. |  |  |  | 0 | P | N | N
13 | 17837 | LIB | HOLCOMB | 1 | ANNUAL MAINTENANCE | 2002-01-17 08:00 | 2002-01-18 16:00 | 1.3 |  | OPS |  | 6 | 6.3 | Doing their annual maintenance. (Holcomb South) |  |  |  | 0 | P | N | N
14 | 17838 | LIB | HOLCOMB | 2 | ANNUAL MAINTENANCE | 2002-02-15 08:00 | 2002-02-16 16:00 | 1.3 |  | OPS |  | 6 | 6.3 | Annual maintenance. (Holcomb South) |  |  |  | 0 | P | N | N
15 | 18057 | LIB | HUGOTON | 16 | MAINTENANCE | 2002-01-17 08:00 | 2002-01-17 14:00 | 0.3 |  | OPS |  | 15 | 3.8 | Service & maintenance. 1800 HP |  |  |  | 0 | P | N | N
16 | 18058 | LIB | HUGOTON | 17 | MAINTENANCE | 2002-03-20 08:00 | 2002-03-20 14:00 | 0.3 |  | OPS |  | 15 | 3.8 | Service and maintenance. 1800 HP |  |  |  | 0 | P | N | N
17 | 17879 | LIB | STEVENS 4 | 1 | SERVICE | 2002-01-09 08:00 | 2002-01-10 16:00 | 1.3 |  | OPS |  | 3 | 4 | Service unit & MP 2. |  |  |  | 0 | P | N | N
18 | 17883 | LIB | STEVENS 4 | 2 | SERVICE | 2002-03-13 08:00 | 2002-03-14 16:00 | 1.3 |  | OPS |  | 3 | 4 | Service unit & MP 2. |  |  |  | 0 | P | N | N
19 | 18060 | LIB | STEVENS 7 | 4 | MP2 | 2002-01-08 09:00 | 2002-01-10 16:00 | 2.3 |  | OPS |  | 4 | 9.2 | MP2 Tasks. |  |  |  | 0 | P | N | N
20 | 18061 | LIB | STEVENS 7 | 2 | MP2 | 2002-02-05 09:00 | 2002-02-07 16:00 | 2.3 |  | OPS |  | 4 | 9.2 | MP2 Tasks. |  |  |  | 0 | P | N | N
21 | 18062 | LIB | STEVENS 7 | 1 | MP2 | 2002-03-05 09:00 | 2002-03-07 16:00 | 2.3 |  | OPS |  | 4 | 9.2 | MP2 Tasks. |  |  |  | 0 | P | N | N
22 | 17978 | LIB | SUBLETTE | 26 | Power Turbine | 2001-09-20 08:00 | 2002-01-31 16:00 | 133.2 |  | OPS |  | 0 | 0 | They are replacing the power turbine. |  |  |  | 0 | U | N | N
23 | 18227 | MID | KERMIT | 1 | FUEL VALVES | 2002-01-08 08:00 | 2002-01-21 16:00 | 14.3 |  | OPS |  | 0 | 0 | They need the fuel valves repaired. They will take them off and send them in for repairs. Also the will do anual maintenance on the unit while it is down. |  |  |  | 0 | P | N | N
24 | 18240 | MIN | NORTH BRANCH | 3 | MP2 & MAINTENANCE | 2002-01-14 07:00 | 2002-01-31 15:30 | 17.3 |  | OPS |  | 0 | 0 | MP2 - Torque anchor bolts inspect all chains and gears inspect x-heads & shoe clearance inspect bearing clearance check comp. piston clearance start air valve maintenace crank shaft deflection comp. rod run out and analyze the unit(recip. trap). |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through March 31, 2002
NORTHERN & TRANSWESTERN Regions Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 8, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17144 | ALB | ATOKA 1 | 719 | HEAD EXCHANGE | 2002-03-05 08:00 | 2002-03-07 16:00 | 2.3 |  | OPS |  | 0 | 0 | Complete UX head exchange. Contractor will remove all power heads. Inspect combustion chambers clean and reinstall new heads. (Flow affect is zero, but suction comes up some). |  |  |  | 0 | P | N | N
2 | 17142 | ALB | ATOKA 1 | 719 | OVERHAUL | 2002-03-12 08:00 | 2002-03-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul replace rings packing R&R all valves inspect cylinders for wear and check rod and main bearings. (Flow affect is zero, but suction comes up some). |  |  |  | 0 | P | N | N
3 | 17145 | ALB | ATOKA 1 | 737 | OVERHAUL | 2002-03-18 08:00 | 2002-03-22 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. (Flow affect is zero, but suction comes up some). |  |  |  | 0 | P | N | N
4 | 17146 | ALB | ATOKA 3 | 761 | OVERHAUL | 2002-03-25 08:00 | 2002-03-29 16:00 | 4.3 |  | OPS |  | 3 | 13 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. |  |  |  | 0 | P | N | N
5 | 18242 | ALB | ATOKA 3 | 761 | REALIGN EXHAUST HEADER | 2002-01-08 07:00 | 2002-01-10 08:00 | 2 |  | OPS |  | 3 | 6.2 | Cooper pulling all heads gaskets and realign exhaust header & intake. Changing #6 head with new one. |  |  |  | 0 | U | N | N
6 | 17148 | ALB | CRAWFORD | 751 | OVERHAUL | 2002-03-11 08:00 | 2002-03-13 16:00 | 2.3 |  | OPS |  | 30 | 60.3 | Complete UX turbine exchange. Contractor will remove old turbine and install and align new reconditioned turbine. (Flow affect depends on total noms. The flow affect is from the total capacity). |  |  |  | 0 | P | N | N
7 | 18243 | ALB | CRAWFORD | CONTROL VALVE | INSTALL CONTROL VALVE | 2002-03-12 08:00 | 2002-03-12 16:00 | 0.3 |  | OPS |  | 60 | 15 | Installing two elbows in the 16" line in order to put in the flow control valve for existing Duke I/C inside the Crawford compressor station. |  |  |  | 0 | P | N | N
8 | 17092 | ALB | STATION 1 | MAINLINE | RED ROCK TIE-IN | 2002-03-04 08:00 | 2002-03-08 16:00 | 4.3 |  | OPS |  | 0 | 0 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. (The flow affect is captured in the Stati | on 4 overhaul Outage). |  |  | 0 | P | N | N
9 | 17093 | ALB | STATION 1 | LOOP LINE | RED ROCK TIE-IN | 2002-03-11 08:00 | 2002-03-13 16:00 | 2.3 |  | OPS |  | 0 | 0 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. (The flow affect is captured in the Stati | on 4 overhaul Outage). |  |  | 0 | P | N | N
10 | 17095 | ALB | STATION 3 | MAINLINE | RED ROCK TIE-IN | 2002-03-18 08:00 | 2002-03-22 16:00 | 4.3 |  | OPS |  | 0 | 0 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. (The flow affect is captured in the Stati | on 4 overhaul Outage). |  |  | 0 | P | N | N
11 | 17096 | ALB | STATION 3 | LOOP LINE | RED ROCK TIE-IN | 2002-03-25 08:00 | 2002-03-27 16:00 | 2.3 |  | OPS |  | 0 | 0 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. (The flow affect is captured in the Stati | on 4 overhaul Outage). |  |  | 0 | P | N | N
12 | 17128 | ALB | STATION 4 | 401 | OVERHAUL | 2002-03-01 08:00 | 2002-04-09 16:00 | 39.3 |  | OPS |  | 200 | 7866.7 | Contractor will disassemble unit all the way to the lower block. Compressor will be overhauled with new rods packing ring and all new compressor valves unit realigned and rechocked. |  |  |  | 0 | P | N | N
13 | 17837 | LIB | HOLCOMB | 1 | ANNUAL MAINTENANCE | 2002-01-17 08:00 | 2002-01-18 16:00 | 1.3 |  | OPS |  | 6 | 6.3 | Doing their annual maintenance. (Holcomb South) |  |  |  | 0 | P | N | N
14 | 17838 | LIB | HOLCOMB | 2 | ANNUAL MAINTENANCE | 2002-02-15 08:00 | 2002-02-16 16:00 | 1.3 |  | OPS |  | 6 | 6.3 | Annual maintenance. (Holcomb South) |  |  |  | 0 | P | N | N
15 | 18057 | LIB | HUGOTON | 16 | MAINTENANCE | 2002-01-17 08:00 | 2002-01-17 14:00 | 0.3 |  | OPS |  | 15 | 3.8 | Service & maintenance. 1800 HP |  |  |  | 0 | P | N | N
16 | 18058 | LIB | HUGOTON | 17 | MAINTENANCE | 2002-03-20 08:00 | 2002-03-20 14:00 | 0.3 |  | OPS |  | 15 | 3.8 | Service and maintenance. 1800 HP |  |  |  | 0 | P | N | N
17 | 17879 | LIB | STEVENS 4 | 1 | SERVICE | 2002-01-09 08:00 | 2002-01-10 16:00 | 1.3 |  | OPS |  | 3 | 4 | Service unit & MP 2. |  |  |  | 0 | P | N | N
18 | 17883 | LIB | STEVENS 4 | 2 | SERVICE | 2002-03-13 08:00 | 2002-03-14 16:00 | 1.3 |  | OPS |  | 3 | 4 | Service unit & MP 2. |  |  |  | 0 | P | N | N
19 | 18060 | LIB | STEVENS 7 | 4 | MP2 | 2002-01-08 09:00 | 2002-01-10 16:00 | 2.3 |  | OPS |  | 4 | 9.2 | MP2 Tasks. |  |  |  | 0 | P | N | N
20 | 18061 | LIB | STEVENS 7 | 2 | MP2 | 2002-02-05 09:00 | 2002-02-07 16:00 | 2.3 |  | OPS |  | 4 | 9.2 | MP2 Tasks. |  |  |  | 0 | P | N | N
21 | 18062 | LIB | STEVENS 7 | 1 | MP2 | 2002-03-05 09:00 | 2002-03-07 16:00 | 2.3 |  | OPS |  | 4 | 9.2 | MP2 Tasks. |  |  |  | 0 | P | N | N
22 | 17978 | LIB | SUBLETTE | 26 | Power Turbine | 2001-09-20 08:00 | 2002-01-31 16:00 | 133.2 |  | OPS |  | 0 | 0 | They are replacing the power turbine. |  |  |  | 0 | U | N | N
23 | 18227 | MID | KERMIT | 1 | FUEL VALVES | 2002-01-08 08:00 | 2002-01-21 16:00 | 14.3 |  | OPS |  | 0 | 0 | They need the fuel valves repaired. They will take them off and send them in for repairs. Also the will do anual maintenance on the unit while it is down. |  |  |  | 0 | P | N | N
24 | 18240 | MIN | NORTH BRANCH | 3 | MP2 & MAINTENANCE | 2002-01-14 07:00 | 2002-01-31 15:30 | 17.3 |  | OPS |  | 0 | 0 | MP2 - Torque anchor bolts inspect all chains and gears inspect x-heads & shoe clearance inspect bearing clearance check comp. piston clearance start air valve maintenace crank shaft deflection comp. rod run out and analyze the unit(recip. trap). |  |  |  | 0 | P | N | N