## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2001 Through December, 2001
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted August 9,, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | (Mmcf)
1 | 17216 | ALB | KINGMAN | PG&E STN | PG&E MEAS STN | 2001-09-19 07:00 | 2001-09-20 07:00 | 1 |  | OPS |  | 0 | 0 | Change out filters and econ filter case at PG&E/TW Measurement Station. (The flow at PG&E and South Socal will be taken to zero). |  |  |  | 0 | P | N | N
2 | 16194 | ALB | STATION 1 | 102 | SAFETY DEVICES | 2001-09-19 08:00 | 2001-09-20 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. |  |  |  | 0 | P | N | N
3 | 16195 | ALB | STATION 1 | 101 | SAFETY DEVICES | 2001-09-25 08:00 | 2001-09-27 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. |  |  |  | 0 | P | N | N
4 | 17090 | ALB | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-10-22 08:00 | 2001-10-26 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
5 | 17091 | ALB | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-05 08:00 | 2001-11-07 16:00 | 2.3 |  | OPS |  | 130 | 303.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
6 | 16900 | ALB | STATION 8 | MAINLINE | MAINLINE BLOCK | 2001-08-28 08:00 | 2001-08-31 16:00 | 3.3 |  | OPS |  | 0 | 0 | Remove 1 section of mainline from service for 4 days. Block pipeline for 2 hours to use station compression to lower section pressure by transferring gas from mainline west of station to mainline east of station then reestablish bypass conditions. |  |  |  | 0 | P | N | N
7 | 16752 | ALB | STATION 8 | 802 | AUTOMATION | 2001-09-04 08:00 | 2001-10-31 16:00 | 57.3 |  | OPS |  | 0 | 0 | Station 8 automation project. 8000 HP |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2001 Through December, 2001
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted August 9,, 2001 | [10 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[11 empty] | (Mmcfd) | (Mmcf)
1 | 17216 | KINGMAN | PG&E STN | PG&E MEAS STN | 2001-09-19 07:00 | 2001-09-20 07:00 | 1 |  | OPS |  | 0 | 0 | Change out filters and econ filter case at PG&E/TW Measurement Station. (The flow at PG&E and South Socal will be taken to zero). |  |  |  | 0 | P | N | N
2 | 16194 | STATION 1 | 102 | SAFETY DEVICES | 2001-09-19 08:00 | 2001-09-20 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. |  |  |  | 0 | P | N | N
3 | 16195 | STATION 1 | 101 | SAFETY DEVICES | 2001-09-25 08:00 | 2001-09-27 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. |  |  |  | 0 | P | N | N
4 | 17090 | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-10-22 08:00 | 2001-10-26 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
5 | 17091 | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-05 08:00 | 2001-11-07 16:00 | 2.3 |  | OPS |  | 130 | 303.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
6 | 16900 | STATION 8 | MAINLINE | MAINLINE BLOCK | 2001-08-28 08:00 | 2001-08-31 16:00 | 3.3 |  | OPS |  | 0 | 0 | Remove 1 section of mainline from service for 4 days. Block pipeline for 2 hours to use station compression to lower section pressure by transferring gas from mainline west of station to mainline east of station then reestablish bypass conditions. |  |  |  | 0 | P | N | N
7 | 16752 | STATION 8 | 802 | AUTOMATION | 2001-09-04 08:00 | 2001-10-31 16:00 | 57.3 |  | OPS |  | 0 | 0 | Station 8 automation project. 8000 HP |  |  |  | 0 | P | N | N