## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2001 Through December, 2001
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted August 23, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | (Mmcf)
1 | 17370 | ALB | GALLUP | 1 | STATOR DAMAGE | 2001-08-19 08:00 | 2001-09-07 16:00 | 19.3 |  | OPS |  | 80 | 1546.7 | Part of the Stator is damaged and they are not sure if it can be repaired in place at this time. |  | 2001-08-19 14:30 |  | 0 | U | N | N
2 | 17216 | ALB | KINGMAN | PG&E STN | PG&E MEAS STN | 2001-09-19 07:00 | 2001-09-20 07:00 | 1 |  | OPS |  | 0 | 0 | Change out filters and econ filter case at PG&E/TW Measurement Station. (The flow at PG&E and South Socal will be taken to zero). |  |  |  | 0 | P | N | N
3 | 16195 | ALB | STATION 1 | 101 | SAFETY DEVICES TURBO & PISTON LINERS | 2001-09-17 08:00 | 2001-09-19 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. Change out Turbo water pump and change piston liners and maybe some heads. Group valve as "Compressor Health Report". |  |  |  | 0 | P | N | N
4 | 16194 | ALB | STATION 1 | 102 | SAFETY DEVICES & MAINTENANCE | 2001-09-19 08:00 | 2001-09-20 16:00 | 1.3 |  | OPS |  | 50 | 66.7 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
5 | 17355 | ALB | STATION 1 | 103 | MAINTENANCE | 2001-09-20 07:00 | 2001-09-21 16:00 | 1.4 |  | OPS |  | 50 | 68.8 | Maintenance. |  |  |  | 0 | U | N | N
6 | 17090 | ALB | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-10-22 08:00 | 2001-10-26 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
7 | 17091 | ALB | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-05 08:00 | 2001-11-07 16:00 | 2.3 |  | OPS |  | 130 | 303.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
8 | 17306 | ALB | STATION 5 |  | CALIPER PIG RUN | 2001-08-28 08:00 | 2001-08-29 16:00 | 1.3 |  | OPS |  | 0 | 0 | Run tool in Loop line Sta. 5 (Thoreau) to Sta. 4 (Section 5) pick up AGM's. Retrieve data and set pig up for next run at Station 4 (Klagetoh)) Haul pig to Sta. 5 - set out AGM's. |  |  |  | 0 | P | N | N
9 | 17307 | ALB | STATION 5 |  | CALIPER PIG RUN | 2001-08-30 08:00 | 2001-08-31 16:00 | 1.3 |  | OPS |  | 0 | 0 | Run tool in mainline from Sta. 5 to Sta. 4 (Section 5) pick up AGM's. Retrieve data from pig at Station 4 (Klagetoh)- travel home. |  |  |  | 0 | P | N | N
10 | 17339 | ALB | STATION 5 | 501 502 503 STATION | OPTO CONTROLS | 2001-09-12 08:00 | 2001-09-14 08:00 | 2 |  | OPS |  | 0 | 0 | Install new OPTO 22 controls and download new programs on units 501 502 503 & station. Install new seal oil level controls on unit 503. Change #4 L/B head and take web deflections on unit 503. Work on recycle lines orifice. 4000 HP |  |  |  | 0 | P | N | N
11 | 17305 | ALB | STATION 7 |  | CALIPER PIG RUN | 2001-08-23 08:00 | 2001-08-24 16:00 | 1.3 |  | OPS |  | 0 | 0 | Run tool from Sta. 7 to Sta. 6 (Section 7 mainline) pick up AGM's. Retrieve data and set pig up for next run at Gallup at Station 6 (Laguna)- travel home. |  |  |  | 0 | P | N | N
12 | 17304 | ALB | STATION 8 |  | CALIPER PIG RUN | 2001-08-21 08:00 | 2001-08-22 16:00 | 1.3 |  | OPS |  | 0 | 0 | Run tool from Sta. 8 to Sta. 7 (Section 8 mainline) pick up AGM's. Retrieve data and set pig up for next run at Station 7 (Mountainair) set out AGM's. |  |  |  | 0 | P | N | N
13 | 16900 | ALB | STATION 8 | MAINLINE | MAINLINE BLOCK | 2001-08-28 08:00 | 2001-08-31 16:00 | 3.3 |  | OPS |  | 0 | 0 | Remove 1 section of mainline from service for 4 days. Block pipeline for 2 hours to use station compression to lower section pressure by transferring gas from mainline west of station to mainline east of station then reestablish bypass conditions. |  |  |  | 0 | P | N | N
14 | 16752 | ALB | STATION 8 | 802 | AUTOMATION | 2001-09-04 08:00 | 2001-10-31 16:00 | 57.3 |  | OPS |  | 0 | 0 | Station 8 automation project. 8000 HP |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2001 Through December, 2001
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted August 23, 2001 | [10 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[11 empty] | (Mmcfd) | (Mmcf)
1 | 17370 | GALLUP | 1 | STATOR DAMAGE | 2001-08-19 08:00 | 2001-09-07 16:00 | 19.3 |  | OPS |  | 80 | 1546.7 | Part of the Stator is damaged and they are not sure if it can be repaired in place at this time. |  | 2001-08-19 14:30 |  | 0 | U | N | N
2 | 17216 | KINGMAN | PG&E STN | PG&E MEAS STN | 2001-09-19 07:00 | 2001-09-20 07:00 | 1 |  | OPS |  | 0 | 0 | Change out filters and econ filter case at PG&E/TW Measurement Station. (The flow at PG&E and South Socal will be taken to zero). |  |  |  | 0 | P | N | N
3 | 16195 | STATION 1 | 101 | SAFETY DEVICES TURBO & PISTON LINERS | 2001-09-17 08:00 | 2001-09-19 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | Safety devices. Change out Turbo water pump and change piston liners and maybe some heads. Group valve as "Compressor Health Report". |  |  |  | 0 | P | N | N
4 | 16194 | STATION 1 | 102 | SAFETY DEVICES & MAINTENANCE | 2001-09-19 08:00 | 2001-09-20 16:00 | 1.3 |  | OPS |  | 50 | 66.7 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
5 | 17355 | STATION 1 | 103 | MAINTENANCE | 2001-09-20 07:00 | 2001-09-21 16:00 | 1.4 |  | OPS |  | 50 | 68.8 | Maintenance. |  |  |  | 0 | U | N | N
6 | 17090 | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-10-22 08:00 | 2001-10-26 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
7 | 17091 | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-05 08:00 | 2001-11-07 16:00 | 2.3 |  | OPS |  | 130 | 303.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
8 | 17306 | STATION 5 |  | CALIPER PIG RUN | 2001-08-28 08:00 | 2001-08-29 16:00 | 1.3 |  | OPS |  | 0 | 0 | Run tool in Loop line Sta. 5 (Thoreau) to Sta. 4 (Section 5) pick up AGM's. Retrieve data and set pig up for next run at Station 4 (Klagetoh)) Haul pig to Sta. 5 - set out AGM's. |  |  |  | 0 | P | N | N
9 | 17307 | STATION 5 |  | CALIPER PIG RUN | 2001-08-30 08:00 | 2001-08-31 16:00 | 1.3 |  | OPS |  | 0 | 0 | Run tool in mainline from Sta. 5 to Sta. 4 (Section 5) pick up AGM's. Retrieve data from pig at Station 4 (Klagetoh)- travel home. |  |  |  | 0 | P | N | N
10 | 17339 | STATION 5 | 501 502 503 STATION | OPTO CONTROLS | 2001-09-12 08:00 | 2001-09-14 08:00 | 2 |  | OPS |  | 0 | 0 | Install new OPTO 22 controls and download new programs on units 501 502 503 & station. Install new seal oil level controls on unit 503. Change #4 L/B head and take web deflections on unit 503. Work on recycle lines orifice. 4000 HP |  |  |  | 0 | P | N | N
11 | 17305 | STATION 7 |  | CALIPER PIG RUN | 2001-08-23 08:00 | 2001-08-24 16:00 | 1.3 |  | OPS |  | 0 | 0 | Run tool from Sta. 7 to Sta. 6 (Section 7 mainline) pick up AGM's. Retrieve data and set pig up for next run at Gallup at Station 6 (Laguna)- travel home. |  |  |  | 0 | P | N | N
12 | 17304 | STATION 8 |  | CALIPER PIG RUN | 2001-08-21 08:00 | 2001-08-22 16:00 | 1.3 |  | OPS |  | 0 | 0 | Run tool from Sta. 8 to Sta. 7 (Section 8 mainline) pick up AGM's. Retrieve data and set pig up for next run at Station 7 (Mountainair) set out AGM's. |  |  |  | 0 | P | N | N
13 | 16900 | STATION 8 | MAINLINE | MAINLINE BLOCK | 2001-08-28 08:00 | 2001-08-31 16:00 | 3.3 |  | OPS |  | 0 | 0 | Remove 1 section of mainline from service for 4 days. Block pipeline for 2 hours to use station compression to lower section pressure by transferring gas from mainline west of station to mainline east of station then reestablish bypass conditions. |  |  |  | 0 | P | N | N
14 | 16752 | STATION 8 | 802 | AUTOMATION | 2001-09-04 08:00 | 2001-10-31 16:00 | 57.3 |  | OPS |  | 0 | 0 | Station 8 automation project. 8000 HP |  |  |  | 0 | P | N | N