## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 10, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17144 | ALB | ATOKA 1 | 719 | HEAD EXCHANGE | 2002-03-05 08:00 | 2002-03-07 16:00 | 2.3 |  | OPS |  | 0 | 0 | Complete UX head exchange. Contractor will remove all power heads. Inspect combustion chambers clean and reinstall new heads. (Flow affect is zero but suction comes up some). |  |  |  | 0 | P | N | N
2 | 17142 | ALB | ATOKA 1 | 719 | OVERHAUL | 2002-03-12 08:00 | 2002-03-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul replace rings packing R&R all valves inspect cylinders for wear and check rod and main bearings. (Flow affect is zero but suction comes up some). |  |  |  | 0 | P | N | N
3 | 17145 | ALB | ATOKA 1 | 737 | OVERHAUL | 2002-03-18 08:00 | 2002-03-22 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. (Flow affect is zero but suction comes up some). |  |  |  | 0 | P | N | N
4 | 17146 | ALB | ATOKA 1 | 761 | OVERHAUL | 2002-03-25 08:00 | 2002-03-29 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. |  |  |  | 0 | P | N | N
5 | 18242 | ALB | ATOKA 3 | 761 | REALIGN EXHAUST HEADER | 2002-01-08 07:00 | 2002-01-10 08:00 | 2 |  | OPS |  | 3 | 6.1 | Cooper pulling all heads gaskets and realign exhaust header & intake. Changing #6 head with new one. |  | 2002-01-08 07:00 |  | 0 | U | N | N
6 | 17148 | ALB | CRAWFORD | 751 | OVERHAUL | 2002-03-11 08:00 | 2002-03-13 16:00 | 2.3 |  | OPS |  | 30 | 70 | Complete UX turbine exchange. Contractor will remove old turbine and install and align new reconditioned turbine. (The flow affect 30 mmcf from capacity). Capacity is around 60 mmcf. |  |  |  | 0 | P | N | N
7 | 18243 | ALB | CRAWFORD | CONTROL VALVE | INSTALL CONTROL VALVE | 2002-03-12 08:00 | 2002-03-12 16:00 | 0.3 |  | OPS |  | 60 | 20 | Installing two elbows in the 16" line in order to put in the flow control valve for existing Duke I/C inside the Crawford compressor station. (The station would need to be down for this work). |  |  |  | 0 | P | N | N
8 | 17092 | ALB | STATION 1 | MAINLINE | RED ROCK TIE-IN | 2002-03-04 08:00 | 2002-03-08 16:00 | 4.3 |  | OPS |  | 50 | 216.7 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. | on 4 overhaul Outage). |  |  | 0 | P | N | N
9 | 17093 | ALB | STATION 1 | LOOP LINE | RED ROCK TIE-IN | 2002-03-11 08:00 | 2002-03-13 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. | on 4 overhaul Outage). |  |  | 0 | P | N | N
10 | 17195 | ALB | STATION 1 | 101 | SAFETY DEVICES | 2002-07-03 08:00 | 2002-07-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
11 | 17196 | ALB | STATION 1 | 102 | SAFETY DEVICES | 2002-07-10 08:00 | 2002-07-14 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
12 | 17197 | ALB | STATION 1 | 103 | SAFETY DEVICES | 2002-07-17 08:00 | 2002-07-21 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
13 | 17198 | ALB | STATION 2 | 201 | SAFETY DEVICES | 2002-07-03 08:00 | 2002-07-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
14 | 17199 | ALB | STATION 2 | 202 | SAFETY DEVICES | 2002-07-10 08:00 | 2002-07-14 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
15 | 17200 | ALB | STATION 2 | 203 | SAFETY DEVICES | 2002-07-17 08:00 | 2002-07-21 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
16 | 18268 | ALB | STATION 3 | 303 | REPAIR & REPLACE LINER | 2002-01-10 07:00 | 2002-01-10 16:00 | 0.4 |  | OPS |  | 0 | 0 | Repair and replace liner & head assembly #2 right. |  |  |  | 0 | P | N | N
17 | 17095 | ALB | STATION 3 | MAINLINE | RED ROCK TIE-IN | 2002-03-18 08:00 | 2002-03-22 16:00 | 4.3 |  | OPS |  | 180 | 780 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
18 | 17096 | ALB | STATION 3 | LOOP LINE | RED ROCK TIE-IN | 2002-03-25 08:00 | 2002-03-27 16:00 | 2.3 |  | OPS |  | 180 | 420 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. | on 4 overhaul Outage). |  |  | 0 | P | N | N
19 | 17201 | ALB | STATION 3 | 301 | SAFETY DEVICES | 2002-07-03 08:00 | 2002-07-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
20 | 17202 | ALB | STATION 3 | 302 | SAFETY DEVICES | 2002-07-10 08:00 | 2002-07-14 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
21 | 17203 | ALB | STATION 3 | 303 | SAFETY DEVICES | 2002-07-17 08:00 | 2002-07-21 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
22 | 17128 | ALB | STATION 4 | 401 | OVERHAUL | 2002-04-01 08:00 | 2002-04-15 16:00 | 14.3 |  | OPS |  | 200 | 2866.7 | Contractor will disassemble unit all the way to the lower block. Compressor will be overhauled with new rods packing ring and all new compressor valves unit realigned and rechocked. |  |  |  | 0 | P | N | N
23 | 17129 | ALB | STATION 4 | 402 | OVERHAUL | 2002-04-17 08:00 | 2002-04-27 16:00 | 10.3 |  | OPS |  | 200 | 2066.7 | Contractor will provide complete compressor overhaul with new rods packing ring and all new compressor valves. Turbo after coolers will be removed and cleaned. |  |  |  | 0 | P | N | N
24 | 17130 | ALB | STATION 4 | 403 | OVERHAUL | 2002-04-29 08:00 | 2002-05-10 16:00 | 10.3 |  | OPS |  | 200 | 2066.7 | Contractor will provide complete compressor overhaul with new rods packing ring and all new compressor valves. Turbo after coolers will be removed and cleaned. |  |  |  | 0 | P | N | N
25 | 17132 | ALB | STATION 5 | 502 | OVERHAUL | 2002-05-01 08:00 | 2002-05-07 16:00 | 6.3 |  | OPS |  | 0 | 0 | Contractor will remove the old exhaust manifold system and replace with new exhaust manifold system. Also replace turbocharger and turbo coolers with the spare turbo and coolers at the station. |  |  |  | 0 | P | N | N
26 | 17131 | ALB | STATION 5 | 501 PHFU | OVERHAUL | 2002-05-10 08:00 | 2002-05-24 16:00 | 14.3 |  | OPS |  | 0 | 0 | Contractor will remove and replace both left and right bank upper blocks. Block replacement will result in a complete upper end overhaul. |  |  |  | 0 | P | N | N
27 | 17133 | ALB | STATION 6 | 601 | VALVE OVERHAUL | 2002-09-02 08:00 | 2002-09-04 16:00 | 2.3 |  | OPS |  | 0 | 0 | Contractor will remove all compressor valves and install all new reconditioned valves. Compressor valves will be sent to VMS for R&R. Upon return valve will be i nstalled in the next unit. |  |  |  | 0 | P | N | N
28 | 17134 | ALB | STATION 6 | 602 PHFU | VALVE OVERHAUL | 2002-09-05 08:00 | 2002-09-08 16:00 | 3.3 |  | OPS |  | 0 | 0 | Contractor will remove all compressor valves and install all new reconditioned valves. Compressor valves will be sent to VMS for R&R. Upon return valve will be i nstalled in the next unit. |  |  |  | 0 | P | N | N
29 | 17135 | ALB | STATION 6 | 603 | VALVE OVERHAUL | 2002-09-09 08:00 | 2002-09-11 16:00 | 2.3 |  | OPS |  | 0 | 0 | Contractor will remove all compressor valves and install all new reconditioned valves. Compressor valves will be sent to VMS for R&R. Upon return valve will be i nstalled in the next unit. |  |  |  | 0 | P | N | N
30 | 17138 | ALB | STATION 7 | 721 | OVERHAUL | 2002-03-04 08:00 | 2002-03-31 16:00 | 27.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete upper and lower end overhaul. Ciontractor will remove generator and it will be sent in for complete restoration. |  |  |  | 0 | P | N | N
31 | 17136 | ALB | STATION 7 | 701 PHFU | OVERHAUL | 2002-04-03 08:00 | 2002-04-11 16:00 | 8.3 |  | OPS |  | 0 | 0 | Contractor will remove the old exhaust manifold and replace with new exhaust manifold system. Both intake manifolds will also be replaced. Intake manifolds will be supplied by Enron. Unit main frame bolts will be checked by ultrasound. Bolts will be rep | laced if cracked or broken. |  |  | 0 | P | N | N
32 | 17137 | ALB | STATION 7 | 702 PHFU | OVERHAUL | 2002-04-15 08:00 | 2002-04-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Contractor will remove left and right intake manifolds and send them to Coopers shop in Odessa for repairs. Upon completion contractor will reinstall. |  |  |  | 0 | P | N | N
33 | 17139 | ALB | STATION 8 | 801 | OVERHAUL | 2002-06-01 08:00 | 2002-06-25 16:00 | 24.3 |  | OPS |  | 0 | 0 | Contractor will perform a partial upper end overhaul. Six pistons and liners will be removed and replaced as needed. The accessory drive chain and sprocket will replaced due to wear. Contractor will perform a complete overhaul including pulling #3 doghous | e to replace gasket. All valves will be sent in for reconditioning. |  |  | 0 | P | N | N
34 | 17140 | ALB | STATION 8 | 802 | OVERHAUL | 2002-06-25 08:00 | 2002-07-10 16:00 | 15.3 |  | OPS |  | 0 | 0 | Contractor will perform a partial upper end overhaul. Six pistons and liners will be removed and replaced as needed. Contractor will perform a complete overhaul and valves will be sent in for reconditioning. |  |  |  | 0 | P | N | N
35 | 17721 | ALB | WT-1 | 102 | BEARING REPLACEMENT | 2002-10-02 08:00 | 2002-10-15 16:00 | 13.3 |  | OPS |  | 0 | 0 | Main bearing and seal replacement. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 10, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17144 | ALB | ATOKA 1 | 719 | HEAD EXCHANGE | 2002-03-05 08:00 | 2002-03-07 16:00 | 2.3 |  | OPS |  | 0 | 0 | Complete UX head exchange. Contractor will remove all power heads. Inspect combustion chambers clean and reinstall new heads. (Flow affect is zero but suction comes up some). |  |  |  | 0 | P | N | N
2 | 17142 | ALB | ATOKA 1 | 719 | OVERHAUL | 2002-03-12 08:00 | 2002-03-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul replace rings packing R&R all valves inspect cylinders for wear and check rod and main bearings. (Flow affect is zero but suction comes up some). |  |  |  | 0 | P | N | N
3 | 17145 | ALB | ATOKA 1 | 737 | OVERHAUL | 2002-03-18 08:00 | 2002-03-22 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. (Flow affect is zero but suction comes up some). |  |  |  | 0 | P | N | N
4 | 17146 | ALB | ATOKA 1 | 761 | OVERHAUL | 2002-03-25 08:00 | 2002-03-29 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. |  |  |  | 0 | P | N | N
5 | 18242 | ALB | ATOKA 3 | 761 | REALIGN EXHAUST HEADER | 2002-01-08 07:00 | 2002-01-10 08:00 | 2 |  | OPS |  | 3 | 6.1 | Cooper pulling all heads gaskets and realign exhaust header & intake. Changing #6 head with new one. |  | 2002-01-08 07:00 |  | 0 | U | N | N
6 | 17148 | ALB | CRAWFORD | 751 | OVERHAUL | 2002-03-11 08:00 | 2002-03-13 16:00 | 2.3 |  | OPS |  | 30 | 70 | Complete UX turbine exchange. Contractor will remove old turbine and install and align new reconditioned turbine. (The flow affect 30 mmcf from capacity). Capacity is around 60 mmcf. |  |  |  | 0 | P | N | N
7 | 18243 | ALB | CRAWFORD | CONTROL VALVE | INSTALL CONTROL VALVE | 2002-03-12 08:00 | 2002-03-12 16:00 | 0.3 |  | OPS |  | 60 | 20 | Installing two elbows in the 16" line in order to put in the flow control valve for existing Duke I/C inside the Crawford compressor station. (The station would need to be down for this work). |  |  |  | 0 | P | N | N
8 | 17092 | ALB | STATION 1 | MAINLINE | RED ROCK TIE-IN | 2002-03-04 08:00 | 2002-03-08 16:00 | 4.3 |  | OPS |  | 50 | 216.7 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. | on 4 overhaul Outage). |  |  | 0 | P | N | N
9 | 17093 | ALB | STATION 1 | LOOP LINE | RED ROCK TIE-IN | 2002-03-11 08:00 | 2002-03-13 16:00 | 2.3 |  | OPS |  | 50 | 116.7 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. | on 4 overhaul Outage). |  |  | 0 | P | N | N
10 | 17195 | ALB | STATION 1 | 101 | SAFETY DEVICES | 2002-07-03 08:00 | 2002-07-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
11 | 17196 | ALB | STATION 1 | 102 | SAFETY DEVICES | 2002-07-10 08:00 | 2002-07-14 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
12 | 17197 | ALB | STATION 1 | 103 | SAFETY DEVICES | 2002-07-17 08:00 | 2002-07-21 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
13 | 17198 | ALB | STATION 2 | 201 | SAFETY DEVICES | 2002-07-03 08:00 | 2002-07-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
14 | 17199 | ALB | STATION 2 | 202 | SAFETY DEVICES | 2002-07-10 08:00 | 2002-07-14 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
15 | 17200 | ALB | STATION 2 | 203 | SAFETY DEVICES | 2002-07-17 08:00 | 2002-07-21 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
16 | 18268 | ALB | STATION 3 | 303 | REPAIR & REPLACE LINER | 2002-01-10 07:00 | 2002-01-10 16:00 | 0.4 |  | OPS |  | 0 | 0 | Repair and replace liner & head assembly #2 right. |  |  |  | 0 | P | N | N
17 | 17095 | ALB | STATION 3 | MAINLINE | RED ROCK TIE-IN | 2002-03-18 08:00 | 2002-03-22 16:00 | 4.3 |  | OPS |  | 180 | 780 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
18 | 17096 | ALB | STATION 3 | LOOP LINE | RED ROCK TIE-IN | 2002-03-25 08:00 | 2002-03-27 16:00 | 2.3 |  | OPS |  | 180 | 420 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. | on 4 overhaul Outage). |  |  | 0 | P | N | N
19 | 17201 | ALB | STATION 3 | 301 | SAFETY DEVICES | 2002-07-03 08:00 | 2002-07-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
20 | 17202 | ALB | STATION 3 | 302 | SAFETY DEVICES | 2002-07-10 08:00 | 2002-07-14 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
21 | 17203 | ALB | STATION 3 | 303 | SAFETY DEVICES | 2002-07-17 08:00 | 2002-07-21 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
22 | 17128 | ALB | STATION 4 | 401 | OVERHAUL | 2002-04-01 08:00 | 2002-04-15 16:00 | 14.3 |  | OPS |  | 200 | 2866.7 | Contractor will disassemble unit all the way to the lower block. Compressor will be overhauled with new rods packing ring and all new compressor valves unit realigned and rechocked. |  |  |  | 0 | P | N | N
23 | 17129 | ALB | STATION 4 | 402 | OVERHAUL | 2002-04-17 08:00 | 2002-04-27 16:00 | 10.3 |  | OPS |  | 200 | 2066.7 | Contractor will provide complete compressor overhaul with new rods packing ring and all new compressor valves. Turbo after coolers will be removed and cleaned. |  |  |  | 0 | P | N | N
24 | 17130 | ALB | STATION 4 | 403 | OVERHAUL | 2002-04-29 08:00 | 2002-05-10 16:00 | 10.3 |  | OPS |  | 200 | 2066.7 | Contractor will provide complete compressor overhaul with new rods packing ring and all new compressor valves. Turbo after coolers will be removed and cleaned. |  |  |  | 0 | P | N | N
25 | 17132 | ALB | STATION 5 | 502 | OVERHAUL | 2002-05-01 08:00 | 2002-05-07 16:00 | 6.3 |  | OPS |  | 0 | 0 | Contractor will remove the old exhaust manifold system and replace with new exhaust manifold system. Also replace turbocharger and turbo coolers with the spare turbo and coolers at the station. |  |  |  | 0 | P | N | N
26 | 17131 | ALB | STATION 5 | 501 PHFU | OVERHAUL | 2002-05-10 08:00 | 2002-05-24 16:00 | 14.3 |  | OPS |  | 0 | 0 | Contractor will remove and replace both left and right bank upper blocks. Block replacement will result in a complete upper end overhaul. |  |  |  | 0 | P | N | N
27 | 17133 | ALB | STATION 6 | 601 | VALVE OVERHAUL | 2002-09-02 08:00 | 2002-09-04 16:00 | 2.3 |  | OPS |  | 0 | 0 | Contractor will remove all compressor valves and install all new reconditioned valves. Compressor valves will be sent to VMS for R&R. Upon return valve will be i nstalled in the next unit. |  |  |  | 0 | P | N | N
28 | 17134 | ALB | STATION 6 | 602 PHFU | VALVE OVERHAUL | 2002-09-05 08:00 | 2002-09-08 16:00 | 3.3 |  | OPS |  | 0 | 0 | Contractor will remove all compressor valves and install all new reconditioned valves. Compressor valves will be sent to VMS for R&R. Upon return valve will be i nstalled in the next unit. |  |  |  | 0 | P | N | N
29 | 17135 | ALB | STATION 6 | 603 | VALVE OVERHAUL | 2002-09-09 08:00 | 2002-09-11 16:00 | 2.3 |  | OPS |  | 0 | 0 | Contractor will remove all compressor valves and install all new reconditioned valves. Compressor valves will be sent to VMS for R&R. Upon return valve will be i nstalled in the next unit. |  |  |  | 0 | P | N | N
30 | 17138 | ALB | STATION 7 | 721 | OVERHAUL | 2002-03-04 08:00 | 2002-03-31 16:00 | 27.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete upper and lower end overhaul. Ciontractor will remove generator and it will be sent in for complete restoration. |  |  |  | 0 | P | N | N
31 | 17136 | ALB | STATION 7 | 701 PHFU | OVERHAUL | 2002-04-03 08:00 | 2002-04-11 16:00 | 8.3 |  | OPS |  | 0 | 0 | Contractor will remove the old exhaust manifold and replace with new exhaust manifold system. Both intake manifolds will also be replaced. Intake manifolds will be supplied by Enron. Unit main frame bolts will be checked by ultrasound. Bolts will be rep | laced if cracked or broken. |  |  | 0 | P | N | N
32 | 17137 | ALB | STATION 7 | 702 PHFU | OVERHAUL | 2002-04-15 08:00 | 2002-04-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Contractor will remove left and right intake manifolds and send them to Coopers shop in Odessa for repairs. Upon completion contractor will reinstall. |  |  |  | 0 | P | N | N
33 | 17139 | ALB | STATION 8 | 801 | OVERHAUL | 2002-06-01 08:00 | 2002-06-25 16:00 | 24.3 |  | OPS |  | 0 | 0 | Contractor will perform a partial upper end overhaul. Six pistons and liners will be removed and replaced as needed. The accessory drive chain and sprocket will replaced due to wear. Contractor will perform a complete overhaul including pulling #3 doghous | e to replace gasket. All valves will be sent in for reconditioning. |  |  | 0 | P | N | N
34 | 17140 | ALB | STATION 8 | 802 | OVERHAUL | 2002-06-25 08:00 | 2002-07-10 16:00 | 15.3 |  | OPS |  | 0 | 0 | Contractor will perform a partial upper end overhaul. Six pistons and liners will be removed and replaced as needed. Contractor will perform a complete overhaul and valves will be sent in for reconditioning. |  |  |  | 0 | P | N | N
35 | 17721 | ALB | WT-1 | 102 | BEARING REPLACEMENT | 2002-10-02 08:00 | 2002-10-15 16:00 | 13.3 |  | OPS |  | 0 | 0 | Main bearing and seal replacement. |  |  |  | 0 | P | N | N