## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Dakota Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 10, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17159 | DAK | FT BUFORD | 3 | OVERHAUL | 2002-04-01 08:00 | 2002-04-26 16:00 | 25.3 |  | OPS |  | 0 | 0 | Superior 8GTLA engine exchange based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
2 | 17160 | DAK | FT BUFORD | 4 | OVERHAUL | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Superior 8GTLA engine exchange based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Dakota Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 10, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17159 | DAK | FT BUFORD | 3 | OVERHAUL | 2002-04-01 08:00 | 2002-04-26 16:00 | 25.3 |  | OPS |  | 0 | 0 | Superior 8GTLA engine exchange based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
2 | 17160 | DAK | FT BUFORD | 4 | OVERHAUL | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Superior 8GTLA engine exchange based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N