## Hatch 02
Owner Name | Georgia Power Company
Station Name | Edwin I Hatch Nuclear Power Station
Unit Name | Hatch 02
NERC Region | SERC
State | GA
Fuel Type | Nuclear
Capacity | 865 MW
Start Date | 2001-12-25
End Date | 2002-01-10
Prv. Start Date | 2001-12-25
Prv. End Date | 2002-01-11
Comments | Unit is back online ramping up to full power. Should take until late Friday to reach 100%
SIC | 4911
Plant ID | 1012040
Unit ID | 1004272
Outage ID | 19297

## Intermountain 01
Owner Name | Intermountain Power Service Corporation
Station Name | Intermountain Power Station
Unit Name | Intermountain 01
NERC Region | WSCC
State | UT
Fuel Type | Coal
Capacity | 820 MW
Start Date | 2002-01-10
End Date | 2002-02-06
Prv. Start Date | 2002-01-11
Prv. End Date | 2002-02-07
Comments | Scrubber Work
SIC | 4911
Plant ID | 1015331
Unit ID | 1007133
Outage ID | 18624

## Colbert 05
Owner Name | TVA
Station Name | Colbert Power Station
Unit Name | Colbert 05
NERC Region | SERC
State | AL
Fuel Type | Coal
Capacity | 550 MW
Start Date | 2002-01-09
End Date | 2002-03-09
Prv. Start Date | 2002-01-17
Prv. End Date | 2002-02-27
Comments | The outage started early due to an electrical fire, so they went ahead and kept the unit down.
SIC | 4911
Plant ID | 1018346
Unit ID | 1003699
Outage ID | 19191

## Colstrip 03
Owner Name | PPL Montana LLC
Station Name | Colstrip Power Station
Unit Name | Colstrip 03
NERC Region | WSCC
State | MT
Fuel Type | Coal
Capacity | 778 MW
Start Date | 2002-01-05
End Date | 2002-01-12
Prv. Start Date | 2002-01-05
Prv. End Date | 2002-01-10
Comments | Generator problem
SIC | 4931
Plant ID | 1015370
Unit ID | 1007494
Outage ID | 19382

## Colstrip 04
Owner Name | PPL Montana LLC
Station Name | Colstrip Power Station
Unit Name | Colstrip 04
NERC Region | WSCC
State | MT
Fuel Type | Coal
Capacity | 778 MW
Start Date | 2002-01-08
End Date | 2002-01-15
Prv. Start Date | 2002-01-08
Prv. End Date | 2002-01-10
Comments | Tube repairs
SIC | 4931
Plant ID | 1015370
Unit ID | 1007495
Outage ID | 19414