## Colbert 05
Owner Name | TVA
Station Name | Colbert Power Station
Unit Name | Colbert 05
NERC Region | SERC
State | AL
Fuel Type | Coal
Capacity | 550 MW
Start Date | 2002-01-09
End Date | 2002-03-09
Prv. Start Date | 2002-01-17
Prv. End Date | 2002-02-27
Comments | The outage started early due to an electrical fire, so they went ahead and kept the unit down.
SIC | 4911
Plant ID | 1018346
Unit ID | 1003699
Outage ID | 19191

## Colstrip 03
Owner Name | PPL Montana LLC
Station Name | Colstrip Power Station
Unit Name | Colstrip 03
NERC Region | WSCC
State | MT
Fuel Type | Coal
Capacity | 778 MW
Start Date | 2002-01-05
End Date | 2002-01-12
Prv. Start Date | 2002-01-05
Prv. End Date | 2002-01-10
Comments | Generator problem
SIC | 4931
Plant ID | 1015370
Unit ID | 1007494
Outage ID | 19382

## Colstrip 04
Owner Name | PPL Montana LLC
Station Name | Colstrip Power Station
Unit Name | Colstrip 04
NERC Region | WSCC
State | MT
Fuel Type | Coal
Capacity | 778 MW
Start Date | 2002-01-08
End Date | 2002-01-15
Prv. Start Date | 2002-01-08
Prv. End Date | 2002-01-10
Comments | Tube repairs
SIC | 4931
Plant ID | 1015370
Unit ID | 1007495
Outage ID | 19414