## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 9, 2001 | [11 empty] | Max | Projected | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Flow | Flow | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[12 empty] | (Mmcfd) | (Mmcfd) | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 17663 | AMA | BEAVER 13 | 1 | REPLACE STUDS | 2001-10-03 13:00 | 2001-10-12 16:00 | 9.1 |  | OPS |  | 0 | 0 | 5 | 45.6 | Replace compressor cylinder studs. |  | 2001-10-03 13:00 |  | 0 |  | U | N | N
2 | 17225 | AMA | BEAVER 2 | ALL | RECOAT | 2001-08-27 06:00 | 2001-10-12 16:00 | 46.4 |  | OPS |  | 0 | 0 | 0 | 0 | Recoat station discharge line. Need the B&A lines at 80% MAOP. (The A line would be 372# and B line about 565#). |  | 2001-08-27 06:00 |  | 0 |  | P | N | N
3 | 17588 | AMA | BEAVER 2 | 3 | PISTON & HEAD | 2001-09-22 09:00 | 2001-10-12 16:00 | 20.3 |  | OPS |  | 0 | 0 | 0 | 0 | Change 2 pistons and 1 head. (Waiting on Rod) |  | 2001-09-22 09:00 |  | 0 |  | U | N | N
4 | 15734 | AMA | CLAUDE | 1 | SAFETY CHECK | 2001-10-16 08:00 | 2001-10-17 16:00 | 1.3 | K-B LINE | OPS |  | 0 | 0 | 0 | 0 | Safety devices check. 9100 HP |  |  |  | 0 |  | P | N | N
5 | 17447 | AMA | ELLIS 1 | 1 | 1500 HR INSP | 2001-10-11 09:00 | 2001-10-11 12:00 | 0.1 |  | OPS |  | 0 | 0 | 2 | 0.3 | 1500 Hr Inspection. Install new throttle linkage. 506 HP |  |  |  | 0 |  | P | N | N
6 | 17449 | AMA | ELLIS 1 | 3 | 1500 HR INSP | 2001-10-15 08:00 | 2001-10-20 16:00 | 5.3 |  | OPS |  | 0 | 0 | 2 | 10.7 | Install new Opto control Panel 1500 Hr. Inspection |  |  |  | 0 |  | P | N | N
7 | 17450 | AMA | ELLIS 1 | 4 | 1500 HR INSP | 2001-10-30 09:00 | 2001-10-30 11:00 | 0.1 |  | OPS |  | 0 | 0 | 5 | 0.4 | 1500 Hr. Inspection. 1035 HP |  |  |  | 0 |  | P | N | N
8 | 17685 | AMA | IVANHOE | DEHY | REPAIR LEAK | 2001-10-08 08:00 | 2001-10-08 16:00 | 0.3 |  | OPS |  | 0 | 0 | 26 | 8.7 | Take dehy down to repair leak on 1" drip line leak. |  |  |  | 0 |  | P | N | N
9 | 15790 | AMA | P 3 | 5 | SAFETY CHECK | 2001-10-10 08:00 | 2001-10-12 16:00 | 2.3 |  | OPS |  | 0 | 0 | 0 | 0 | Annual safety devices check. 1000 HP |  |  |  | 0 |  | P | N | N
10 | 17016 | AMA | ROGER MILLS | 5 | MECHNICAL FAILURE | 2001-06-19 16:00 | 2001-11-30 16:00 | 164 |  | OPS |  | 0 | 0 | 0 | 0 | They had a mechnical failure on unit #5. Not sure of the exact completion. |  | 2001-06-19 16:00 |  | 0 |  | U | N | N
11 | 15944 | AMA | SPEARMAN | 2 | OVERHAUL | 2001-10-29 08:00 | 2001-11-16 12:00 | 18.2 | TM103-02 | OPS |  | 0 | 0 | 0 | 0 | Minor overhaul. The date may change depending on #3 CB control project. 2250 HP (Will not start on this outage until unit 3 is back to normal operation). Start date moved back to coordinate with customer outages per their request. |  |  |  | 0 |  | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 9, 2001 | [10 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[11 empty] | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 17663 | BEAVER 13 | 1 | REPLACE STUDS | 2001-10-03 13:00 | 2001-10-12 16:00 | 9.1 |  | OPS |  | 5 | 45.6 | Replace compressor cylinder studs. |  | 2001-10-03 13:00 |  | 0 |  | U | N | N
2 | 17225 | BEAVER 2 | ALL | RECOAT | 2001-08-27 06:00 | 2001-10-12 16:00 | 46.4 |  | OPS |  | 0 | 0 | Recoat station discharge line. Need the B&A lines at 80% MAOP. (The A line would be 372# and B line about 565#). |  | 2001-08-27 06:00 |  | 0 |  | P | N | N
3 | 17588 | BEAVER 2 | 3 | PISTON & HEAD | 2001-09-22 09:00 | 2001-10-12 16:00 | 20.3 |  | OPS |  | 0 | 0 | Change 2 pistons and 1 head. (Waiting on Rod) |  | 2001-09-22 09:00 |  | 0 |  | U | N | N
4 | 15734 | CLAUDE | 1 | SAFETY CHECK | 2001-10-16 08:00 | 2001-10-17 16:00 | 1.3 | K-B LINE | OPS |  | 0 | 0 | Safety devices check. 9100 HP |  |  |  | 0 |  | P | N | N
5 | 17447 | ELLIS 1 | 1 | 1500 HR INSP | 2001-10-11 09:00 | 2001-10-11 12:00 | 0.1 |  | OPS |  | 2 | 0.3 | 1500 Hr Inspection. Install new throttle linkage. 506 HP |  |  |  | 0 |  | P | N | N
6 | 17449 | ELLIS 1 | 3 | 1500 HR INSP | 2001-10-15 08:00 | 2001-10-20 16:00 | 5.3 |  | OPS |  | 2 | 10.7 | Install new Opto control Panel 1500 Hr. Inspection |  |  |  | 0 |  | P | N | N
7 | 17450 | ELLIS 1 | 4 | 1500 HR INSP | 2001-10-30 09:00 | 2001-10-30 11:00 | 0.1 |  | OPS |  | 5 | 0.4 | 1500 Hr. Inspection. 1035 HP |  |  |  | 0 |  | P | N | N
8 | 17685 | IVANHOE | DEHY | REPAIR LEAK | 2001-10-08 08:00 | 2001-10-08 16:00 | 0.3 |  | OPS |  | 26 | 8.7 | Take dehy down to repair leak on 1" drip line leak. |  |  |  | 0 |  | P | N | N
9 | 15790 | P 3 | 5 | SAFETY CHECK | 2001-10-10 08:00 | 2001-10-12 16:00 | 2.3 |  | OPS |  | 0 | 0 | Annual safety devices check. 1000 HP |  |  |  | 0 |  | P | N | N
10 | 17016 | ROGER MILLS | 5 | MECHNICAL FAILURE | 2001-06-19 16:00 | 2001-11-30 16:00 | 164 |  | OPS |  | 0 | 0 | They had a mechnical failure on unit #5. Not sure of the exact completion. |  | 2001-06-19 16:00 |  | 0 |  | U | N | N
11 | 15944 | SPEARMAN | 2 | OVERHAUL | 2001-10-29 08:00 | 2001-11-16 12:00 | 18.2 | TM103-02 | OPS |  | 0 | 0 | Minor overhaul. The date may change depending on #3 CB control project. 2250 HP (Will not start on this outage until unit 3 is back to normal operation). Start date moved back to coordinate with customer outages per their request. |  |  |  | 0 |  | P | N | N