## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 16, 2001 | [11 empty] | Max | Projected | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Flow | Flow | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[12 empty] | (Mmcfd) | (Mmcfd) | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 17588 | AMA | BEAVER 2 | 3 | PISTON & HEAD | 2001-09-22 09:00 | 2001-10-19 16:00 | 27.3 |  | OPS |  | 0 | 0 | 0 | 0 | Change 2 pistons and 1 head. (Waiting on Rod) |  | 2001-09-22 09:00 |  | 0 |  | U | N | N
2 | 15734 | AMA | CLAUDE | 1 | SAFETY CHECK | 2001-10-16 08:00 | 2001-10-17 16:00 | 1.3 | K-B LINE | OPS |  | 0 | 0 | 0 | 0 | Safety devices check. 9100 HP |  |  |  | 0 |  | P | N | N
3 | 17449 | AMA | ELLIS 1 | 3 | 1500 HR INSP | 2001-10-12 13:00 | 2001-10-20 16:00 | 8.1 |  | OPS |  | 0 | 0 | 2 | 16.3 | Install new Opto control Panel 1500 Hr. Inspection. Update 10/12 - taking unit down to get a jump on Monday's panel board installation. Will adjust other units to accommodate volume. |  |  |  | 0 |  | P | N | N
4 | 17450 | AMA | ELLIS 1 | 4 | 1500 HR INSP | 2001-10-30 09:00 | 2001-10-30 11:00 | 0.1 |  | OPS |  | 0 | 0 | 5 | 0.4 | 1500 Hr. Inspection. 1035 HP |  |  |  | 0 |  | P | N | N
5 | 17723 | AMA | PAMPA | A LINE | A LINE LEAKS | 2001-11-05 08:00 | 2001-11-09 16:00 | 4.3 | TXG89001 | OPS |  | 0 | 0 | 0 | 0 | Repair three leaks on A line. This will necessitate shutting in OneOK's Galgray plant (2.2 m 2/d) as well as Skellytown TBS (50 mcf/d) and Crawford Plant Fuel which is used only as an emergency back up. |  |  |  | 0 |  | P | N | N
6 | 17016 | AMA | ROGER MILLS | 5 | MECHNICAL FAILURE | 2001-06-19 16:00 | 2001-11-30 16:00 | 164 |  | OPS |  | 0 | 0 | 0 | 0 | They had a mechnical failure on unit #5. Not sure of the exact completion. |  | 2001-06-19 16:00 |  | 0 |  | U | N | N
7 | 15944 | AMA | SPEARMAN | 2 | OVERHAUL | 2001-10-29 08:00 | 2001-11-16 12:00 | 18.2 | TM103-02 | OPS |  | 0 | 0 | 0 | 0 | Minor overhaul. The date may change depending on #3 CB control project. 2250 HP (Will not start on this outage until unit 3 is back to normal operation). Start date moved back to coordinate with customer outages per their request. |  |  |  | 0 |  | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 16, 2001 | [10 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[11 empty] | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 17588 | BEAVER 2 | 3 | PISTON & HEAD | 2001-09-22 09:00 | 2001-10-19 16:00 | 27.3 |  | OPS |  | 0 | 0 | Change 2 pistons and 1 head. (Waiting on Rod) |  | 2001-09-22 09:00 |  | 0 |  | U | N | N
2 | 15734 | CLAUDE | 1 | SAFETY CHECK | 2001-10-16 08:00 | 2001-10-17 16:00 | 1.3 | K-B LINE | OPS |  | 0 | 0 | Safety devices check. 9100 HP |  |  |  | 0 |  | P | N | N
3 | 17449 | ELLIS 1 | 3 | 1500 HR INSP | 2001-10-12 13:00 | 2001-10-20 16:00 | 8.1 |  | OPS |  | 2 | 16.3 | Install new Opto control Panel 1500 Hr. Inspection. Update 10/12 - taking unit down to get a jump on Monday's panel board installation. Will adjust other units to accommodate volume. |  |  |  | 0 |  | P | N | N
4 | 17450 | ELLIS 1 | 4 | 1500 HR INSP | 2001-10-30 09:00 | 2001-10-30 11:00 | 0.1 |  | OPS |  | 5 | 0.4 | 1500 Hr. Inspection. 1035 HP |  |  |  | 0 |  | P | N | N
5 | 17723 | PAMPA | A LINE | A LINE LEAKS | 2001-11-05 08:00 | 2001-11-09 16:00 | 4.3 | TXG89001 | OPS |  | 0 | 0 | Repair three leaks on A line. This will necessitate shutting in OneOK's Galgray plant (2.2 m 2/d) as well as Skellytown TBS (50 mcf/d) and Crawford Plant Fuel which is used only as an emergency back up. |  |  |  | 0 |  | P | N | N
6 | 17016 | ROGER MILLS | 5 | MECHNICAL FAILURE | 2001-06-19 16:00 | 2001-11-30 16:00 | 164 |  | OPS |  | 0 | 0 | They had a mechnical failure on unit #5. Not sure of the exact completion. |  | 2001-06-19 16:00 |  | 0 |  | U | N | N
7 | 15944 | SPEARMAN | 2 | OVERHAUL | 2001-10-29 08:00 | 2001-11-16 12:00 | 18.2 | TM103-02 | OPS |  | 0 | 0 | Minor overhaul. The date may change depending on #3 CB control project. 2250 HP (Will not start on this outage until unit 3 is back to normal operation). Start date moved back to coordinate with customer outages per their request. |  |  |  | 0 |  | P | N | N