## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Midland Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 16, 2001 | [11 empty] | Max | Projected | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Flow | Flow | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[12 empty] | (Mmcfd) | (Mmcfd) | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 16026 | MID | ELDORADO | 2 3 | QUATERLY ESD | 2001-12-07 08:00 | 2001-12-07 11:00 | 0.1 | TM20801 | OPS |  | 0 | 0 | 0 | 0 | Quaterly ESD test. 1262 HP |  |  |  | 0 |  | P | N | N
2 | 17680 | MID | KERMIT | 1 | LEAK ON 30" DISCHARGE VALVE | 2001-10-04 08:00 | 2001-10-12 16:00 | 8.3 |  | OPS |  | 0 | 0 | 0 | 0 | Kermit #1 turbine 30" discharge shafer valve flange leaking. They need to dig up valve and replace the gaskets. (This outage will affect deliveries when flows are in the 300 to 400 range). Right now the unit is not required. |  | 2001-10-04 08:00 |  | 0 |  | U | N | N
3 | 17227 | MID | PLAINVIEW | 1 | STARTER | 2001-11-05 08:00 | 2001-11-19 16:00 | 14.3 |  | OPS |  | 0 | 0 | 0 | 0 | Install new starter and controls. 9100 HP |  |  |  | 0 |  | P | N | N
4 | 17226 | MID | SEMINOLE | 1 | STARTER | 2001-11-26 08:00 | 2001-12-03 16:00 | 7.3 |  | OPS |  | 0 | 0 | 0 | 0 | Install new starter and new controls. 9100 HP |  |  |  | 0 |  | P | N | N
5 | 17150 | MID | SEMINOLE | 1 | OVERHAUL | 2002-03-05 08:00 | 2002-04-01 16:00 | 27.3 |  | OPS |  | 0 | 0 | 0 | 0 | Complete disassembly and overhaul of gas producer and power turbine. |  |  |  | 0 |  | P | N | N
6 | 17407 | MID | SPRAYBERRY | 8 | TORQUE ANCHOR BOLTS | 2001-08-26 08:00 | 2001-10-26 16:00 | 61.3 |  | OPS |  | 0 | 0 | 0 | 0 | Torque anchor bolts and inspect x-head shoes and bearing. Also crank deflection. |  | 2001-08-26 08:00 |  | 0 |  | U | N | N
7 | 16142 | MID | WT 2 | 201 | OVERHAUL | 2002-03-05 08:00 | 2002-04-05 16:00 | 31.3 |  | OPS |  | 0 | 0 | 0 | 0 | Overhaul |  |  |  | 0 |  | P | N | N
8 | 17408 | MID | WT-2 | 202 | COMPRESSOR ALIGNMENT | 2001-10-01 08:00 | 2001-10-12 08:00 | 11 |  | OPS |  | 0 | 0 | 0 | 0 | Compressor alignment on unit #2. |  | 2001-10-01 08:00 |  | 0 |  | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Midland Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 16, 2001 | [10 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[11 empty] | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 16026 | ELDORADO | 2 3 | QUATERLY ESD | 2001-12-07 08:00 | 2001-12-07 11:00 | 0.1 | TM20801 | OPS |  | 0 | 0 | Quaterly ESD test. 1262 HP |  |  |  | 0 |  | P | N | N
2 | 17680 | KERMIT | 1 | LEAK ON 30" DISCHARGE VALVE | 2001-10-04 08:00 | 2001-10-12 16:00 | 8.3 |  | OPS |  | 0 | 0 | Kermit #1 turbine 30" discharge shafer valve flange leaking. They need to dig up valve and replace the gaskets. (This outage will affect deliveries when flows are in the 300 to 400 range). Right now the unit is not required. |  | 2001-10-04 08:00 |  | 0 |  | U | N | N
3 | 17227 | PLAINVIEW | 1 | STARTER | 2001-11-05 08:00 | 2001-11-19 16:00 | 14.3 |  | OPS |  | 0 | 0 | Install new starter and controls. 9100 HP |  |  |  | 0 |  | P | N | N
4 | 17226 | SEMINOLE | 1 | STARTER | 2001-11-26 08:00 | 2001-12-03 16:00 | 7.3 |  | OPS |  | 0 | 0 | Install new starter and new controls. 9100 HP |  |  |  | 0 |  | P | N | N
5 | 17150 | SEMINOLE | 1 | OVERHAUL | 2002-03-05 08:00 | 2002-04-01 16:00 | 27.3 |  | OPS |  | 0 | 0 | Complete disassembly and overhaul of gas producer and power turbine. |  |  |  | 0 |  | P | N | N
6 | 17407 | SPRAYBERRY | 8 | TORQUE ANCHOR BOLTS | 2001-08-26 08:00 | 2001-10-26 16:00 | 61.3 |  | OPS |  | 0 | 0 | Torque anchor bolts and inspect x-head shoes and bearing. Also crank deflection. |  | 2001-08-26 08:00 |  | 0 |  | U | N | N
7 | 16142 | WT 2 | 201 | OVERHAUL | 2002-03-05 08:00 | 2002-04-05 16:00 | 31.3 |  | OPS |  | 0 | 0 | Overhaul |  |  |  | 0 |  | P | N | N
8 | 17408 | WT-2 | 202 | COMPRESSOR ALIGNMENT | 2001-10-01 08:00 | 2001-10-12 08:00 | 11 |  | OPS |  | 0 | 0 | Compressor alignment on unit #2. |  | 2001-10-01 08:00 |  | 0 |  | P | N | N