## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Dakota Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 18, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 16073 | DAK | SO SIOUX | WAYNE CREEK | WAYNE BL | 2001-10-08 08:00 | 2001-10-25 16:00 | 17.3 | NEB57001 | 453 | C.014559 | 0 | 0 | Replace and lower approximately 900 feet of the 4" Wayne BL at the Logan Creek crossing. |  |  |  | 0 |  | P | N | N
2 | 16074 | DAK | SO SIOUX | AKRON BL | AKRON BL | 2001-10-29 08:00 | 2001-11-08 16:00 | 10.3 | IAB72901 | 453 | C.014588 | 0 | 0 | Replace and lower approximately 60 ft of the 3" and 600' of the 6" Akron BL at the Big Sioux River Crossing MP 6.99. Affects IAB72901 & SDB94401 |  |  |  | 0 |  | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Dakota Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 18, 2001 | [10 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[11 empty] | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 16073 | SO SIOUX | WAYNE CREEK | WAYNE BL | 2001-10-08 08:00 | 2001-10-25 16:00 | 17.3 | NEB57001 | 453 | C.014559 | 0 | 0 | Replace and lower approximately 900 feet of the 4" Wayne BL at the Logan Creek crossing. |  |  |  | 0 |  | P | N | N
2 | 16074 | SO SIOUX | AKRON BL | AKRON BL | 2001-10-29 08:00 | 2001-11-08 16:00 | 10.3 | IAB72901 | 453 | C.014588 | 0 | 0 | Replace and lower approximately 60 ft of the 3" and 600' of the 6" Akron BL at the Big Sioux River Crossing MP 6.99. Affects IAB72901 & SDB94401 |  |  |  | 0 |  | P | N | N