## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Des Moines Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 18, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 16063 | DES | BELLEVILLE | 1 | ANNUAL PM | 2001-10-15 09:00 | 2001-10-19 16:00 | 4.3 |  | OPS |  | 0 | 0 | Belleville Unit 1 annual PM. 1100 HP (Dates are tentative the PM's will be done whenever the system and the teams are able. |  |  |  | 0 |  | P | N | N
2 | 16064 | DES | BELLEVILLE | 2 | ANNUAL PM | 2001-10-22 09:00 | 2001-10-26 16:00 | 4.3 |  | OPS |  | 0 | 0 | Belleville Unit 2 annual PM. 1100 HP (Dates are tentative the PM's will be done whenever the system and the teams are able). |  |  |  | 0 |  | P | N | N
3 | 16065 | DES | BELLEVILLE | 3 | ANNUAL PM | 2001-10-29 09:00 | 2001-11-02 16:00 | 4.3 |  | OPS |  | 0 | 0 | Belleville Unit 3 Annual PM. 1100 HP (Dates are tentative the PM's will be done whenever the system and the teams are able). |  |  |  | 0 |  | P | N | N
4 | 17521 | DES | BELLEVILLE | 1 2 3 | ESD TEST | 2002-05-07 10:00 | 2002-05-07 12:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 3300 HP |  |  |  | 0 |  | P | N | N
5 | 16066 | DES | GALENA | 1 | ANNUAL PM | 2001-11-05 08:00 | 2001-11-09 16:00 | 4.3 |  | OPS |  | 0 | 0 | Galena Unit 1 Annual PM. 4000 HP |  |  |  | 0 |  | P | N | N
6 | 16067 | DES | GALENA | 2 | ANNUAL PM | 2001-11-12 08:00 | 2001-11-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Galena Unit 2 Annual PM. 4000 HP |  |  |  | 0 |  | P | N | N
7 | 17161 | DES | GALENA | 1 | OVERHAUL | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Solar Centaur Turbine exchange based on analysis and run hours. |  |  |  | 0 |  | P | N | N
8 | 17520 | DES | GALENA | 1 2 | ESD TEST | 2002-05-14 09:00 | 2002-05-14 11:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 8000 HP |  |  |  | 0 |  | P | N | N
9 | 17726 | DES | OGDEN | 14 | LEAK | 2001-10-15 10:00 | 2001-10-17 15:30 | 2.2 |  | OPS |  | 0 | 0 | Inner cooler leak. 2000 HP |  | 2001-10-15 10:00 |  | 0 |  | U | N | N
10 | 17725 | DES | OGDEN | 11 | SPARK PLUG WELLS | 2001-10-18 09:00 | 2001-10-26 15:00 | 4.3 |  | OPS |  | 0 | 0 | Remove mill in place and install new Dry type spark plug wells. 1600 HP |  |  |  | 0 |  | P | N | N
11 | 17724 | DES | OGDEN | 12 | SPARK PLUG WELLS | 2001-10-29 09:00 | 2001-11-02 15:00 | 4.3 |  | OPS |  | 0 | 0 | Remove mill in place and install new Dry type spark plug wells. 1600 HP |  |  |  | 0 |  | P | N | N
12 | 17164 | DES | OGDEN | 15 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 |  | P | N | N
13 | 17229 | DES | OTTAWA | N MANHATTAN | N MANHATTAN CV | 2002-04-17 08:00 | 2002-04-21 16:00 | 4.3 |  | 453 | C.014802 | 0 | 0 | North Manhattan CV replacement. Remove existing control valve and install a new quieter valve. |  |  |  | 0 |  | P | N | N
14 | 17414 | DES | PLATTEVILLE | W SALEM TBS | W SALEM TBS | 2001-10-24 08:00 | 2001-10-24 16:00 | 0.3 | WIB12201 | 453 | C.014888 | 0 | 0 | Replace the West Salem TBS #1 blow off valve. Replacement of leaking valve required for branch line odorization. |  |  |  | 0 |  | P | N | N
15 | 16040 | DES | WATERLOO | 5 | INSTALL PLC | 2001-10-01 08:00 | 2001-10-31 16:00 | 30.3 |  | 425 | C.014520 | 0 | 0 | Shut down unit 5 at Waterloo for the installation of a new PLC and the replacement of selected end devices. |  | 2001-10-01 08:00 |  | 0 |  | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Des Moines Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 18, 2001 | [10 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[11 empty] | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 16063 | BELLEVILLE | 1 | ANNUAL PM | 2001-10-15 09:00 | 2001-10-19 16:00 | 4.3 |  | OPS |  | 0 | 0 | Belleville Unit 1 annual PM. 1100 HP (Dates are tentative the PM's will be done whenever the system and the teams are able. |  |  |  | 0 |  | P | N | N
2 | 16064 | BELLEVILLE | 2 | ANNUAL PM | 2001-10-22 09:00 | 2001-10-26 16:00 | 4.3 |  | OPS |  | 0 | 0 | Belleville Unit 2 annual PM. 1100 HP (Dates are tentative the PM's will be done whenever the system and the teams are able). |  |  |  | 0 |  | P | N | N
3 | 16065 | BELLEVILLE | 3 | ANNUAL PM | 2001-10-29 09:00 | 2001-11-02 16:00 | 4.3 |  | OPS |  | 0 | 0 | Belleville Unit 3 Annual PM. 1100 HP (Dates are tentative the PM's will be done whenever the system and the teams are able). |  |  |  | 0 |  | P | N | N
4 | 17521 | BELLEVILLE | 1 2 3 | ESD TEST | 2002-05-07 10:00 | 2002-05-07 12:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 3300 HP |  |  |  | 0 |  | P | N | N
5 | 16066 | GALENA | 1 | ANNUAL PM | 2001-11-05 08:00 | 2001-11-09 16:00 | 4.3 |  | OPS |  | 0 | 0 | Galena Unit 1 Annual PM. 4000 HP |  |  |  | 0 |  | P | N | N
6 | 16067 | GALENA | 2 | ANNUAL PM | 2001-11-12 08:00 | 2001-11-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Galena Unit 2 Annual PM. 4000 HP |  |  |  | 0 |  | P | N | N
7 | 17161 | GALENA | 1 | OVERHAUL | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Solar Centaur Turbine exchange based on analysis and run hours. |  |  |  | 0 |  | P | N | N
8 | 17520 | GALENA | 1 2 | ESD TEST | 2002-05-14 09:00 | 2002-05-14 11:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 8000 HP |  |  |  | 0 |  | P | N | N
9 | 17726 | OGDEN | 14 | LEAK | 2001-10-15 10:00 | 2001-10-17 15:30 | 2.2 |  | OPS |  | 0 | 0 | Inner cooler leak. 2000 HP |  | 2001-10-15 10:00 |  | 0 |  | U | N | N
10 | 17725 | OGDEN | 11 | SPARK PLUG WELLS | 2001-10-18 09:00 | 2001-10-26 15:00 | 4.3 |  | OPS |  | 0 | 0 | Remove mill in place and install new Dry type spark plug wells. 1600 HP |  |  |  | 0 |  | P | N | N
11 | 17724 | OGDEN | 12 | SPARK PLUG WELLS | 2001-10-29 09:00 | 2001-11-02 15:00 | 4.3 |  | OPS |  | 0 | 0 | Remove mill in place and install new Dry type spark plug wells. 1600 HP |  |  |  | 0 |  | P | N | N
12 | 17164 | OGDEN | 15 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 |  | P | N | N
13 | 17229 | OTTAWA | N MANHATTAN | N MANHATTAN CV | 2002-04-17 08:00 | 2002-04-21 16:00 | 4.3 |  | 453 | C.014802 | 0 | 0 | North Manhattan CV replacement. Remove existing control valve and install a new quieter valve. |  |  |  | 0 |  | P | N | N
14 | 17414 | PLATTEVILLE | W SALEM TBS | W SALEM TBS | 2001-10-24 08:00 | 2001-10-24 16:00 | 0.3 | WIB12201 | 453 | C.014888 | 0 | 0 | Replace the West Salem TBS #1 blow off valve. Replacement of leaking valve required for branch line odorization. |  |  |  | 0 |  | P | N | N
15 | 16040 | WATERLOO | 5 | INSTALL PLC | 2001-10-01 08:00 | 2001-10-31 16:00 | 30.3 |  | 425 | C.014520 | 0 | 0 | Shut down unit 5 at Waterloo for the installation of a new PLC and the replacement of selected end devices. |  | 2001-10-01 08:00 |  | 0 |  | P | N | N