## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Beatrice Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 19, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 16516 | BEA | BEATRICE | 25 | ALIGNMENT & MAINTENANCE | 2001-07-23 08:00 | 2001-10-19 16:00 | 88.3 |  | OPS |  | 0 | 0 | Camshaft alignment. Minor maintenance. |  | 2001-07-23 08:00 |  | 0 |  | P | N | N
2 | 17690 | BEA | BEATRICE | 21 | MAINTENANCE | 2001-10-08 07:30 | 2001-10-10 16:00 | 2.4 |  | OPS |  | 0 | 0 | Replace foundation bolt nuts take crankshaft deflections and compressor rod run out readings. 2000 HP |  |  |  | 0 |  | P | N | N
3 | 17340 | BEA | BEATRICE | SCHUYLER BL | SCHUYLER BL CASING | 2001-10-15 07:00 | 2001-10-18 15:00 | 3.3 | NEB41701 | OPS |  | 0 | 0 | Remove 57' of casing from abandoned railroad ROW on the 8" Schuyler BL at MP 7.59. Contract services will be utilized for the removal process. |  |  |  | 0 |  | P | N | N
4 | 16952 | BEA | BEATRICE | C LINE | TRAILBLAZER TO C LINE | 2001-10-30 07:00 | 2001-10-30 23:00 | 0.7 |  | 453 | C.014625 | 230 | 153.3 | Install a new line from the Trailblazer line to the C line and modify existing valve to allow the TB to A line tie-over to be utilized. (TB line will require a 16 hour outage where there will be no flow from Trailblazer). Blk Vlv 63101 BBB01 will be clos | ed to isolate the line segment. C line suction upstream of ML block vlv will also require an outage. |  |  | 0 |  | P | N | N
5 | 17735 | BEA | BUSHTON | 32 | UNIT EXCHANGE | 2001-10-15 08:00 | 2001-11-01 16:00 | 17.3 |  | OPS |  | 0 | 0 | Unit 32 is in California for repair. We are putting unit 25 from Mullinvile it's place until further notice or unit 32 has been been completed and returned to service. |  | 2001-10-15 08:00 |  | 0 |  | P | N | N
6 | 17497 | BEA | BUSHTON | CONTROLLER #5 | CHECK VALVE | 2001-10-31 08:00 | 2001-10-31 15:00 | 0.3 |  | OPS |  | 130 | 37.9 | Remove check valve flapper from controller 5 check valve. (This date is tentative). Outage depends on approval and when Jomax Const can start. |  |  |  | 0 |  | P | N | N
7 | 16935 | BEA | BUSHTON |  | LYONS FUEL GAS | 2001-11-14 08:00 | 2001-11-21 16:00 | 7.3 |  | 453 | C.014723 | 0 | 0 | Install 500 000 BTU/hr heater on the main fuel gas supply line and connect the Lyons gas into the main plant fuel gas. Also install filter/separator on the Lyons supply gas line. |  |  |  | 0 |  | P | N | N
8 | 17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 |  | P | N | N
9 | 17548 | BEA | CUNNINGHAM | #3 DEHY | HEAT EXCHANGER ON #3 DEHY | 2001-09-21 08:00 | 2001-10-31 16:00 | 40.3 |  | OPS |  | 0 | 0 | Take Heat Exchanger out of #3 dehy to be repaired. We will have to take it to Tulsa to get fixed. Max withdrawl volumes will not be affected unless we go below 48 BCF GIP. |  | 2001-09-21 08:00 |  | 0 |  | U | N | N
10 | 17155 | BEA | CUNNINGHAM | 6 | OVERHAUL | 2001-10-08 08:00 | 2001-11-02 16:00 | 25.3 |  | OPS |  | 0 | 0 | Major overhaul on MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (This outage will decrease the total injection & withdrawal rate by 100mmcfd). |  |  |  | 0 |  | P | N | N
11 | 17714 | BEA | CUNNINGHAM | UGS WELLS | INTERNAL CORROSION | 2001-10-12 07:00 | 2001-11-12 15:30 | 31.3 |  | OPS |  | 20 | 626.7 | Wells 36-13 and 36-14 are unavailable for withdrawal due to internal corrosion on the separators vessels. |  | 2001-10-12 07:00 |  | 0 |  | U | N | N
12 | 17332 | BEA | CUNNINGHAM | ALL | ELEC SWITCH GEAR | 2001-11-12 07:00 | 2001-11-16 16:00 | 4.4 |  | OPS |  | 0 | 0 | Week of 11/12-16 all electrics will not be available. 11/12 & 13 dual fuels are available. 11/14 dual fuels are not available from 8:00 to 16:00 11/15 - 12 noon all units and plants should be available. Electric test switch gear and 4000 volt motors. |  |  |  | 0 |  | P | N | N
13 | 16070 | BEA | OAKLAND | MACEDONIA BL | MACEDONIA BL | 2001-09-24 08:00 | 2001-10-15 16:00 | 21.3 | IAB74701 | 453 | C.014567 | 0 | 0 | Replace and lower approximately 1250 ft of the 2" Macedonia BL (IAB74701 at the Nishnabotna River Crossing MP 3.32. |  |  |  | 0 |  | P | N | N
14 | 17739 | BEA | OAKLAND | 18 | CRANKCASE EXPLOSION | 2001-10-16 18:00 | 2001-10-19 18:00 | 3 |  | OPS |  | 250 | 750 | Crankcase explosion on unit 18. Replace liner and piston. 3400 HP |  | 2001-10-16 18:00 |  | 0 |  | U | N | N
15 | 17166 | BEA | PALMYRA | 21 | OVERHAUL | 2002-05-06 08:00 | 2002-05-31 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 |  | P | N | N
16 | 17167 | BEA | PALMYRA | 22 | OVERHAUL | 2002-05-27 08:00 | 2002-06-14 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 |  | P | N | N
17 | 17736 | BEA | TESCOTT | 1 2 | SCRUBBER TANK | 2001-10-18 12:00 | 2001-10-26 16:00 | 8.2 |  | OPS |  | 0 | 0 | Units 1 & 2 suction header will be blown down to remove the old scrubber tank and vent any leakage from any of the other scrubbers through them. Part of outage 17507. 12 400 HP |  | 2001-10-18 12:00 |  | 0 |  | U | N | N
18 | 17507 | BEA | TESCOTT | ALL | SCRUBBERS | 2001-10-22 08:00 | 2001-10-26 17:00 | 4.4 |  | OPS | C.014568 | 0 | 0 | Replace scrubber dump tank and install new level controls and dump valves on 10 scrubbers. |  |  |  | 0 |  | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Beatrice Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 19, 2001 | [10 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[11 empty] | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 16516 | BEATRICE | 25 | ALIGNMENT & MAINTENANCE | 2001-07-23 08:00 | 2001-10-19 16:00 | 88.3 |  | OPS |  | 0 | 0 | Camshaft alignment. Minor maintenance. |  | 2001-07-23 08:00 |  | 0 |  | P | N | N
2 | 17690 | BEATRICE | 21 | MAINTENANCE | 2001-10-08 07:30 | 2001-10-10 16:00 | 2.4 |  | OPS |  | 0 | 0 | Replace foundation bolt nuts take crankshaft deflections and compressor rod run out readings. 2000 HP |  |  |  | 0 |  | P | N | N
3 | 17340 | BEATRICE | SCHUYLER BL | SCHUYLER BL CASING | 2001-10-15 07:00 | 2001-10-18 15:00 | 3.3 | NEB41701 | OPS |  | 0 | 0 | Remove 57' of casing from abandoned railroad ROW on the 8" Schuyler BL at MP 7.59. Contract services will be utilized for the removal process. |  |  |  | 0 |  | P | N | N
4 | 16952 | BEATRICE | C LINE | TRAILBLAZER TO C LINE | 2001-10-30 07:00 | 2001-10-30 23:00 | 0.7 |  | 453 | C.014625 | 230 | 153.3 | Install a new line from the Trailblazer line to the C line and modify existing valve to allow the TB to A line tie-over to be utilized. (TB line will require a 16 hour outage where there will be no flow from Trailblazer). Blk Vlv 63101 BBB01 will be clos | ed to isolate the line segment. C line suction upstream of ML block vlv will also require an outage. |  |  | 0 |  | P | N | N
5 | 17735 | BUSHTON | 32 | UNIT EXCHANGE | 2001-10-15 08:00 | 2001-11-01 16:00 | 17.3 |  | OPS |  | 0 | 0 | Unit 32 is in California for repair. We are putting unit 25 from Mullinvile it's place until further notice or unit 32 has been been completed and returned to service. |  | 2001-10-15 08:00 |  | 0 |  | P | N | N
6 | 17497 | BUSHTON | CONTROLLER #5 | CHECK VALVE | 2001-10-31 08:00 | 2001-10-31 15:00 | 0.3 |  | OPS |  | 130 | 37.9 | Remove check valve flapper from controller 5 check valve. (This date is tentative). Outage depends on approval and when Jomax Const can start. |  |  |  | 0 |  | P | N | N
7 | 16935 | BUSHTON |  | LYONS FUEL GAS | 2001-11-14 08:00 | 2001-11-21 16:00 | 7.3 |  | 453 | C.014723 | 0 | 0 | Install 500 000 BTU/hr heater on the main fuel gas supply line and connect the Lyons gas into the main plant fuel gas. Also install filter/separator on the Lyons supply gas line. |  |  |  | 0 |  | P | N | N
8 | 17151 | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 |  | P | N | N
9 | 17548 | CUNNINGHAM | #3 DEHY | HEAT EXCHANGER ON #3 DEHY | 2001-09-21 08:00 | 2001-10-31 16:00 | 40.3 |  | OPS |  | 0 | 0 | Take Heat Exchanger out of #3 dehy to be repaired. We will have to take it to Tulsa to get fixed. Max withdrawl volumes will not be affected unless we go below 48 BCF GIP. |  | 2001-09-21 08:00 |  | 0 |  | U | N | N
10 | 17155 | CUNNINGHAM | 6 | OVERHAUL | 2001-10-08 08:00 | 2001-11-02 16:00 | 25.3 |  | OPS |  | 0 | 0 | Major overhaul on MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (This outage will decrease the total injection & withdrawal rate by 100mmcfd). |  |  |  | 0 |  | P | N | N
11 | 17714 | CUNNINGHAM | UGS WELLS | INTERNAL CORROSION | 2001-10-12 07:00 | 2001-11-12 15:30 | 31.3 |  | OPS |  | 20 | 626.7 | Wells 36-13 and 36-14 are unavailable for withdrawal due to internal corrosion on the separators vessels. |  | 2001-10-12 07:00 |  | 0 |  | U | N | N
12 | 17332 | CUNNINGHAM | ALL | ELEC SWITCH GEAR | 2001-11-12 07:00 | 2001-11-16 16:00 | 4.4 |  | OPS |  | 0 | 0 | Week of 11/12-16 all electrics will not be available. 11/12 & 13 dual fuels are available. 11/14 dual fuels are not available from 8:00 to 16:00 11/15 - 12 noon all units and plants should be available. Electric test switch gear and 4000 volt motors. |  |  |  | 0 |  | P | N | N
13 | 16070 | OAKLAND | MACEDONIA BL | MACEDONIA BL | 2001-09-24 08:00 | 2001-10-15 16:00 | 21.3 | IAB74701 | 453 | C.014567 | 0 | 0 | Replace and lower approximately 1250 ft of the 2" Macedonia BL (IAB74701 at the Nishnabotna River Crossing MP 3.32. |  |  |  | 0 |  | P | N | N
14 | 17739 | OAKLAND | 18 | CRANKCASE EXPLOSION | 2001-10-16 18:00 | 2001-10-19 18:00 | 3 |  | OPS |  | 250 | 750 | Crankcase explosion on unit 18. Replace liner and piston. 3400 HP |  | 2001-10-16 18:00 |  | 0 |  | U | N | N
15 | 17166 | PALMYRA | 21 | OVERHAUL | 2002-05-06 08:00 | 2002-05-31 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 |  | P | N | N
16 | 17167 | PALMYRA | 22 | OVERHAUL | 2002-05-27 08:00 | 2002-06-14 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 |  | P | N | N
17 | 17736 | TESCOTT | 1 2 | SCRUBBER TANK | 2001-10-18 12:00 | 2001-10-26 16:00 | 8.2 |  | OPS |  | 0 | 0 | Units 1 & 2 suction header will be blown down to remove the old scrubber tank and vent any leakage from any of the other scrubbers through them. Part of outage 17507. 12 400 HP |  | 2001-10-18 12:00 |  | 0 |  | U | N | N
18 | 17507 | TESCOTT | ALL | SCRUBBERS | 2001-10-22 08:00 | 2001-10-26 17:00 | 4.4 |  | OPS | C.014568 | 0 | 0 | Replace scrubber dump tank and install new level controls and dump valves on 10 scrubbers. |  |  |  | 0 |  | P | N | N