## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted November 1, 2001 | [11 empty] | Max | Projected | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Flow | Flow | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[12 empty] | (Mmcfd) | (Mmcfd) | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 17756 | ALB | ARTESIA | AGAVE I/C | HOT TAP | 2001-11-27 08:00 | 2001-11-27 17:00 | 0.4 |  | OPS |  | 0 | 0 | 0 | 0 | Doing a hot tap on the 24" loop line. Max pressure at needed during the work is 712#. |  |  |  | 0 |  | P | N | N
2 | 17144 | ALB | ATOKA 1 | 719 | HEAD EXCHANGE | 2002-03-05 08:00 | 2002-03-07 16:00 | 2.3 |  | OPS |  | 0 | 0 | 0 | 0 | Complete UX head exchange. Contractor will remove all power heads. Inspect combustion chambers clean and reinstall new heads. |  |  |  | 0 |  | P | N | N
3 | 17142 | ALB | ATOKA 1 | 719 | OVERHAUL | 2002-03-12 08:00 | 2002-03-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | 0 | 0 | Contractor will perform a complete compressor overhaul replace rings packing R&R all valves inspect cylinders for wear and check rod and main bearings. |  |  |  | 0 |  | P | N | N
4 | 17145 | ALB | ATOKA 1 | 737 | OVERHAUL | 2002-03-18 08:00 | 2002-03-22 16:00 | 4.3 |  | OPS |  | 0 | 0 | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. |  |  |  | 0 |  | P | N | N
5 | 17146 | ALB | ATOKA 1 | 761 | OVERHAUL | 2002-03-25 08:00 | 2002-03-29 16:00 | 4.3 |  | OPS |  | 0 | 0 | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. |  |  |  | 0 |  | P | N | N
6 | 18031 | ALB | ATOKA 3 | 762 | BEARING & ROD | 2001-11-01 08:00 | 2001-11-01 16:00 | 0.3 |  | OPS |  | 0 | 0 | 7 | 2.3 | They need to repair a bad bearing rod on the fans. |  |  |  | 0 |  | U | N | N
7 | 17395 | ALB | CRAWFORD | 756 | CLEAN & INHIBIT THE CRAWFORD LOOP 16 | 2001-10-29 07:00 | 2001-11-01 16:00 | 3.4 |  | OPS |  | 0 | 0 | 0 | 0 | Flow will need to be cut from 54 mmcf/day to 40 mmcf/day. Arther Pue farm tap & Highlands Crawford Delivery will be shut in so that no chemical will get into the system. |  |  |  | 0 |  | P | N | N
8 | 17148 | ALB | CRAWFORD | 751 | OVERHAUL | 2002-03-11 08:00 | 2002-03-13 16:00 | 2.3 |  | OPS |  | 0 | 0 | 0 | 0 | Complete UX turbine exchange. Contractor will remove old turbine and install and align new reconditioned turbine. |  |  |  | 0 |  | P | N | N
9 | 17092 | ALB | STATION 1 | MAINLINE | RED ROCK TIE-IN | 2002-03-04 08:00 | 2002-03-08 16:00 | 4.3 |  | OPS |  | 0 | 0 | 100 | 433.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 |  | P | N | N
10 | 17093 | ALB | STATION 1 | LOOP LINE | RED ROCK TIE-IN | 2002-03-11 08:00 | 2002-03-13 16:00 | 2.3 |  | OPS |  | 0 | 0 | 100 | 233.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 |  | P | N | N
11 | 17090 | ALB | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-11-12 08:00 | 2001-11-15 16:00 | 3.3 |  | OPS |  | 0 | 0 | 130 | 433.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 |  | P | N | N
12 | 17091 | ALB | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-15 08:00 | 2001-11-19 16:00 | 4.3 |  | OPS |  | 0 | 0 | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 |  | P | N | N
13 | 17095 | ALB | STATION 3 | MAINLINE | RED ROCK TIE-IN | 2002-03-18 08:00 | 2002-03-22 16:00 | 4.3 |  | OPS |  | 0 | 0 | 80 | 346.7 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 |  | P | N | N
14 | 17096 | ALB | STATION 3 | LOOP LINE | RED ROCK TIE-IN | 2002-03-25 08:00 | 2002-03-27 16:00 | 2.3 |  | OPS |  | 0 | 0 | 80 | 186.7 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 |  | P | N | N
15 | 17128 | ALB | STATION 4 | 401 | OVERHAUL | 2002-04-01 08:00 | 2002-05-10 16:00 | 39.3 |  | OPS |  | 0 | 0 | 200 | 7866.7 | Contractor will disassemble unit all the way to the lower block. Compressor will be overhauled with new rods packing ring and all new compressor valves unit realigned and rechocked. |  |  |  | 0 |  | P | N | N
16 | 17129 | ALB | STATION 4 | 402 | OVERHAUL | 2002-05-15 08:00 | 2002-05-25 16:00 | 10.3 |  | OPS |  | 0 | 0 | 200 | 2066.7 | Contractor will provide coplete compressor overhaul with new rods packing ring and all new compressor valves. Turbo after coolers will be removed and cleaned. |  |  |  | 0 |  | P | N | N
17 | 17130 | ALB | STATION 4 | 403 | OVERHAUL | 2002-05-26 08:00 | 2002-06-04 16:00 | 9.3 |  | OPS |  | 0 | 0 | 200 | 1866.7 | Contractor will provide coplete compressor overhaul with new rods packing ring and all new compressor valves. Turbo after coolers will be removed and cleaned. |  |  |  | 0 |  | P | N | N
18 | 17132 | ALB | STATION 5 | 502 | OVERHAUL | 2002-05-01 08:00 | 2002-05-07 16:00 | 6.3 |  | OPS |  | 0 | 0 | 0 | 0 | Contractor will remove the old exhaust manifold system and replace with new exhaust manifold system. Also replace turbocharger and turbo coolers with the spare turbo and coolers at the station. |  |  |  | 0 |  | P | N | N
19 | 17131 | ALB | STATION 5 | 501 PHFU | OVERHAUL | 2002-05-10 08:00 | 2002-05-24 16:00 | 14.3 |  | OPS |  | 0 | 0 | 0 | 0 | Contractor will remove and replace both left and right bank upper blocks. Block replacement will result in a complete upper end overhaul. |  |  |  | 0 |  | P | N | N
20 | 17136 | ALB | STATION 7 | 701 PHFU | OVERHAUL | 2002-04-03 08:00 | 2002-04-11 16:00 | 8.3 |  | OPS |  | 0 | 0 | 0 | 0 | Contractor will remove the old exhaust manifold and replace with new exhaust manifold system. Both intake manifolds will also be replaced. Intake manifolds will be supplied by Enron. Unit main frame bolts will be checked by ultrasound. Bolts will be rep | laced if cracked or broken. |  |  | 0 |  | P | N | N
21 | 17137 | ALB | STATION 7 | 702 PHFU | OVERHAUL | 2002-04-15 08:00 | 2002-04-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | 0 | 0 | Contractor will remove left and right intake manifolds and send them to Coopers shop in Odessa for repairs. Upon completion contractor will reinstall. |  |  |  | 0 |  | P | N | N
22 | 17138 | ALB | STATION 7 | 721 | OVERHAUL | 2002-05-20 08:00 | 2002-05-28 16:00 | 8.3 |  | OPS |  | 0 | 0 | 0 | 0 | Contractor will perform a complete upper and lower end overhaul. Ciontractor will remove generator and it will be sent in for complete restoration. |  |  |  | 0 |  | P | N | N
23 | 16752 | ALB | STATION 8 | ALL | AUTOMATION | 2001-09-04 08:00 | 2001-10-31 16:00 | 57.3 |  | OPS |  | 0 | 0 | 0 | 0 | Station 8 automation project. 8000 HP |  | 2001-09-04 08:00 |  | 0 |  | P | N | N
24 | 17694 | ALB | STATION 9 | 903 | EXHAUST MANIFOLD | 2001-11-05 08:00 | 2001-11-16 08:00 | 11 |  | OPS |  | 0 | 0 | 0 | 0 | Change out 903 exhaust manifold. |  |  |  | 0 |  | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through May 31, 2002
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted November 1, 2001 | [10 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act. | Act.
No. | ID# | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | Throughput | P/U | Pub | Ver
[11 empty] | (Mmcfd) | [5 empty] | mmcf/d | Affect
1 | 17756 | ARTESIA | AGAVE I/C | HOT TAP | 2001-11-27 08:00 | 2001-11-27 17:00 | 0.4 |  | OPS |  | 0 | 0 | Doing a hot tap on the 24" loop line. Max pressure at needed during the work is 712#. |  |  |  | 0 |  | P | N | N
2 | 17144 | ATOKA 1 | 719 | HEAD EXCHANGE | 2002-03-05 08:00 | 2002-03-07 16:00 | 2.3 |  | OPS |  | 0 | 0 | Complete UX head exchange. Contractor will remove all power heads. Inspect combustion chambers clean and reinstall new heads. |  |  |  | 0 |  | P | N | N
3 | 17142 | ATOKA 1 | 719 | OVERHAUL | 2002-03-12 08:00 | 2002-03-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul replace rings packing R&R all valves inspect cylinders for wear and check rod and main bearings. |  |  |  | 0 |  | P | N | N
4 | 17145 | ATOKA 1 | 737 | OVERHAUL | 2002-03-18 08:00 | 2002-03-22 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. |  |  |  | 0 |  | P | N | N
5 | 17146 | ATOKA 1 | 761 | OVERHAUL | 2002-03-25 08:00 | 2002-03-29 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. |  |  |  | 0 |  | P | N | N
6 | 18031 | ATOKA 3 | 762 | BEARING & ROD | 2001-11-01 08:00 | 2001-11-01 16:00 | 0.3 |  | OPS |  | 7 | 2.3 | They need to repair a bad bearing rod on the fans. |  |  |  | 0 |  | U | N | N
7 | 17395 | CRAWFORD | 756 | CLEAN & INHIBIT THE CRAWFORD LOOP 16 | 2001-10-29 07:00 | 2001-11-01 16:00 | 3.4 |  | OPS |  | 0 | 0 | Flow will need to be cut from 54 mmcf/day to 40 mmcf/day. Arther Pue farm tap & Highlands Crawford Delivery will be shut in so that no chemical will get into the system. |  |  |  | 0 |  | P | N | N
8 | 17148 | CRAWFORD | 751 | OVERHAUL | 2002-03-11 08:00 | 2002-03-13 16:00 | 2.3 |  | OPS |  | 0 | 0 | Complete UX turbine exchange. Contractor will remove old turbine and install and align new reconditioned turbine. |  |  |  | 0 |  | P | N | N
9 | 17092 | STATION 1 | MAINLINE | RED ROCK TIE-IN | 2002-03-04 08:00 | 2002-03-08 16:00 | 4.3 |  | OPS |  | 100 | 433.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 |  | P | N | N
10 | 17093 | STATION 1 | LOOP LINE | RED ROCK TIE-IN | 2002-03-11 08:00 | 2002-03-13 16:00 | 2.3 |  | OPS |  | 100 | 233.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 |  | P | N | N
11 | 17090 | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-11-12 08:00 | 2001-11-15 16:00 | 3.3 |  | OPS |  | 130 | 433.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 |  | P | N | N
12 | 17091 | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-15 08:00 | 2001-11-19 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 |  | P | N | N
13 | 17095 | STATION 3 | MAINLINE | RED ROCK TIE-IN | 2002-03-18 08:00 | 2002-03-22 16:00 | 4.3 |  | OPS |  | 80 | 346.7 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 |  | P | N | N
14 | 17096 | STATION 3 | LOOP LINE | RED ROCK TIE-IN | 2002-03-25 08:00 | 2002-03-27 16:00 | 2.3 |  | OPS |  | 80 | 186.7 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 |  | P | N | N
15 | 17128 | STATION 4 | 401 | OVERHAUL | 2002-04-01 08:00 | 2002-05-10 16:00 | 39.3 |  | OPS |  | 200 | 7866.7 | Contractor will disassemble unit all the way to the lower block. Compressor will be overhauled with new rods packing ring and all new compressor valves unit realigned and rechocked. |  |  |  | 0 |  | P | N | N
16 | 17129 | STATION 4 | 402 | OVERHAUL | 2002-05-15 08:00 | 2002-05-25 16:00 | 10.3 |  | OPS |  | 200 | 2066.7 | Contractor will provide coplete compressor overhaul with new rods packing ring and all new compressor valves. Turbo after coolers will be removed and cleaned. |  |  |  | 0 |  | P | N | N
17 | 17130 | STATION 4 | 403 | OVERHAUL | 2002-05-26 08:00 | 2002-06-04 16:00 | 9.3 |  | OPS |  | 200 | 1866.7 | Contractor will provide coplete compressor overhaul with new rods packing ring and all new compressor valves. Turbo after coolers will be removed and cleaned. |  |  |  | 0 |  | P | N | N
18 | 17132 | STATION 5 | 502 | OVERHAUL | 2002-05-01 08:00 | 2002-05-07 16:00 | 6.3 |  | OPS |  | 0 | 0 | Contractor will remove the old exhaust manifold system and replace with new exhaust manifold system. Also replace turbocharger and turbo coolers with the spare turbo and coolers at the station. |  |  |  | 0 |  | P | N | N
19 | 17131 | STATION 5 | 501 PHFU | OVERHAUL | 2002-05-10 08:00 | 2002-05-24 16:00 | 14.3 |  | OPS |  | 0 | 0 | Contractor will remove and replace both left and right bank upper blocks. Block replacement will result in a complete upper end overhaul. |  |  |  | 0 |  | P | N | N
20 | 17136 | STATION 7 | 701 PHFU | OVERHAUL | 2002-04-03 08:00 | 2002-04-11 16:00 | 8.3 |  | OPS |  | 0 | 0 | Contractor will remove the old exhaust manifold and replace with new exhaust manifold system. Both intake manifolds will also be replaced. Intake manifolds will be supplied by Enron. Unit main frame bolts will be checked by ultrasound. Bolts will be rep | laced if cracked or broken. |  |  | 0 |  | P | N | N
21 | 17137 | STATION 7 | 702 PHFU | OVERHAUL | 2002-04-15 08:00 | 2002-04-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Contractor will remove left and right intake manifolds and send them to Coopers shop in Odessa for repairs. Upon completion contractor will reinstall. |  |  |  | 0 |  | P | N | N
22 | 17138 | STATION 7 | 721 | OVERHAUL | 2002-05-20 08:00 | 2002-05-28 16:00 | 8.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete upper and lower end overhaul. Ciontractor will remove generator and it will be sent in for complete restoration. |  |  |  | 0 |  | P | N | N
23 | 16752 | STATION 8 | ALL | AUTOMATION | 2001-09-04 08:00 | 2001-10-31 16:00 | 57.3 |  | OPS |  | 0 | 0 | Station 8 automation project. 8000 HP |  | 2001-09-04 08:00 |  | 0 |  | P | N | N
24 | 17694 | STATION 9 | 903 | EXHAUST MANIFOLD | 2001-11-05 08:00 | 2001-11-16 08:00 | 11 |  | OPS |  | 0 | 0 | Change out 903 exhaust manifold. |  |  |  | 0 |  | P | N | N