## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - December 1, 2001 Through January 31, 2002
NORTHERN & TRANSWESTERN RegionS Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted December 10, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Hours/ | Total | P/U | Pub | Ver
[12 empty] | (Mmcfd) |  |  |  |  | Day | Hours
1 | 18147 | AMA | BEAVER 2 | 5 | REPLACE LINER EALS | 2001-12-10 07:30 | 2001-12-14 16:00 | 4.4 |  | OPS |  | 4 | 16 | Pull liners and replace liner seals o rings and head gasket. |  |  | 0 | 0 | P | N | N
2 | 18080 | AMA | ELLIS 1 | 1 | 1500 HR INSP | 2001-12-12 09:00 | 2001-12-12 12:00 | 0.1 |  | OPS |  | 3 | 0.4 | 1500 Hr. Inspection 506 HP |  |  | 0 | 0 | P | N | N
3 | 18079 | AMA | ELLIS 1 | 3 | 1500 HR INSP | 2001-12-13 09:00 | 2001-12-13 12:00 | 0.1 |  | OPS |  | 3 | 0.4 | 1500 Hr. Inspection. 649 HP |  |  | 0 | 0 | P | N | N
4 | 18086 | AMA | ELLIS 3 | 6 | 1500 HR INSP | 2001-12-06 09:00 | 2001-12-06 12:00 | 0.1 |  | OPS |  | 3.5 | 0.4 | 1500 Hr. Inspection. 527 HP |  |  | 0 | 0 | P | N | N
1 | 18140 | LIB | FINNEY 2 | ALL | VRU INSTALLATION | 2001-12-18 08:00 | 2001-12-18 14:00 | 0.3 |  | OPS |  | 16 | 4 | Installation of VRU's. |  |  | 0 | 0 | P | N | N
2 | 18142 | LIB | FINNEY 3 | ALL | VRU INSTALLATION | 2001-12-19 08:00 | 2001-12-19 14:00 | 0.3 |  | OPS |  | 5 | 1.3 | Installation of VRU's. |  |  | 0 | 0 | P | N | N
3 | 17991 | LIB | FINNEY 3 | 3 | MAINTENANCE | 2002-01-08 09:00 | 2002-01-08 16:00 | 0.3 |  | OPS |  | 3 | 0.9 | Scheduled maintenance: work orders & DET list. |  |  | 0 | 0 | P | N | N
4 | 18141 | LIB | FINNEY 4 | ALL | VRU INSTALLATION | 2001-12-18 14:00 | 2001-12-18 20:00 | 0.3 |  | OPS |  | 10 | 2.5 | Installation of VRU's. |  |  | 0 | 0 | P | N | N
5 | 18201 | LIB | HUGOTON | 21 | SPEED CONTROL | 2001-12-08 23:30 | 2001-12-10 16:00 | 1.7 |  | OPS |  | 3 | 5.1 | #21 having problems with speed control probably not enough load. |  | 2001-12-08 23:30 | 0 | 0 | U | N | N
6 | 18057 | LIB | HUGOTON | 16 | MAINTENANCE | 2002-01-17 08:00 | 2002-01-17 14:00 | 0.3 |  | OPS |  | 15 | 3.8 | Service & maintenance. 1800 HP |  |  | 0 | 0 | P | N | N
7 | 17824 | LIB | STEVENS 4 | 1 | CHECK VALVES | 2001-12-19 08:00 | 2001-12-19 16:00 | 0.3 |  | OPS |  | 7 | 2.3 | Repairing leaks on the valves. |  |  | 0 | 0 | P | N | N
8 | 17827 | LIB | STEVENS 4 | 2 | CHECK VALVES | 2001-12-20 08:00 | 2001-12-20 16:00 | 0.3 |  | OPS |  | 7 | 2.3 | Repairing check valve leaks. |  |  | 0 | 0 | P | N | N
9 | 17879 | LIB | STEVENS 4 | 1 | SERVICE | 2002-01-09 08:00 | 2002-01-09 16:00 | 0.5 |  | OPS |  | 7 | 3.5 | Service unit & MP 2. |  |  | 0 | 0 | P | N | N
10 | 17890 | LIB | STEVENS 4 | 4 | SERVICE | 2002-01-16 08:00 | 2002-01-16 16:00 | 1.3 |  | OPS |  | 0 | 0 | Service unit & MP 2. |  |  | 0 | 0 | P | N | N
11 | 18171 | LIB | SUBLETTE | VRU | VRU INSTALLATION | 2001-12-17 08:00 | 2001-12-17 20:00 | 0.5 |  | OPS |  | 50 | 25 | Installing VRU unit. Affects Haskell Co. and Sublette field flows. |  |  | 0 | 0 | P | N | N
1 | 18133 | MID | PLAINS TURBINE | 1 | CHANGE SUCTION VALVE | 2001-12-13 08:00 | 2001-12-13 18:00 | 0.4 |  | OPS |  | 0 | 0 | Changing out suction valve to the compressor. (16" valve) ElPaso will move the volumes and give it back to us on the 30". |  |  | 0 | 0 | P | N | N
1 | 18191 | MIN | CHATFIELD | 1 | TROUBLE SHOOTING | 2001-12-12 08:00 | 2001-12-12 16:00 | 0.3 |  | OPS |  | 0 | 0 | The unit is available but there still a few problems they like to iron out. |  |  | 0 | 0 | P | N | N
2 | 18190 | MIN | GARNER | LNG | BEARING FAILURE | 2001-12-04 08:00 | 2001-12-26 16:00 | 22.3 |  | OPS |  | 0 | 0 | Refrigerant compressor is down. Having some bearing problems. Working on problem at this time as to cause. Awaiting parts expected about the 14th. |  | 2001-12-04 08:00 | 0 | 0 | U | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - December 1, 2001 Through January 31, 2002
NORTHERN & TRANSWESTERN RegionS Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted December 10, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Hours/ | Total | P/U | Pub | Ver
[12 empty] | (Mmcfd) |  |  |  |  | Day | Hours
1 | 18147 | AMA | BEAVER 2 | 5 | REPLACE LINER EALS | 2001-12-10 07:30 | 2001-12-14 16:00 | 4.4 |  | OPS |  | 4 | 16 | Pull liners and replace liner seals o rings and head gasket. |  |  | 0 | 0 | P | N | N
2 | 18080 | AMA | ELLIS 1 | 1 | 1500 HR INSP | 2001-12-12 09:00 | 2001-12-12 12:00 | 0.1 |  | OPS |  | 3 | 0.4 | 1500 Hr. Inspection 506 HP |  |  | 0 | 0 | P | N | N
3 | 18079 | AMA | ELLIS 1 | 3 | 1500 HR INSP | 2001-12-13 09:00 | 2001-12-13 12:00 | 0.1 |  | OPS |  | 3 | 0.4 | 1500 Hr. Inspection. 649 HP |  |  | 0 | 0 | P | N | N
4 | 18086 | AMA | ELLIS 3 | 6 | 1500 HR INSP | 2001-12-06 09:00 | 2001-12-06 12:00 | 0.1 |  | OPS |  | 3.5 | 0.4 | 1500 Hr. Inspection. 527 HP |  |  | 0 | 0 | P | N | N
1 | 18140 | LIB | FINNEY 2 | ALL | VRU INSTALLATION | 2001-12-18 08:00 | 2001-12-18 14:00 | 0.3 |  | OPS |  | 16 | 4 | Installation of VRU's. |  |  | 0 | 0 | P | N | N
2 | 18142 | LIB | FINNEY 3 | ALL | VRU INSTALLATION | 2001-12-19 08:00 | 2001-12-19 14:00 | 0.3 |  | OPS |  | 5 | 1.3 | Installation of VRU's. |  |  | 0 | 0 | P | N | N
3 | 17991 | LIB | FINNEY 3 | 3 | MAINTENANCE | 2002-01-08 09:00 | 2002-01-08 16:00 | 0.3 |  | OPS |  | 3 | 0.9 | Scheduled maintenance: work orders & DET list. |  |  | 0 | 0 | P | N | N
4 | 18141 | LIB | FINNEY 4 | ALL | VRU INSTALLATION | 2001-12-18 14:00 | 2001-12-18 20:00 | 0.3 |  | OPS |  | 10 | 2.5 | Installation of VRU's. |  |  | 0 | 0 | P | N | N
5 | 18201 | LIB | HUGOTON | 21 | SPEED CONTROL | 2001-12-08 23:30 | 2001-12-10 16:00 | 1.7 |  | OPS |  | 3 | 5.1 | #21 having problems with speed control probably not enough load. |  | 2001-12-08 23:30 | 0 | 0 | U | N | N
6 | 18057 | LIB | HUGOTON | 16 | MAINTENANCE | 2002-01-17 08:00 | 2002-01-17 14:00 | 0.3 |  | OPS |  | 15 | 3.8 | Service & maintenance. 1800 HP |  |  | 0 | 0 | P | N | N
7 | 17824 | LIB | STEVENS 4 | 1 | CHECK VALVES | 2001-12-19 08:00 | 2001-12-19 16:00 | 0.3 |  | OPS |  | 7 | 2.3 | Repairing leaks on the valves. |  |  | 0 | 0 | P | N | N
8 | 17827 | LIB | STEVENS 4 | 2 | CHECK VALVES | 2001-12-20 08:00 | 2001-12-20 16:00 | 0.3 |  | OPS |  | 7 | 2.3 | Repairing check valve leaks. |  |  | 0 | 0 | P | N | N
9 | 17879 | LIB | STEVENS 4 | 1 | SERVICE | 2002-01-09 08:00 | 2002-01-09 16:00 | 0.5 |  | OPS |  | 7 | 3.5 | Service unit & MP 2. |  |  | 0 | 0 | P | N | N
10 | 17890 | LIB | STEVENS 4 | 4 | SERVICE | 2002-01-16 08:00 | 2002-01-16 16:00 | 1.3 |  | OPS |  | 0 | 0 | Service unit & MP 2. |  |  | 0 | 0 | P | N | N
11 | 18171 | LIB | SUBLETTE | VRU | VRU INSTALLATION | 2001-12-17 08:00 | 2001-12-17 20:00 | 0.5 |  | OPS |  | 50 | 25 | Installing VRU unit. Affects Haskell Co. and Sublette field flows. |  |  | 0 | 0 | P | N | N
1 | 18133 | MID | PLAINS TURBINE | 1 | CHANGE SUCTION VALVE | 2001-12-13 08:00 | 2001-12-13 18:00 | 0.4 |  | OPS |  | 0 | 0 | Changing out suction valve to the compressor. (16" valve) ElPaso will move the volumes and give it back to us on the 30". |  |  | 0 | 0 | P | N | N
1 | 18191 | MIN | CHATFIELD | 1 | TROUBLE SHOOTING | 2001-12-12 08:00 | 2001-12-12 16:00 | 0.3 |  | OPS |  | 0 | 0 | The unit is available but there still a few problems they like to iron out. |  |  | 0 | 0 | P | N | N
2 | 18190 | MIN | GARNER | LNG | BEARING FAILURE | 2001-12-04 08:00 | 2001-12-26 16:00 | 22.3 |  | OPS |  | 0 | 0 | Refrigerant compressor is down. Having some bearing problems. Working on problem at this time as to cause. Awaiting parts expected about the 14th. |  | 2001-12-04 08:00 | 0 | 0 | U | N | N