## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Beatrice Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 15, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18299 | BEA | BEATRICE | 24 | OVERHAUL #12 CYLINDER | 2002-01-14 07:00 | 2002-01-17 15:30 | 3.3 |  | OPS |  | 0 | 0 | Overhaul #12 power cylinder replace compressor valve replace hydraulic lifters etc. |  |  |  | 0 | P | N | N
2 | 18271 | BEA | BUSHTON | 31 | CHANGE WATER PUMP SEAL | 2002-01-09 07:30 | 2002-01-10 16:00 | 1.4 |  | OPS |  | 0 | 0 | Change out water pump seal and PM'S. |  | 2002-01-09 07:30 |  | 0 | U | N | N
3 | 18244 | BEA | BUSHTON | 28 | ANNUAL PM | 2002-01-17 08:00 | 2002-01-18 16:00 | 1.3 |  | OPS |  | 0 | 0 | Annual PM's. (Can do the PM If unit is down for no demand). |  |  |  | 0 | U | N | N
4 | 17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
5 | 17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
6 | 18300 | BEA | CUNNINGHAM | 4 | BAD SPEED SWITCH | 2002-01-12 22:00 | 2002-01-15 16:00 | 2.8 |  | OPS |  | 0 | 0 | Bad speed switch standby sent in for repair (status unknown will check on Monday). Flow affect depends on system requirements. |  | 2002-01-12 22:00 |  | 0 | U | N | N
7 | 17154 | BEA | CUNNINGHAM | 5 | OVERHAUL | 2002-01-28 07:00 | 2002-02-15 16:00 | 18.4 |  | OPS |  | 0 | 0 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
8 | 17166 | BEA | PALMYRA | 21 | OVERHAUL | 2002-05-06 08:00 | 2002-05-31 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
9 | 17167 | BEA | PALMYRA | 22 | OVERHAUL | 2002-05-27 08:00 | 2002-06-14 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
10 | 17168 | BEA | PALMYRA | 23 | OVERHAUL | 2002-06-17 08:00 | 2002-07-05 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
11 | 17169 | BEA | PALMYRA | 24 | OVERHAUL | 2002-07-08 08:00 | 2002-07-19 16:00 | 11.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
12 | 17170 | BEA | PALMYRA | 25 | OVERHAUL | 2002-07-22 08:00 | 2002-08-02 16:00 | 11.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
13 | 16327 | BEA | SO OMAHA | CREEK XING | OMAHA 3RD BL | 2002-07-15 08:00 | 2002-07-15 16:00 | 0.3 |  | 453 | C.014544 | 0 | 0 | Replace and lower approximately 200 feet of the 16" Omaha 3rd branch line at MP 16.86. |  |  |  | 0 | P | N | N
14 | 17172 | BEA | TESCOTT | 2 | OVERHAUL | 2002-08-05 08:00 | 2002-08-30 16:00 | 25.3 |  | OPS |  | 0 | 0 | Turbine overhaul on a GE Frame III based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
15 | 17174 | BEA | TESCOTT | 4 | OVERHAUL | 2002-09-02 08:00 | 2002-09-27 16:00 | 25.3 |  | OPS |  | 0 | 0 | Turbine overhaul on a GE Frame III based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
16 | 17173 | BEA | TESCOTT | 3 | OVERHAUL | 2002-09-30 08:00 | 2002-10-25 16:00 | 25.3 |  | OPS |  | 0 | 0 | Turbine overhaul on a GE Frame III based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Beatrice Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 15, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18299 | BEA | BEATRICE | 24 | OVERHAUL #12 CYLINDER | 2002-01-14 07:00 | 2002-01-17 15:30 | 3.3 |  | OPS |  | 0 | 0 | Overhaul #12 power cylinder replace compressor valve replace hydraulic lifters etc. |  |  |  | 0 | P | N | N
2 | 18271 | BEA | BUSHTON | 31 | CHANGE WATER PUMP SEAL | 2002-01-09 07:30 | 2002-01-10 16:00 | 1.4 |  | OPS |  | 0 | 0 | Change out water pump seal and PM'S. |  | 2002-01-09 07:30 |  | 0 | U | N | N
3 | 18244 | BEA | BUSHTON | 28 | ANNUAL PM | 2002-01-17 08:00 | 2002-01-18 16:00 | 1.3 |  | OPS |  | 0 | 0 | Annual PM's. (Can do the PM If unit is down for no demand). |  |  |  | 0 | U | N | N
4 | 17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
5 | 17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
6 | 18300 | BEA | CUNNINGHAM | 4 | BAD SPEED SWITCH | 2002-01-12 22:00 | 2002-01-15 16:00 | 2.8 |  | OPS |  | 0 | 0 | Bad speed switch standby sent in for repair (status unknown will check on Monday). Flow affect depends on system requirements. |  | 2002-01-12 22:00 |  | 0 | U | N | N
7 | 17154 | BEA | CUNNINGHAM | 5 | OVERHAUL | 2002-01-28 07:00 | 2002-02-15 16:00 | 18.4 |  | OPS |  | 0 | 0 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
8 | 17166 | BEA | PALMYRA | 21 | OVERHAUL | 2002-05-06 08:00 | 2002-05-31 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
9 | 17167 | BEA | PALMYRA | 22 | OVERHAUL | 2002-05-27 08:00 | 2002-06-14 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
10 | 17168 | BEA | PALMYRA | 23 | OVERHAUL | 2002-06-17 08:00 | 2002-07-05 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
11 | 17169 | BEA | PALMYRA | 24 | OVERHAUL | 2002-07-08 08:00 | 2002-07-19 16:00 | 11.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
12 | 17170 | BEA | PALMYRA | 25 | OVERHAUL | 2002-07-22 08:00 | 2002-08-02 16:00 | 11.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
13 | 16327 | BEA | SO OMAHA | CREEK XING | OMAHA 3RD BL | 2002-07-15 08:00 | 2002-07-15 16:00 | 0.3 |  | 453 | C.014544 | 0 | 0 | Replace and lower approximately 200 feet of the 16" Omaha 3rd branch line at MP 16.86. |  |  |  | 0 | P | N | N
14 | 17172 | BEA | TESCOTT | 2 | OVERHAUL | 2002-08-05 08:00 | 2002-08-30 16:00 | 25.3 |  | OPS |  | 0 | 0 | Turbine overhaul on a GE Frame III based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
15 | 17174 | BEA | TESCOTT | 4 | OVERHAUL | 2002-09-02 08:00 | 2002-09-27 16:00 | 25.3 |  | OPS |  | 0 | 0 | Turbine overhaul on a GE Frame III based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
16 | 17173 | BEA | TESCOTT | 3 | OVERHAUL | 2002-09-30 08:00 | 2002-10-25 16:00 | 25.3 |  | OPS |  | 0 | 0 | Turbine overhaul on a GE Frame III based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N