## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
DesMoines Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 17, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17521 | DES | BELLEVILLE | 1 2 3 | ESD TEST | 2002-05-07 10:00 | 2002-05-07 12:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 3300 HP |  |  |  | 0 | P | N | N
2 | 17518 | DES | BELLEVILLE | 1 | ANNUAL PM | 2002-09-09 09:00 | 2002-09-13 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 1100 HP |  |  |  | 0 | P | N | N
3 | 17517 | DES | BELLEVILLE | 2 | ANNUAL PM | 2002-09-16 09:00 | 2002-09-20 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 1100 HP |  |  |  | 0 | P | N | N
4 | 17516 | DES | BELLEVILLE | 3 | ANNUAL PM | 2002-09-23 09:00 | 2002-09-27 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 1100 HP |  |  |  | 0 | P | N | N
5 | 17161 | DES | GALENA | 1 | OVERHAUL | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Solar Centaur Turbine exchange based on analysis and run hours. |  |  |  | 0 | P | N | N
6 | 17520 | DES | GALENA | 1 2 | ESD TEST | 2002-05-14 09:00 | 2002-05-14 11:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 8000 HP |  |  |  | 0 | P | N | N
7 | 17519 | DES | GALENA | 1 | ANNUAL PM | 2002-10-07 08:00 | 2002-10-11 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 4000 HP |  |  |  | 0 | P | N | N
8 | 17515 | DES | GALENA | 2 | ANNUAL PM | 2002-10-14 08:00 | 2002-10-18 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 4000 HP |  |  |  | 0 | P | N | N
9 | 18287 | DES | OGDEN | 16 | P.M. | 2002-02-25 08:00 | 2002-03-25 16:00 | 28.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
10 | 18286 | DES | OGDEN | 15 | P.M. | 2002-03-11 08:00 | 2002-03-22 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
11 | 18285 | DES | OGDEN | 14 | P.M. | 2002-03-25 08:00 | 2002-04-05 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
12 | 18284 | DES | OGDEN | 13 | P.M. | 2002-04-08 08:00 | 2002-04-19 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
13 | 18290 | DES | OGDEN | 16 | MCS & CONTROLS | 2002-04-22 08:00 | 2002-04-26 16:00 | 4.3 |  | OPS |  | 0 | 0 | MCS and Controls work on engines. |  |  |  | 0 | P | N | N
14 | 17164 | DES | OGDEN | 15 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
15 | 18289 | DES | OGDEN | 18 | P.M | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
16 | 18291 | DES | OGDEN | 14 | MCS & CONTROLS | 2002-05-20 08:00 | 2002-05-24 16:00 | 4.3 |  | OPS |  | 0 | 0 | MCS and Controls work on engines. |  |  |  | 0 | P | N | N
17 | 18292 | DES | OGDEN | PLANT 3 | BSD | 2002-05-29 08:00 | 2002-05-29 16:00 | 0.3 |  | OPS |  | 0 | 0 | Scheduled BSD. |  |  |  | 0 | P | N | N
18 | 17163 | DES | OGDEN | 14 | OVERHAUL | 2002-06-03 08:00 | 2002-06-28 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
19 | 18293 | DES | OGDEN | PLANT 2 | BSD | 2002-06-05 08:00 | 2002-06-05 16:00 | 0.3 |  | OPS |  | 0 | 0 | Scheduled BSD. |  |  |  | 0 | P | N | N
20 | 17165 | DES | OGDEN | 16 | OVERHAUL | 2002-07-08 08:00 | 2002-08-02 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
21 | 18278 | DES | OGDEN | 7 | P.M. | 2002-07-29 08:00 | 2002-08-02 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive maintenance. |  |  |  | 0 | P | N | N
22 | 18279 | DES | OGDEN | 8 | P.M. | 2002-08-05 08:00 | 2002-08-09 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
23 | 17162 | DES | OGDEN | 13 | OVERHAUL | 2002-08-05 08:00 | 2002-08-30 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
24 | 18280 | DES | OGDEN | 9 | P.M. | 2002-08-12 08:00 | 2002-08-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
25 | 18281 | DES | OGDEN | 10 | P.M. | 2002-08-19 08:00 | 2002-08-23 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
26 | 18282 | DES | OGDEN | 11 | P.M. | 2002-08-26 08:00 | 2002-08-30 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
27 | 18283 | DES | OGDEN | 12 | P.M. | 2002-09-03 08:00 | 2002-09-06 16:00 | 3.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
28 | 18288 | DES | OGDEN | 17 | P.M. | 2002-09-16 08:00 | 2002-09-27 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
29 | 17229 | DES | OTTAWA | N MANHATTAN | N MANHATTAN CV | 2002-04-17 08:00 | 2002-04-21 16:00 | 4.3 |  | 453 | C.014802 | 0 | 0 | North Manhattan CV replacement. Remove existing control valve and install a new quieter valve. |  |  |  | 0 | P | N | N
30 | 17171 | DES | REDFIELD | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-02 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Cooper GMWA-8based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
DesMoines Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 17, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17521 | DES | BELLEVILLE | 1 2 3 | ESD TEST | 2002-05-07 10:00 | 2002-05-07 12:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 3300 HP |  |  |  | 0 | P | N | N
2 | 17518 | DES | BELLEVILLE | 1 | ANNUAL PM | 2002-09-09 09:00 | 2002-09-13 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 1100 HP |  |  |  | 0 | P | N | N
3 | 17517 | DES | BELLEVILLE | 2 | ANNUAL PM | 2002-09-16 09:00 | 2002-09-20 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 1100 HP |  |  |  | 0 | P | N | N
4 | 17516 | DES | BELLEVILLE | 3 | ANNUAL PM | 2002-09-23 09:00 | 2002-09-27 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 1100 HP |  |  |  | 0 | P | N | N
5 | 17161 | DES | GALENA | 1 | OVERHAUL | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Solar Centaur Turbine exchange based on analysis and run hours. |  |  |  | 0 | P | N | N
6 | 17520 | DES | GALENA | 1 2 | ESD TEST | 2002-05-14 09:00 | 2002-05-14 11:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 8000 HP |  |  |  | 0 | P | N | N
7 | 17519 | DES | GALENA | 1 | ANNUAL PM | 2002-10-07 08:00 | 2002-10-11 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 4000 HP |  |  |  | 0 | P | N | N
8 | 17515 | DES | GALENA | 2 | ANNUAL PM | 2002-10-14 08:00 | 2002-10-18 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 4000 HP |  |  |  | 0 | P | N | N
9 | 18287 | DES | OGDEN | 16 | P.M. | 2002-02-25 08:00 | 2002-03-25 16:00 | 28.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
10 | 18286 | DES | OGDEN | 15 | P.M. | 2002-03-11 08:00 | 2002-03-22 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
11 | 18285 | DES | OGDEN | 14 | P.M. | 2002-03-25 08:00 | 2002-04-05 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
12 | 18284 | DES | OGDEN | 13 | P.M. | 2002-04-08 08:00 | 2002-04-19 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
13 | 18290 | DES | OGDEN | 16 | MCS & CONTROLS | 2002-04-22 08:00 | 2002-04-26 16:00 | 4.3 |  | OPS |  | 0 | 0 | MCS and Controls work on engines. |  |  |  | 0 | P | N | N
14 | 17164 | DES | OGDEN | 15 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
15 | 18289 | DES | OGDEN | 18 | P.M | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
16 | 18291 | DES | OGDEN | 14 | MCS & CONTROLS | 2002-05-20 08:00 | 2002-05-24 16:00 | 4.3 |  | OPS |  | 0 | 0 | MCS and Controls work on engines. |  |  |  | 0 | P | N | N
17 | 18292 | DES | OGDEN | PLANT 3 | BSD | 2002-05-29 08:00 | 2002-05-29 16:00 | 0.3 |  | OPS |  | 0 | 0 | Scheduled BSD. |  |  |  | 0 | P | N | N
18 | 17163 | DES | OGDEN | 14 | OVERHAUL | 2002-06-03 08:00 | 2002-06-28 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
19 | 18293 | DES | OGDEN | PLANT 2 | BSD | 2002-06-05 08:00 | 2002-06-05 16:00 | 0.3 |  | OPS |  | 0 | 0 | Scheduled BSD. |  |  |  | 0 | P | N | N
20 | 17165 | DES | OGDEN | 16 | OVERHAUL | 2002-07-08 08:00 | 2002-08-02 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
21 | 18278 | DES | OGDEN | 7 | P.M. | 2002-07-29 08:00 | 2002-08-02 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive maintenance. |  |  |  | 0 | P | N | N
22 | 18279 | DES | OGDEN | 8 | P.M. | 2002-08-05 08:00 | 2002-08-09 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
23 | 17162 | DES | OGDEN | 13 | OVERHAUL | 2002-08-05 08:00 | 2002-08-30 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
24 | 18280 | DES | OGDEN | 9 | P.M. | 2002-08-12 08:00 | 2002-08-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
25 | 18281 | DES | OGDEN | 10 | P.M. | 2002-08-19 08:00 | 2002-08-23 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
26 | 18282 | DES | OGDEN | 11 | P.M. | 2002-08-26 08:00 | 2002-08-30 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
27 | 18283 | DES | OGDEN | 12 | P.M. | 2002-09-03 08:00 | 2002-09-06 16:00 | 3.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
28 | 18288 | DES | OGDEN | 17 | P.M. | 2002-09-16 08:00 | 2002-09-27 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
29 | 17229 | DES | OTTAWA | N MANHATTAN | N MANHATTAN CV | 2002-04-17 08:00 | 2002-04-21 16:00 | 4.3 |  | 453 | C.014802 | 0 | 0 | North Manhattan CV replacement. Remove existing control valve and install a new quieter valve. |  |  |  | 0 | P | N | N
30 | 17171 | DES | REDFIELD | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-02 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Cooper GMWA-8based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N