## Potrero 03
Owner Name | Mirant California LLC
Station Name | Potrero Power Station
Unit Name | Potrero 03
NERC Region | WSCC
State | CA
Fuel Type | Natural Gas / Fuel Oil
Capacity | 218 MW
Start Date | 2002-01-01
End Date | 2002-01-28
Prv. Start Date | 2002-01-01
Prv. End Date | 2002-01-18
Comments | Boiler / Tune-up Work
SIC | 4931
Plant ID | 1011270
Unit ID | 1005070
Outage ID | 19333

## Shasta 01
Owner Name | US Bureau
Station Name | Shasta Lake Hydro Power Station
Unit Name | Hydro 01
NERC Region | WSCC
State | CA
Fuel Type | Hydro
Capacity | 125 MW
Start Date | 2002-01-07
End Date | 2002-01-27
Prv. Start Date | 2002-01-07
Prv. End Date | 2002-01-20
Comments | Maintenance
SIC | 4911
Plant ID | 1027529
Unit ID | 1007159
Outage ID | 19409

## Rock Creek 02
Owner Name | Pacific Gas and Electric Company
Station Name | Rock Creek Hydro Power House
Unit Name | Hydro 02
NERC Region | WSCC
State | CA
Fuel Type | Hydro
Capacity | 62 MW
Start Date | 2001-10-23
End Date | 2002-01-20
Prv. Start Date | 2001-10-23
Prv. End Date | 2002-01-28
Comments | Valve Repairs
SIC | 4911
Plant ID | 1056456
Unit ID | 1020033
Outage ID | 18706

## Roseville CT 02
Owner Name | Northern California Power Agency
Station Name | Roseville CT Project 01
Unit Name | Roseville CT 02
NERC Region | WSCC
State | CA
Fuel Type | Natural Gas / Fuel Oil
Capacity | 25 MW
Start Date | 2001-12-10
End Date | 2002-01-22
Prv. Start Date | 2001-12-10
Prv. End Date | 2002-01-20
Comments | Generator Work
SIC | 4911
Plant ID | 1054166
Unit ID | 1017466
Outage ID | 19172

## Pittsburg 02
Owner Name | Mirant California LLC
Station Name | Pittsburg Power Station
Unit Name | Pittsburg 02
NERC Region | WSCC
State | CA
Fuel Type | Natural Gas / Fuel Oil
Capacity | 156 MW
Start Date | 2002-01-11
End Date | 2002-01-22
Prv. Start Date | 2002-01-11
Prv. End Date | 2002-01-20
Comments | Multiple Tube Leaks
SIC | 4931
Plant ID | 1507901
Unit ID | 1004728
Outage ID | 19485

## Hunters Point 04
Owner Name | Pacific Gas and Electric Company
Station Name | Hunters Point Power Station
Unit Name | Hunters Point 04
NERC Region | WSCC
State | CA
Fuel Type | Natural Gas / Fuel Oil
Capacity | 156 MW
Start Date | 2001-10-07
End Date | 2002-01-24
Prv. Start Date | 2001-10-07
Prv. End Date | 2002-01-20
Comments | Boiler Work
SIC | 4911
Plant ID | 1011051
Unit ID | 1004950
Outage ID | 15375