## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 22, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18245 | AMA | BEAVER 6 | 2 | 1500 HR. INSPECTION | 2002-02-20 10:00 | 2002-02-20 13:00 | 0.1 |  | OPS |  | 5 | 0.6 | 1500 hour inspection. |  |  |  | 0 | P | N | N
2 | 18262 | AMA | CANADIAN | 1 & 3 | REFLIEF VALVE TEST | 2002-03-12 08:00 | 2002-03-12 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual relief valve test. Station will be shut down. |  |  |  | 0 | P | N | N
3 | 18263 | AMA | CANADIAN | 1 & 3 | ANNUAL ESD | 2002-09-11 08:00 | 2002-09-11 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual ESD. |  |  |  | 0 | P | N | N
4 | 18247 | AMA | ELLIS 1 | 1 | 1500 HR. INSPECTION | 2002-02-12 09:00 | 2002-02-12 16:00 | 0.3 |  | OPS |  | 3 | 0.9 | 1500 hour inspection. |  |  |  | 0 | P | N | N
5 | 18248 | AMA | ELLIS 1 | 3 | 1500 HR. INSPECTION | 2002-02-13 09:00 | 2002-02-13 11:00 | 0.1 |  | OPS |  | 3 | 0.3 | 1500 hour inspection. |  |  |  | 0 | P | N | N
6 | 18249 | AMA | ELLIS 1 | 4 | 1500 HR. INSPECTION | 2002-02-14 09:00 | 2002-02-14 12:00 | 0.1 |  | OPS |  | 7 | 0.9 | 1500 hour inspection. |  |  |  | 0 | P | N | N
7 | 18258 | AMA | ELLIS 3 | 6 | 1500 HR INSPECTION | 2002-02-04 09:00 | 2002-02-04 12:00 | 0.1 |  | OPS |  | 4.2 | 0.5 | 1500 hour inspection |  |  |  | 0 | P | N | N
8 | 18261 | AMA | HEMPHILL 2 | ANNUAL ESD | ANNUAL ESD | 2002-09-10 08:00 | 2002-09-10 16:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
9 | 18260 | AMA | HEMPHILL 3 | ANNUAL ESD | ANNUAL ESD | 2002-09-09 08:00 | 2002-09-09 16:00 | 0.3 |  | OPS |  | 1.4 | 0.5 | Annual ESD. |  |  |  | 0 | P | N | N
10 | 18264 | AMA | HEMPHILL 4 | ALL | ANNUAL ESD | 2002-09-12 08:00 | 2002-09-12 09:00 | 0 |  | OPS |  | 1.4 | 0.1 | Annual ESD. |  |  |  | 0 | P | N | N
11 | 17016 | AMA | ROGER MILLS | 5 | MECHNICAL FAILURE | 2001-09-19 16:00 | 2002-03-30 16:00 | 192 |  | OPS |  | 0 | 0 | They had a mechnical failure on unit #5. Not sure of the exact completion. (Completion date moved into March 2002). |  | 2001-09-19 16:00 |  | 0 | U | N | N
12 | 18238 | AMA | SUNRAY | 4 | RH 3&4 CYLINDER | 2001-11-30 08:00 | 2002-06-01 16:00 | 183.3 |  | OPS |  | 0 | 0 | The rings are out on the RH 3&4 cylinder. (Waiting for clearence to overhaul unit). |  | 2001-11-30 08:00 |  | 0 | U | N | N
13 | 18239 | AMA | SUNRAY | 5 | CRACKED HEAD | 2001-12-22 08:00 | 2002-06-03 16:00 | 163.3 |  | OPS |  | 0 | 0 | LH #3 head is cracked- It will require a complete overhaul on the LH side. (This work is subject to approval). |  | 2001-12-22 08:00 |  | 0 | U | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 22, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18245 | AMA | BEAVER 6 | 2 | 1500 HR. INSPECTION | 2002-02-20 10:00 | 2002-02-20 13:00 | 0.1 |  | OPS |  | 5 | 0.6 | 1500 hour inspection. |  |  |  | 0 | P | N | N
2 | 18262 | AMA | CANADIAN | 1 & 3 | REFLIEF VALVE TEST | 2002-03-12 08:00 | 2002-03-12 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual relief valve test. Station will be shut down. |  |  |  | 0 | P | N | N
3 | 18263 | AMA | CANADIAN | 1 & 3 | ANNUAL ESD | 2002-09-11 08:00 | 2002-09-11 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual ESD. |  |  |  | 0 | P | N | N
4 | 18247 | AMA | ELLIS 1 | 1 | 1500 HR. INSPECTION | 2002-02-12 09:00 | 2002-02-12 16:00 | 0.3 |  | OPS |  | 3 | 0.9 | 1500 hour inspection. |  |  |  | 0 | P | N | N
5 | 18248 | AMA | ELLIS 1 | 3 | 1500 HR. INSPECTION | 2002-02-13 09:00 | 2002-02-13 11:00 | 0.1 |  | OPS |  | 3 | 0.3 | 1500 hour inspection. |  |  |  | 0 | P | N | N
6 | 18249 | AMA | ELLIS 1 | 4 | 1500 HR. INSPECTION | 2002-02-14 09:00 | 2002-02-14 12:00 | 0.1 |  | OPS |  | 7 | 0.9 | 1500 hour inspection. |  |  |  | 0 | P | N | N
7 | 18258 | AMA | ELLIS 3 | 6 | 1500 HR INSPECTION | 2002-02-04 09:00 | 2002-02-04 12:00 | 0.1 |  | OPS |  | 4.2 | 0.5 | 1500 hour inspection |  |  |  | 0 | P | N | N
8 | 18261 | AMA | HEMPHILL 2 | ANNUAL ESD | ANNUAL ESD | 2002-09-10 08:00 | 2002-09-10 16:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
9 | 18260 | AMA | HEMPHILL 3 | ANNUAL ESD | ANNUAL ESD | 2002-09-09 08:00 | 2002-09-09 16:00 | 0.3 |  | OPS |  | 1.4 | 0.5 | Annual ESD. |  |  |  | 0 | P | N | N
10 | 18264 | AMA | HEMPHILL 4 | ALL | ANNUAL ESD | 2002-09-12 08:00 | 2002-09-12 09:00 | 0 |  | OPS |  | 1.4 | 0.1 | Annual ESD. |  |  |  | 0 | P | N | N
11 | 17016 | AMA | ROGER MILLS | 5 | MECHNICAL FAILURE | 2001-09-19 16:00 | 2002-03-30 16:00 | 192 |  | OPS |  | 0 | 0 | They had a mechnical failure on unit #5. Not sure of the exact completion. (Completion date moved into March 2002). |  | 2001-09-19 16:00 |  | 0 | U | N | N
12 | 18238 | AMA | SUNRAY | 4 | RH 3&4 CYLINDER | 2001-11-30 08:00 | 2002-06-01 16:00 | 183.3 |  | OPS |  | 0 | 0 | The rings are out on the RH 3&4 cylinder. (Waiting for clearence to overhaul unit). |  | 2001-11-30 08:00 |  | 0 | U | N | N
13 | 18239 | AMA | SUNRAY | 5 | CRACKED HEAD | 2001-12-22 08:00 | 2002-06-03 16:00 | 163.3 |  | OPS |  | 0 | 0 | LH #3 head is cracked- It will require a complete overhaul on the LH side. (This work is subject to approval). |  | 2001-12-22 08:00 |  | 0 | U | N | N