## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Minneapolis Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 22, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17153 | MIN | CARLTON | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Cooper 12-V250 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
2 | 18298 | MIN | CHATFIELD | ALL | ESD | 2002-11-08 08:00 | 2002-11-08 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
3 | 18296 | MIN | FAIRBAULT | ALL | ESD | 2002-10-09 08:00 | 2002-10-09 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
4 | 17157 | MIN | FARMINGTON | 4 | OVERHAUL | 2002-06-03 08:00 | 2002-06-28 16:00 | 25.3 |  | OPS |  | 0 | 0 | Top end overhaul on an Ingersoll Rand KVT606 based on analysis and run time hours. Unit will have heads removed inspected and rebuilt to OEM standards. |  |  |  | 0 | P | N | N
5 | 17158 | MIN | FARMINGTON | 5 | OVERHAUL | 2002-07-08 08:00 | 2002-07-26 16:00 | 18.3 |  | OPS |  | 0 | 0 | Top end overhaul on an Ingersoll Rand KVT616 based on analysis and run time hours. Unit will have heads removed inspected and rebuilt to OEM standards. |  |  |  | 0 | P | N | N
6 | 17156 | MIN | FARMINGTON | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS48 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
7 | 18190 | MIN | GARNER | LNG | BEARING FAILURE | 2001-12-04 08:00 | 2002-03-21 16:00 | 107.3 |  | OPS |  | 0 | 0 | Refrigerant compressor is down. Having some bearing problems. Working with York Techs to find the problem. They want to make sure they have all the parts on hand when they take it apart. (Completion date is tentative). |  | 2001-12-04 08:00 |  | 0 | U | N | N
8 | 18273 | MIN | HUGO | 1 | ANNUAL ESD | 2002-07-18 12:30 | 2002-07-19 14:30 | 1.1 |  | OPS |  | 0 | 0 | Annual ESD training and testing station ESD system will be tested with blowoff caps on. Need to perform routine maintenance on the 19" and will be ready for service at 14:30. |  |  |  | 0 | P | N | N
9 | 18297 | MIN | LACRESCENT | ALL | ESD | 2002-11-07 08:00 | 2002-11-07 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
10 | 18240 | MIN | NORTH BRANCH | 3 | MP2 & MAINTENANCE | 2002-01-14 07:00 | 2002-01-31 15:30 | 17.3 |  | OPS |  | 0 | 0 | MP2 - Torque anchor bolts inspect all chains and gears inspect x-heads & shoe clearance inspect bearing clearance check comp. piston clearance start air valve maintenace crank shaft deflection comp. rod run out and analyze the unit(recip. trap). |  |  |  | 0 | P | N | N
11 | 18274 | MIN | NORTH BRANCH | ALL | ANNUAL ESD | 2002-07-18 08:00 | 2002-07-25 12:00 | 7.2 |  | OPS |  | 0 | 0 | Annual ESD Training and Testing O-Rring replacement on check valves on compressor units General maintenance leak repairs etc. (Neighboring Stations may be need to carry the load while North Branch is down). |  |  |  | 0 | P | N | N
12 | 18295 | MIN | OWATONNA | ALL | ESD TEST | 2002-10-08 08:00 | 2002-10-08 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
13 | 18269 | MIN | WRENSHALL | SUCTION VALVES | REPLACE SUCTON VALVES | 2002-06-01 08:00 | 2002-08-15 16:00 | 75.3 |  | OPS |  | 0 | 0 | Replace suction valves on all LNG pumps and check valve on g-601b lng PUMP. Will not be able to Vaporize for about 10 weeks do to warming lines and replacing suction valves. |  |  |  | 0 | P | N | N
14 | 18270 | MIN | WRENSHALL | ESD | ESD TEST | 2002-06-05 07:00 | 2002-06-05 10:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD test. Will affect LNG plant only. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Minneapolis Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 22, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17153 | MIN | CARLTON | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Cooper 12-V250 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
2 | 18298 | MIN | CHATFIELD | ALL | ESD | 2002-11-08 08:00 | 2002-11-08 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
3 | 18296 | MIN | FAIRBAULT | ALL | ESD | 2002-10-09 08:00 | 2002-10-09 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
4 | 17157 | MIN | FARMINGTON | 4 | OVERHAUL | 2002-06-03 08:00 | 2002-06-28 16:00 | 25.3 |  | OPS |  | 0 | 0 | Top end overhaul on an Ingersoll Rand KVT606 based on analysis and run time hours. Unit will have heads removed inspected and rebuilt to OEM standards. |  |  |  | 0 | P | N | N
5 | 17158 | MIN | FARMINGTON | 5 | OVERHAUL | 2002-07-08 08:00 | 2002-07-26 16:00 | 18.3 |  | OPS |  | 0 | 0 | Top end overhaul on an Ingersoll Rand KVT616 based on analysis and run time hours. Unit will have heads removed inspected and rebuilt to OEM standards. |  |  |  | 0 | P | N | N
6 | 17156 | MIN | FARMINGTON | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS48 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
7 | 18190 | MIN | GARNER | LNG | BEARING FAILURE | 2001-12-04 08:00 | 2002-03-21 16:00 | 107.3 |  | OPS |  | 0 | 0 | Refrigerant compressor is down. Having some bearing problems. Working with York Techs to find the problem. They want to make sure they have all the parts on hand when they take it apart. (Completion date is tentative). |  | 2001-12-04 08:00 |  | 0 | U | N | N
8 | 18273 | MIN | HUGO | 1 | ANNUAL ESD | 2002-07-18 12:30 | 2002-07-19 14:30 | 1.1 |  | OPS |  | 0 | 0 | Annual ESD training and testing station ESD system will be tested with blowoff caps on. Need to perform routine maintenance on the 19" and will be ready for service at 14:30. |  |  |  | 0 | P | N | N
9 | 18297 | MIN | LACRESCENT | ALL | ESD | 2002-11-07 08:00 | 2002-11-07 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
10 | 18240 | MIN | NORTH BRANCH | 3 | MP2 & MAINTENANCE | 2002-01-14 07:00 | 2002-01-31 15:30 | 17.3 |  | OPS |  | 0 | 0 | MP2 - Torque anchor bolts inspect all chains and gears inspect x-heads & shoe clearance inspect bearing clearance check comp. piston clearance start air valve maintenace crank shaft deflection comp. rod run out and analyze the unit(recip. trap). |  |  |  | 0 | P | N | N
11 | 18274 | MIN | NORTH BRANCH | ALL | ANNUAL ESD | 2002-07-18 08:00 | 2002-07-25 12:00 | 7.2 |  | OPS |  | 0 | 0 | Annual ESD Training and Testing O-Rring replacement on check valves on compressor units General maintenance leak repairs etc. (Neighboring Stations may be need to carry the load while North Branch is down). |  |  |  | 0 | P | N | N
12 | 18295 | MIN | OWATONNA | ALL | ESD TEST | 2002-10-08 08:00 | 2002-10-08 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
13 | 18269 | MIN | WRENSHALL | SUCTION VALVES | REPLACE SUCTON VALVES | 2002-06-01 08:00 | 2002-08-15 16:00 | 75.3 |  | OPS |  | 0 | 0 | Replace suction valves on all LNG pumps and check valve on g-601b lng PUMP. Will not be able to Vaporize for about 10 weeks do to warming lines and replacing suction valves. |  |  |  | 0 | P | N | N
14 | 18270 | MIN | WRENSHALL | ESD | ESD TEST | 2002-06-05 07:00 | 2002-06-05 10:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD test. Will affect LNG plant only. |  |  |  | 0 | P | N | N