## 012502Bu
PLANNED AND UNPLANNED OUTAGES AFFECTING THE BUSHTON UNIVERSE.
2002-01-25
The information provided is tentative and may be changed without further notice. Northern Natural Gas Transwestern and Florida Gas Transmission are not responsible for any reliance on this information.
# | Region | Location | Units | Title | EstStart | EstComp | Dur (Days) | Est Flow Affected | Est Thru Affected | DescOfWork | ActStart | ActComp | Act Flow Affected | Planned Unplanned
18245 | AMA | BEAVER 6 | 2 | 1500 HR. INSPECTION | 2002-02-20 10:00 | 2002-02-20 13:00 | 0.1 | 5 | 0.6 | 1500 hour inspection. |  |  | 0 | P
18247 | AMA | ELLIS 1 | 1 | 1500 HR. INSPECTION | 2002-02-12 09:00 | 2002-02-12 16:00 | 0.3 | 3 | 0.9 | 1500 hour inspection. |  |  | 0 | P
18248 | AMA | ELLIS 1 | 3 | 1500 HR. INSPECTION | 2002-02-13 09:00 | 2002-02-13 11:00 | 0.1 | 3 | 0.3 | 1500 hour inspection. |  |  | 0 | P
18249 | AMA | ELLIS 1 | 4 | 1500 HR. INSPECTION | 2002-02-14 09:00 | 2002-02-14 12:00 | 0.1 | 7 | 0.9 | 1500 hour inspection. |  |  | 0 | P
18258 | AMA | ELLIS 3 | 6 | 1500 HR INSPECTION | 2002-02-04 09:00 | 2002-02-04 12:00 | 0.1 | 4.2 | 0.5 | 1500 hour inspection |  |  | 0 | P
17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P
17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P
17154 | BEA | CUNNINGHAM | 5 | OVERHAUL | 2002-04-01 07:00 | 2002-04-22 15:30 | 21.3 | 0 | 0 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (Flow affect will depends the needs on the pipeline). Unit pumps about 75 mmcfd. |  |  | 0 | P
18307 | LIB | CLARK 2 | 2 | FIN-FAN BEARING | 2002-01-13 19:00 | 2002-01-18 16:00 | 4.9 | 0 | 0 | Changing Fin-Fan Bearing. Put on unit 1 & 7. (No flow affect). | 2002-01-13 19:00 |  | 0 | U
18001 | LIB | FINNEY 2 | 1 | MAINTENANCE | 2002-02-05 09:00 | 2002-02-05 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18012 | LIB | FINNEY 2 | 1 | MAINTENANCE | 2002-03-05 08:00 | 2002-03-07 16:00 | 2.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18003 | LIB | FINNEY 2 | 2 | MAINTENANCE | 2002-02-07 09:00 | 2002-02-07 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18013 | LIB | FINNEY 2 | 2 | MAINTENANCE | 2002-03-07 08:00 | 2002-03-08 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18005 | LIB | FINNEY 2 | 3 | MAINTENANCE | 2002-02-12 09:00 | 2002-02-12 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18014 | LIB | FINNEY 2 | 3 | MAINTENANCE | 2002-03-12 08:00 | 2002-03-13 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18006 | LIB | FINNEY 2 | 5 | MAINTENANCE | 2002-02-14 09:00 | 2002-02-14 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18016 | LIB | FINNEY 2 | 5 | MAINTENANCE | 2002-03-18 08:00 | 2002-03-18 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18007 | LIB | FINNEY 2 | 6 | MAINTENANCE | 2002-02-19 09:00 | 2002-02-19 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18017 | LIB | FINNEY 2 | 6 | MAINTENANCE | 2002-03-19 08:00 | 2002-03-20 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18008 | LIB | FINNEY 2 | 7 | MAINTENANCE | 2002-02-21 09:00 | 2002-02-21 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18018 | LIB | FINNEY 2 | 7 | MAINTENANCE | 2002-03-21 08:00 | 2002-03-22 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17999 | LIB | FINNEY 2 | 8 | MAINTENANCE | 2002-01-24 09:00 | 2002-01-24 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18009 | LIB | FINNEY 2 | 8 | MAINTENANCE | 2002-02-26 09:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18019 | LIB | FINNEY 2 | 8 | MAINTENANCE | 2002-03-26 08:00 | 2002-03-27 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18000 | LIB | FINNEY 2 | 9 | MAINTENANCE | 2002-01-29 09:00 | 2002-01-29 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18010 | LIB | FINNEY 2 | 9 | MAINTENANCE | 2002-02-28 09:00 | 2002-02-28 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18020 | LIB | FINNEY 2 | 9 | MAINTENANCE | 2002-03-28 08:00 | 2002-03-29 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18004 | LIB | FINNEY 3 | 1 | MAINTENANCE | 2002-02-08 09:00 | 2002-02-08 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18047 | LIB | FINNEY 3 | 1 | MAINTENANCE | 2002-12-06 08:00 | 2002-12-06 16:00 | 0.3 | 0 | 0 | Scheduled maintenance - work orders & DET list. |  |  | 0 | P
18002 | LIB | FINNEY 3 | 3 | MAINTENANCE | 2002-02-05 09:00 | 2002-02-05 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18015 | LIB | FINNEY 3 | 3 | MAINTENANCE | 2002-03-14 09:00 | 2002-03-14 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17698 | LIB | FINNEY 4 | 1 | BEARING SENSOR | 2001-10-05 14:00 | 2002-06-30 16:30 | 268.1 | 0 | 0 | Lost main bearing sensor. Pulled doors off to check sensor and found metal in crankcase. Drained oil and located problem. Unit will have to be re-worked. | 2001-10-05 14:00 |  | 0 | U
18011 | LIB | FINNEY 4 | 1 | MAINTENANCE | 2002-02-28 08:00 | 2002-02-28 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17837 | LIB | HOLCOMB | 1 | ANNUAL MAINTENANCE | 2002-01-23 08:00 | 2002-01-24 16:00 | 1.3 | 6 | 8 | Doing their annual maintenance. (This unit pumps Holcomb South) |  |  | 0 | P
17838 | LIB | HOLCOMB | 2 | ANNUAL MAINTENANCE | 2002-02-15 08:00 | 2002-02-16 16:00 | 1.3 | 6 | 8 | Annual maintenance. (This unit pumps Holcomb South). |  |  | 0 | P
17836 | LIB | HOLCOMB | 10 | REPLACE PISTONS & RINGS | 2002-05-01 08:00 | 2002-05-31 16:00 | 30.3 | 0 | 0 | Replace pistons and rings overhaul 2 & 3 compressors. |  |  | 0 | P
17839 | LIB | HOLCOMB | ESD | ANNUAL ESD | 2002-05-14 08:00 | 2002-05-16 16:00 | 2.3 | 135 | 315 | Annual ESD and maintenance. |  |  | 0 | P
17840 | LIB | HOLCOMB | HOLCOMB SOUTH | ESD | 2002-05-14 08:00 | 2002-05-16 16:00 | 2.3 | 0 | 0 | Outage coordinated with Holcomb's Annual ESD. |  |  | 0 | P
18314 | LIB | HUGOTON | 16 | SERVICE & MAINTENANCE | 2002-10-08 08:00 | 2002-10-08 16:00 | 0.3 | 12 | 4 | Service and maintenance. |  |  | 0 | P
18102 | LIB | HUGOTON | 17 | SERVICE | 2002-10-15 08:00 | 2002-10-15 14:00 | 0.3 | 3 | 0.8 | Service and maintenance. 1800 HP |  |  | 0 | P
18089 | LIB | HUGOTON | ALL | ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 100 | 233.3 | Planned ESD. |  |  | 0 | P
17634 | LIB | MORTON 1 | 3 | MP2 | 2002-07-08 07:30 | 2002-07-26 16:00 | 18.4 | 0 | 0 | MP2 8 000 hour inspection. |  |  | 0 | P
17644 | LIB | MORTON 1 | 3 | CONTROLS PM | 2002-12-02 07:30 | 2002-12-06 16:00 | 4.4 | 0 | 0 | Controls PM |  |  | 0 | P
17630 | LIB | MORTON 1 | 4 | MP2 | 2002-06-10 07:30 | 2002-06-21 16:00 | 11.4 | 0 | 0 | MP2 8 000 hr inspection |  |  | 0 | P
17645 | LIB | MORTON 1 | 4 | CONTROLS PM | 2002-12-09 07:30 | 2002-12-11 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17614 | LIB | MORTON 1 | 5 | CONTROLS PM | 2002-01-22 07:30 | 2002-01-24 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17615 | LIB | MORTON 1 | 6 | CONTROLS PM | 2002-01-24 07:30 | 2002-01-25 16:00 | 1.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17616 | LIB | MORTON 1 | 7 | CONTROLS PM | 2002-02-04 07:30 | 2002-02-06 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17639 | LIB | MORTON 1 | 8 | CONTROLS PM | 2002-09-05 07:30 | 2002-09-07 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17641 | LIB | MORTON 1 | 9 | CONTROLS PM | 2002-09-12 07:30 | 2002-09-14 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17617 | LIB | MORTON 1 | 10 | CONTROLS PM | 2002-02-11 07:30 | 2002-02-15 16:00 | 4.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17640 | LIB | MORTON 1 | 10 | MP2 | 2002-09-05 07:30 | 2002-09-23 16:00 | 18.4 | 0 | 0 | MP2 8 000 hour inspection |  |  | 0 | P
17637 | LIB | MORTON 1 | 11 | CONTROLS PM | 2002-08-12 07:30 | 2002-08-16 16:00 | 4.4 | 0 | 0 | Controls PM |  |  | 0 | P
17638 | LIB | MORTON 1 | 12 | CONTROLS PM | 2002-08-19 07:30 | 2002-08-23 16:00 | 4.4 | 0 | 0 | Controls PM |  |  | 0 | P
17622 | LIB | MORTON 1 | ALL | ANNUAL ESD | 2002-05-06 07:30 | 2002-05-11 16:00 | 5.4 | 18 | 96.8 | Annual ESD. |  |  | 0 | P
17626 | LIB | MORTON 6 | 1 | MP 2 | 2002-05-13 07:30 | 2002-05-24 16:00 | 11.4 | 4 | 45.5 | MP2 8 000 hour inspect. |  |  | 0 | P
17642 | LIB | MORTON 6 | 1 | CONTROLS PM | 2002-10-07 07:30 | 2002-10-09 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17628 | LIB | MORTON 6 | 2 | MP2 | 2002-05-28 07:30 | 2002-06-07 16:00 | 10.4 | 4 | 41.5 | MP2 8 000 hr inspection |  |  | 0 | P
17643 | LIB | MORTON 6 | 2 | CONTROLS PM | 2002-10-14 07:30 | 2002-10-16 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17623 | LIB | MORTON 6 | ALL | ANNUAL ESD | 2002-05-06 07:30 | 2002-05-11 16:00 | 5.4 | 18 | 96.8 | Annual ESD. |  |  | 0 | P
18312 | LIB | MULLINVILLE | 19 | REPLACE ROD BEARING | 2002-01-16 14:00 | 2002-02-08 16:00 | 23.1 | 0 | 0 | Will remove bearing and inspect crank shaft. | 2002-01-16 14:00 |  | 0 | U
18343 | LIB | MULLINVILLE | 23 | WARRENTY WORK | 2002-01-28 08:00 | 2002-01-29 16:00 | 1.3 | 0 | 0 | Exline is doing some warrenty work on the ignition system. |  |  | 0 | U
18342 | LIB | MULLINVILLE | 24 | WARRENTY WORK | 2002-01-25 08:00 | 2002-01-26 16:00 | 1.3 | 0 | 0 | Exline is doing some warrenty work on the ignition system. | 2002-01-25 08:00 |  | 0 | U
18069 | LIB | STEVENS 1 | 1 | MAINTENANCE | 2002-02-05 07:30 | 2002-02-06 16:00 | 1.4 | 0 | 0 | Service unit and MP2 tasks. |  |  | 0 | P
17765 | LIB | STEVENS 1 | 1 | PMS | 2002-02-05 08:00 | 2002-02-06 16:00 | 1.3 | 0 | 0 | Pm scheduled work. |  |  | 0 | P
18071 | LIB | STEVENS 1 | 2 | MAINTENANCE | 2002-03-05 07:30 | 2002-03-06 16:00 | 1.4 | 0 | 0 | Service unit and MP2 tasks. |  |  | 0 | P
17766 | LIB | STEVENS 1 | 2 | PMS | 2002-03-05 08:00 | 2002-03-06 16:00 | 1.3 | 0 | 0 | PM scheduled work. |  |  | 0 | P
18070 | LIB | STEVENS 1 | 4 | MAINTENANCE | 2002-02-20 07:30 | 2002-02-20 16:00 | 0.4 | 0 | 0 | Service unit and MP2 tasks. |  |  | 0 | P
18072 | LIB | STEVENS 1 | 6 | MAINTENANCE | 2002-03-19 07:30 | 2002-03-20 16:00 | 1.4 | 0 | 0 | Service unit and MP2 tasks. |  |  | 0 | P
17767 | LIB | STEVENS 1 | 6 | PMS | 2002-03-19 08:00 | 2002-03-20 16:00 | 1.3 | 0 | 0 | PM scheduled work. |  |  | 0 | P
18068 | LIB | STEVENS 1 | 7 | MAINTENANCE | 2002-01-23 07:30 | 2002-01-23 16:00 | 0.4 | 0 | 0 | Service unit and MP2 tasks. |  |  | 0 | P
18073 | LIB | STEVENS 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-09 16:00 | 2.4 | 0 | 0 | Annual ESD. |  |  | 0 | P
17801 | LIB | STEVENS 2 | 3 | MP2 | 2002-01-24 08:00 | 2002-01-24 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17802 | LIB | STEVENS 2 | 3 | MP2 | 2002-02-06 08:00 | 2002-02-06 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17771 | LIB | STEVENS 2 | 3 | SERVICE | 2002-03-14 08:00 | 2002-03-14 16:00 | 0.3 | 0 | 0 | Service Unit 1324 HP |  |  | 0 | P
17803 | LIB | STEVENS 2 | 3 | MP2 | 2002-04-02 08:00 | 2002-04-02 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17804 | LIB | STEVENS 2 | 3 | MP2 | 2002-05-07 08:00 | 2002-05-07 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17805 | LIB | STEVENS 2 | 3 | MP2 | 2002-06-05 08:00 | 2002-06-05 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17806 | LIB | STEVENS 2 | 3 | MP2 | 2002-07-24 08:00 | 2002-07-24 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17807 | LIB | STEVENS 2 | 3 | MP2 | 2002-08-14 08:00 | 2002-08-14 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17772 | LIB | STEVENS 2 | 3 | SERVICE | 2002-09-03 08:00 | 2002-09-03 16:00 | 0.3 | 0 | 0 | Service unit 1324 HP |  |  | 0 | P
17808 | LIB | STEVENS 2 | 3 | MP2 | 2002-10-08 08:00 | 2002-10-08 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17809 | LIB | STEVENS 2 | 3 | MP2 | 2002-11-13 08:00 | 2002-11-13 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17773 | LIB | STEVENS 2 | 3 | SERVICE | 2002-12-04 08:00 | 2002-12-04 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 1324 HP |  |  | 0 | P
18241 | LIB | STEVENS 2 | 6 | REPLACE POWER CYLINDER | 2002-01-02 08:00 | 2002-02-01 16:00 | 30.3 | 0 | 0 | Unit #6 has a power cylinder leaking water into the crankcase. Will have to replace the power cylinder. MP2 | 2002-01-02 08:00 |  | 0 | U
17811 | LIB | STEVENS 2 | 6 | MP2 | 2002-02-07 08:00 | 2002-02-07 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17774 | LIB | STEVENS 2 | 6 | SERVICE | 2002-03-06 08:00 | 2002-03-06 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM 1234 HP |  |  | 0 | P
17812 | LIB | STEVENS 2 | 6 | MP2 | 2002-04-03 08:00 | 2002-04-03 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17813 | LIB | STEVENS 2 | 6 | MP2 | 2002-05-08 08:00 | 2002-05-08 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17814 | LIB | STEVENS 2 | 6 | MP2 | 2002-06-06 08:00 | 2002-06-06 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17815 | LIB | STEVENS 2 | 6 | MP2 | 2002-07-25 08:00 | 2002-07-25 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17775 | LIB | STEVENS 2 | 6 | SERVICE | 2002-08-13 08:00 | 2002-08-13 16:00 | 0.3 | 0 | 0 | Service unit. 1234 HP |  |  | 0 | P
17816 | LIB | STEVENS 2 | 6 | MP2 | 2002-09-18 08:00 | 2002-09-18 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17817 | LIB | STEVENS 2 | 6 | MP2 | 2002-10-09 08:00 | 2002-10-09 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17776 | LIB | STEVENS 2 | 6 | SERVICE | 2002-11-14 08:00 | 2002-11-14 16:00 | 0.3 | 0 | 0 | Service unit. 1234 HP |  |  | 0 | P
17818 | LIB | STEVENS 2 | 6 | MP2 | 2002-12-03 08:00 | 2002-12-03 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17819 | LIB | STEVENS 2 | 7 | MP2 | 2002-01-24 08:00 | 2002-01-24 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 586 HP |  |  | 0 | P
17830 | LIB | STEVENS 2 | 7 | CHECK VALVES | 2002-01-28 08:00 | 2002-01-28 16:00 | 0.3 | 0 | 0 | Repairing check valve leaks. |  |  | 0 | P
17777 | LIB | STEVENS 2 | 7 | SERVICE | 2002-02-05 08:00 | 2002-02-05 16:00 | 0.3 | 0 | 0 | Service unit. 1234 HP |  |  | 0 | P
17820 | LIB | STEVENS 2 | 7 | MP2 | 2002-03-19 08:00 | 2002-03-19 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 586 HP |  |  | 0 | P
17778 | LIB | STEVENS 2 | 7 | SERVICE | 2002-04-09 08:00 | 2002-04-09 16:00 | 0.3 | 0 | 0 | Service unit. 1234 HP |  |  | 0 | P
17821 | LIB | STEVENS 2 | 7 | MP2 | 2002-05-09 08:00 | 2002-05-09 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 586 HP |  |  | 0 | P
17779 | LIB | STEVENS 2 | 7 | SERVICE | 2002-06-11 08:00 | 2002-06-11 16:00 | 0.3 | 0 | 0 | Service unit. 1234 HP |  |  | 0 | P
17780 | LIB | STEVENS 2 | 7 | SERVICE | 2002-07-23 08:00 | 2002-07-23 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 1234 HP |  |  | 0 | P
17822 | LIB | STEVENS 2 | 7 | MP2 | 2002-08-15 08:00 | 2002-08-15 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 586 HP |  |  | 0 | P
17781 | LIB | STEVENS 2 | 7 | SERVICE | 2002-09-17 08:00 | 2002-09-17 16:00 | 0.3 | 0 | 0 | Service unit 586 HP |  |  | 0 | P
17823 | LIB | STEVENS 2 | 7 | MP2 | 2002-10-10 08:00 | 2002-10-10 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 586 HP |  |  | 0 | P
17782 | LIB | STEVENS 2 | 7 | SERVICE | 2002-11-12 08:00 | 2002-11-12 16:00 | 0.3 | 0 | 0 | Service unit. 586 HP |  |  | 0 | P
17825 | LIB | STEVENS 2 | 7 | MP2 | 2002-12-17 08:00 | 2002-12-17 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 586 HP |  |  | 0 | P
17783 | LIB | STEVENS 2 | 8 | SERVICE | 2002-01-29 08:00 | 2002-01-29 16:00 | 0.3 | 0 | 0 | Service unit. 764 HP |  |  | 0 | P
17828 | LIB | STEVENS 2 | 8 | MP2 | 2002-02-14 08:00 | 2002-02-14 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 764 HP |  |  | 0 | P
17784 | LIB | STEVENS 2 | 8 | SERVICE | 2002-03-05 08:00 | 2002-03-05 16:00 | 0.3 | 0 | 0 | Service unit. 764 HP |  |  | 0 | P
17829 | LIB | STEVENS 2 | 8 | MP2 | 2002-04-04 08:00 | 2002-04-04 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 764 HP |  |  | 0 | P
17831 | LIB | STEVENS 2 | 8 | MP2 | 2002-05-21 08:00 | 2002-05-21 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 764 HP |  |  | 0 | P
17785 | LIB | STEVENS 2 | 8 | SERVICE | 2002-06-04 08:00 | 2002-06-04 16:00 | 0.3 | 0 | 0 | Service unit. 764 HP |  |  | 0 | P
17786 | LIB | STEVENS 2 | 8 | SERVICE | 2002-07-02 08:00 | 2002-07-02 16:00 | 0.3 | 0 | 0 | Service unit. 764 HP |  |  | 0 | P
17832 | LIB | STEVENS 2 | 8 | MP2 | 2002-08-20 08:00 | 2002-08-20 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 764 HP |  |  | 0 | P
17787 | LIB | STEVENS 2 | 8 | SERVICE | 2002-09-15 08:00 | 2002-09-15 16:00 | 0.3 | 0 | 0 | Service unit. 764 HP |  |  | 0 | P
17833 | LIB | STEVENS 2 | 8 | MP2 | 2002-10-22 08:00 | 2002-10-22 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 764 HP |  |  | 0 | P
17834 | LIB | STEVENS 2 | 8 | MP2 | 2002-11-19 08:00 | 2002-11-19 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 764 HP |  |  | 0 | P
17788 | LIB | STEVENS 2 | 8 | SERVICE | 2002-12-05 08:00 | 2002-12-05 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 764 HP |  |  | 0 | P
17790 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-02-11 08:00 | 2002-02-13 16:00 | 2.3 | 0 | 0 | Service Unit & MP2 Tasks. 375 HP |  |  | 0 | P
17791 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-03-07 08:00 | 2002-03-13 16:00 | 6.3 | 0 | 0 | Service units plus panel S/D & PM. 375 HP |  |  | 0 | P
17792 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-04-10 08:00 | 2002-04-16 16:00 | 6.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17793 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-05-13 08:00 | 2002-05-15 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17794 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-06-17 08:00 | 2002-06-19 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17795 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-07-09 08:00 | 2002-07-11 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17796 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-08-06 08:00 | 2002-08-08 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17797 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-09-09 08:00 | 2002-09-11 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17798 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-10-15 08:00 | 2002-10-17 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17799 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-11-05 08:00 | 2002-11-07 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17800 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-12-10 08:00 | 2002-12-12 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17842 | LIB | STEVENS 2 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 0 | 0 | Annual ESD |  |  | 0 | P
17843 | LIB | STEVENS 3 | 1 | SERVICE | 2002-02-05 08:00 | 2002-02-06 16:00 | 1.3 | 0 | 0 | Service unit plus panel S/D & PM MP2 Tasks. 1064 HP |  |  | 0 | P
17853 | LIB | STEVENS 3 | 1 | MP2 | 2002-03-26 08:00 | 2002-03-26 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17854 | LIB | STEVENS 3 | 1 | MP2 | 2002-04-23 08:00 | 2002-04-23 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17855 | LIB | STEVENS 3 | 1 | MP2 | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17844 | LIB | STEVENS 3 | 1 | SERVICE | 2002-06-04 08:00 | 2002-06-05 16:00 | 1.3 | 0 | 0 | Service & MP2 Tasks. 1064 HP |  |  | 0 | P
17856 | LIB | STEVENS 3 | 1 | MP2 | 2002-07-30 08:00 | 2002-07-30 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17857 | LIB | STEVENS 3 | 1 | MP2 | 2002-08-20 08:00 | 2002-08-20 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17858 | LIB | STEVENS 3 | 1 | MP2 | 2002-09-24 08:00 | 2002-09-24 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17845 | LIB | STEVENS 3 | 1 | SERVICE | 2002-10-08 08:00 | 2002-10-09 16:00 | 1.3 | 0 | 0 | Service & MP2 Tasks. 1064 HP |  |  | 0 | P
17859 | LIB | STEVENS 3 | 1 | MP2 | 2002-11-20 08:00 | 2002-11-20 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17860 | LIB | STEVENS 3 | 1 | MP2 | 2002-12-17 08:00 | 2002-12-17 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17861 | LIB | STEVENS 3 | 3 | MP2 | 2002-01-29 08:00 | 2002-01-29 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17862 | LIB | STEVENS 3 | 3 | MP2 | 2002-02-26 08:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17846 | LIB | STEVENS 3 | 3 | SERVICE | 2002-03-12 08:00 | 2002-03-13 16:00 | 1.3 | 0 | 0 | Service unit plus panel S/D & PM MP2 Tasks. 1100 HP |  |  | 0 | P
17863 | LIB | STEVENS 3 | 3 | MP2 | 2002-04-24 08:00 | 2002-04-24 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17864 | LIB | STEVENS 3 | 3 | MP2 | 2002-05-28 08:00 | 2002-05-28 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17865 | LIB | STEVENS 3 | 3 | MP2 | 2002-06-19 08:00 | 2002-06-19 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17847 | LIB | STEVENS 3 | 3 | SERVICE | 2002-07-23 08:00 | 2002-07-24 16:00 | 1.3 | 0 | 0 | Service unit MP2 Tasks. 1100 HP |  |  | 0 | P
17866 | LIB | STEVENS 3 | 3 | MP2 | 2002-08-27 08:00 | 2002-08-27 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17867 | LIB | STEVENS 3 | 3 | MP2 | 2002-09-11 08:00 | 2002-09-11 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17868 | LIB | STEVENS 3 | 3 | MP2 | 2002-10-29 08:00 | 2002-10-29 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17848 | LIB | STEVENS 3 | 3 | SERVICE | 2002-11-12 08:00 | 2002-11-13 16:00 | 1.3 | 0 | 0 | Service unit MP2 Tasks. 1100 HP |  |  | 0 | P
17869 | LIB | STEVENS 3 | 3 | MP2 | 2002-12-04 08:00 | 2002-12-04 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17871 | LIB | STEVENS 3 | 4 | MP2 | 2002-02-19 08:00 | 2002-02-19 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17849 | LIB | STEVENS 3 | 4 | SERVICE | 2002-03-19 08:00 | 2002-03-20 16:00 | 1.3 | 0 | 0 | Service unit plus panel S/D & PM MP2 Tasks. 1600 HP |  |  | 0 | P
17872 | LIB | STEVENS 3 | 4 | MP2 | 2002-04-16 08:00 | 2002-04-16 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17873 | LIB | STEVENS 3 | 4 | MP2 | 2002-05-29 08:00 | 2002-05-29 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17874 | LIB | STEVENS 3 | 4 | MP2 | 2002-06-12 08:00 | 2002-06-12 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17850 | LIB | STEVENS 3 | 4 | SERVICE | 2002-07-16 08:00 | 2002-07-17 16:00 | 1.3 | 0 | 0 | Service unit MP2 Tasks. 1600 HP |  |  | 0 | P
17875 | LIB | STEVENS 3 | 4 | MP2 | 2002-08-28 08:00 | 2002-08-28 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17876 | LIB | STEVENS 3 | 4 | MP2 | 2002-09-18 08:00 | 2002-09-18 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17851 | LIB | STEVENS 3 | 4 | SERVICE | 2002-10-15 08:00 | 2002-10-16 16:00 | 1.3 | 0 | 0 | Service unit MP2 Tasks. 1600 HP |  |  | 0 | P
17877 | LIB | STEVENS 3 | 4 | MP2 | 2002-11-19 08:00 | 2002-11-19 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17878 | LIB | STEVENS 3 | 4 | MP2 | 2002-12-11 08:00 | 2002-12-11 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17896 | LIB | STEVENS 4 | 1 | MP2 | 2002-02-13 08:00 | 2002-02-13 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17897 | LIB | STEVENS 4 | 1 | MP2 | 2002-03-20 08:00 | 2002-03-20 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17898 | LIB | STEVENS 4 | 1 | MP2 | 2002-04-17 08:00 | 2002-04-17 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17880 | LIB | STEVENS 4 | 1 | SERVICE | 2002-05-09 08:00 | 2002-05-10 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17899 | LIB | STEVENS 4 | 1 | MP2 | 2002-06-19 08:00 | 2002-06-19 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17900 | LIB | STEVENS 4 | 1 | MP2 | 2002-07-17 08:00 | 2002-07-17 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17901 | LIB | STEVENS 4 | 1 | MP2 | 2002-08-14 08:00 | 2002-08-14 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17881 | LIB | STEVENS 4 | 1 | SERVICE | 2002-09-11 08:00 | 2002-09-12 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17902 | LIB | STEVENS 4 | 1 | MP2 | 2002-10-16 08:00 | 2002-10-16 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17882 | LIB | STEVENS 4 | 1 | SERVICE | 2002-11-05 08:00 | 2002-11-06 16:00 | 1.3 | 0 | 0 | Panel S/D & PM MP 2. |  |  | 0 | P
17903 | LIB | STEVENS 4 | 1 | MP2 | 2002-12-11 08:00 | 2002-12-11 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17905 | LIB | STEVENS 4 | 2 | MP2 | 2002-02-21 08:00 | 2002-02-21 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17883 | LIB | STEVENS 4 | 2 | SERVICE | 2002-03-13 08:00 | 2002-03-14 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17906 | LIB | STEVENS 4 | 2 | MP2 | 2002-04-18 08:00 | 2002-04-18 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17907 | LIB | STEVENS 4 | 2 | MP2 | 2002-05-23 08:00 | 2002-05-23 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17908 | LIB | STEVENS 4 | 2 | MP2 | 2002-06-20 08:00 | 2002-06-20 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17884 | LIB | STEVENS 4 | 2 | SERVICE | 2002-07-10 08:00 | 2002-07-11 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17909 | LIB | STEVENS 4 | 2 | MP2 | 2002-08-15 08:00 | 2002-08-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17910 | LIB | STEVENS 4 | 2 | MP2 | 2002-09-26 08:00 | 2002-09-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17911 | LIB | STEVENS 4 | 2 | MP2 | 2002-10-17 08:00 | 2002-10-17 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17885 | LIB | STEVENS 4 | 2 | SERVICE | 2002-11-13 08:00 | 2002-11-14 16:00 | 1.3 | 0 | 0 | Service unit panel S/D & MP 2. |  |  | 0 | P
17912 | LIB | STEVENS 4 | 2 | MP2 | 2002-12-12 08:00 | 2002-12-12 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17886 | LIB | STEVENS 4 | 3 | SERVICE | 2002-02-20 08:00 | 2002-02-20 16:00 | 0.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17914 | LIB | STEVENS 4 | 3 | MP2 | 2002-03-22 08:00 | 2002-03-22 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17915 | LIB | STEVENS 4 | 3 | MP2 | 2002-04-19 08:00 | 2002-04-19 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17916 | LIB | STEVENS 4 | 3 | MP2 | 2002-05-21 08:00 | 2002-05-21 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17887 | LIB | STEVENS 4 | 3 | SERVICE | 2002-06-12 08:00 | 2002-06-12 16:00 | 0.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17917 | LIB | STEVENS 4 | 3 | MP2 | 2002-07-19 08:00 | 2002-07-19 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17918 | LIB | STEVENS 4 | 3 | MP2 | 2002-08-16 08:00 | 2002-08-16 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17919 | LIB | STEVENS 4 | 3 | MP2 | 2002-09-27 08:00 | 2002-09-27 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17888 | LIB | STEVENS 4 | 3 | SERVICE | 2002-10-09 08:00 | 2002-10-09 16:00 | 0.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17889 | LIB | STEVENS 4 | 3 | SERVICE | 2002-11-06 08:00 | 2002-11-06 16:00 | 0.3 | 0 | 0 | Panel S/D & MP 2. |  |  | 0 | P
17920 | LIB | STEVENS 4 | 3 | MP2 | 2002-12-10 08:00 | 2002-12-10 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17921 | LIB | STEVENS 4 | 4 | MP2 | 2002-02-18 08:00 | 2002-02-18 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17922 | LIB | STEVENS 4 | 4 | MP2 | 2002-03-26 08:00 | 2002-03-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17923 | LIB | STEVENS 4 | 4 | MP2 | 2002-04-22 08:00 | 2002-04-22 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17891 | LIB | STEVENS 4 | 4 | SERVICE | 2002-05-15 08:00 | 2002-05-16 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17892 | LIB | STEVENS 4 | 4 | OVERHAUL | 2002-06-01 08:00 | 2002-07-01 16:00 | 30.3 | 0 | 0 | Comp. & engine overhaul. |  |  | 0 | P
17924 | LIB | STEVENS 4 | 4 | MP2 | 2002-06-25 08:00 | 2002-06-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17925 | LIB | STEVENS 4 | 4 | MP2 | 2002-07-16 08:00 | 2002-07-16 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17926 | LIB | STEVENS 4 | 4 | MP2 | 2002-08-13 08:00 | 2002-08-13 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17893 | LIB | STEVENS 4 | 4 | SERVICE | 2002-09-18 08:00 | 2002-09-19 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17927 | LIB | STEVENS 4 | 4 | MP2 | 2002-10-15 08:00 | 2002-10-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17894 | LIB | STEVENS 4 | 4 | SERVICE | 2002-11-15 08:00 | 2002-11-15 16:00 | 0.3 | 0 | 0 | Panel S/D & MP 2. |  |  | 0 | P
17928 | LIB | STEVENS 4 | 4 | MP2 | 2002-12-09 08:00 | 2002-12-09 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17895 | LIB | STEVENS 4 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 0 | 0 | Annual ESD. |  |  | 0 | P
17763 | LIB | STEVENS 6 | 3 | PMS | 2002-01-30 08:00 | 2002-01-30 16:00 | 0.3 | 0 | 0 | PM scheduled work. |  |  | 0 | P
18062 | LIB | STEVENS 7 | 1 | MP2 | 2002-03-05 09:00 | 2002-03-07 16:00 | 2.3 | 4 | 9.2 | MP2 Tasks. |  |  | 0 | P
18061 | LIB | STEVENS 7 | 2 | MP2 | 2002-02-05 09:00 | 2002-02-07 16:00 | 2.3 | 4 | 9.2 | MP2 Tasks. |  |  | 0 | P
17983 | LIB | SUBLETTE | 13 | MP2 | 2002-01-23 08:00 | 2002-01-23 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17984 | LIB | SUBLETTE | 13 | MP2 | 2002-01-29 08:00 | 2002-01-29 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17985 | LIB | SUBLETTE | 13 | MP2 | 2002-02-13 08:00 | 2002-02-13 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17986 | LIB | SUBLETTE | 13 | MP2 | 2002-02-27 08:00 | 2002-02-27 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17987 | LIB | SUBLETTE | 13 | MP2 | 2002-03-13 08:00 | 2002-03-13 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17988 | LIB | SUBLETTE | 13 | MP2 | 2002-03-27 08:00 | 2002-03-27 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17936 | LIB | SUBLETTE | 14 | MP2 | 2002-01-23 08:00 | 2002-01-23 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17937 | LIB | SUBLETTE | 14 | MP2 | 2002-02-06 08:00 | 2002-02-06 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17938 | LIB | SUBLETTE | 14 | MP2 | 2002-02-20 08:00 | 2002-02-20 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17939 | LIB | SUBLETTE | 14 | MP2 | 2002-03-07 08:00 | 2002-03-07 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17940 | LIB | SUBLETTE | 14 | MP2 | 2002-03-20 08:00 | 2002-03-20 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17941 | LIB | SUBLETTE | 19 | MP2 | 2002-01-25 08:00 | 2002-01-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17942 | LIB | SUBLETTE | 19 | MP2 | 2002-01-31 08:00 | 2002-01-31 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17943 | LIB | SUBLETTE | 19 | MP2 | 2002-02-11 08:00 | 2002-02-11 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17944 | LIB | SUBLETTE | 19 | MP2 | 2002-02-25 08:00 | 2002-02-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17945 | LIB | SUBLETTE | 19 | MP2 | 2002-03-04 08:00 | 2002-03-04 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17946 | LIB | SUBLETTE | 19 | MP2 | 2002-03-25 08:00 | 2002-03-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17947 | LIB | SUBLETTE | 20 | MP2 | 2002-01-21 08:00 | 2002-01-21 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17948 | LIB | SUBLETTE | 20 | MP2 | 2002-01-25 08:00 | 2002-01-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17949 | LIB | SUBLETTE | 20 | MP2 | 2002-02-05 08:00 | 2002-02-05 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17950 | LIB | SUBLETTE | 20 | MP2 | 2002-02-28 08:00 | 2002-02-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17951 | LIB | SUBLETTE | 20 | MP2 | 2002-03-15 08:00 | 2002-03-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17952 | LIB | SUBLETTE | 20 | MP2 | 2002-03-29 08:00 | 2002-03-29 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17953 | LIB | SUBLETTE | 21 | MP2 | 2002-01-24 08:00 | 2002-01-24 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17954 | LIB | SUBLETTE | 21 | MP2 | 2002-01-28 08:00 | 2002-01-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17955 | LIB | SUBLETTE | 21 | MP2 | 2002-02-04 08:00 | 2002-02-04 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17956 | LIB | SUBLETTE | 21 | MP2 | 2002-02-26 08:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17957 | LIB | SUBLETTE | 21 | MP2 | 2002-03-11 08:00 | 2002-03-11 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17958 | LIB | SUBLETTE | 21 | MP2 | 2002-03-28 08:00 | 2002-03-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17959 | LIB | SUBLETTE | 22 | MP2 | 2002-01-18 08:00 | 2002-01-18 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17960 | LIB | SUBLETTE | 22 | MP2 | 2002-01-24 08:00 | 2002-01-24 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17961 | LIB | SUBLETTE | 22 | MP2 | 2002-02-01 08:00 | 2002-02-01 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17962 | LIB | SUBLETTE | 22 | MP2 | 2002-02-15 08:00 | 2002-02-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17963 | LIB | SUBLETTE | 22 | MP2 | 2002-03-01 08:00 | 2002-03-01 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17964 | LIB | SUBLETTE | 22 | MP2 | 2002-03-22 08:00 | 2002-03-22 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17966 | LIB | SUBLETTE | 23 | MP2 | 2002-01-21 08:00 | 2002-01-21 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17965 | LIB | SUBLETTE | 23 | MP2 | 2002-01-22 08:00 | 2002-01-22 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17967 | LIB | SUBLETTE | 23 | MP2 | 2002-02-07 08:00 | 2002-02-07 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17968 | LIB | SUBLETTE | 23 | MP2 | 2002-02-22 08:00 | 2002-02-22 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17969 | LIB | SUBLETTE | 23 | MP2 | 2002-03-05 08:00 | 2002-03-05 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17970 | LIB | SUBLETTE | 23 | MP2 | 2002-03-26 08:00 | 2002-03-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17971 | LIB | SUBLETTE | 24 | MP2 | 2002-01-28 08:00 | 2002-01-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17972 | LIB | SUBLETTE | 24 | MP2 | 2002-01-30 08:00 | 2002-01-30 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17973 | LIB | SUBLETTE | 24 | MP2 | 2002-02-14 08:00 | 2002-02-14 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17974 | LIB | SUBLETTE | 24 | MP2 | 2002-02-25 08:00 | 2002-02-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17975 | LIB | SUBLETTE | 24 | MP2 | 2002-03-08 08:00 | 2002-03-08 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17976 | LIB | SUBLETTE | 24 | MP2 | 2002-03-21 08:00 | 2002-03-21 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17979 | LIB | SUBLETTE | 26 | MP2 | 2002-02-11 08:00 | 2002-02-11 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17980 | LIB | SUBLETTE | 26 | MP2 | 2002-02-28 08:00 | 2002-02-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17981 | LIB | SUBLETTE | 26 | MP2 | 2002-03-04 08:00 | 2002-03-04 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17982 | LIB | SUBLETTE | 26 | MP2 | 2002-03-25 08:00 | 2002-03-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17930 | LIB | SUBLETTE | 27 | MP2 | 2002-01-28 08:00 | 2002-01-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17929 | LIB | SUBLETTE | 27 | MP2 | 2002-01-29 08:00 | 2002-01-29 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17931 | LIB | SUBLETTE | 27 | MP2 | 2002-02-14 08:00 | 2002-02-14 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17932 | LIB | SUBLETTE | 27 | MP2 | 2002-02-26 08:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17933 | LIB | SUBLETTE | 27 | MP2 | 2002-03-15 08:00 | 2002-03-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17934 | LIB | SUBLETTE | 27 | MP2 | 2002-03-29 08:00 | 2002-03-29 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
16441 | LIB | TATE | 1 | OVERHAUL | 2002-10-01 08:00 | 2002-12-01 16:00 | 61.3 | 0 | 0 | Major engine and compressor overhaul. |  |  | 0 | P
16442 | LIB | TATE | 3 | OVERHAUL | 2002-08-01 08:00 | 2002-10-01 16:00 | 61.3 | 0 | 0 | Major engine and compressor overhaul. |  |  | 0 | P
17754 | LIB | TATE | 10 | INSPECTION | 2002-12-02 08:00 | 2002-12-13 16:00 | 11.3 | 0 | 0 | Unit inspection. |  |  | 0 | P
17755 | LIB | TATE | 11 | INSPECTION | 2002-12-16 08:00 | 2002-12-20 16:00 | 4.3 | 0 | 0 | Unit inspection. |  |  | 0 | P
17757 | LIB | TATE | ALL | ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 | 14 | 4.7 | Annual ESD test. |  |  | 0 | P
17668 | LIB | TEXAS 1 | 2 | ENGINE SERVICE | 2002-03-19 08:00 | 2002-03-19 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17620 | LIB | TEXAS 1 | 2 | CONTROLS PM | 2002-04-08 07:30 | 2002-04-10 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17669 | LIB | TEXAS 1 | 2 | ENGINE SERVICE | 2002-08-27 08:00 | 2002-08-27 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17670 | LIB | TEXAS 1 | 2 | INSPEC TION | 2002-10-21 08:00 | 2002-10-25 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17671 | LIB | TEXAS 1 | 3 | INSPECTION | 2002-02-18 08:00 | 2002-02-22 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17627 | LIB | TEXAS 1 | 3 | CONTROLS PM | 2002-05-14 07:30 | 2002-05-16 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17672 | LIB | TEXAS 1 | 3 | ENGINE SERVICE | 2002-06-05 08:00 | 2002-06-05 16:00 | 0.3 | 0 | 0 | Engine service |  |  | 0 | P
17621 | LIB | TEXAS 1 | 6 | CONTROLS PM | 2002-04-15 07:30 | 2002-04-17 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17624 | LIB | TEXAS 1 | ALL | ANNUAL ESD | 2002-05-06 07:30 | 2002-05-11 16:00 | 5.4 | 10 | 53.8 | Annual ESD. |  |  | 0 | P
17629 | LIB | TEXAS 2 | 1 | CONTROLS PM | 2002-06-10 07:30 | 2002-06-12 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17631 | LIB | TEXAS 2 | 2 | CONTROLS PM | 2002-06-18 07:30 | 2002-06-20 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17633 | LIB | TEXAS 2 | 3 | CONTROLS PM | 2002-07-08 07:30 | 2002-07-10 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17635 | LIB | TEXAS 2 | 4 | CONTROLS PM | 2002-07-15 07:30 | 2002-07-17 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17636 | LIB | TEXAS 2 | 5 | CONTROLS PM | 2002-08-05 07:30 | 2002-08-07 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17618 | LIB | TEXAS 2 | 6 | CONTROLS PM | 2002-03-04 07:30 | 2002-03-06 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17676 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-04-18 08:00 | 2002-04-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17677 | LIB | TEXAS 2 | 6 | INSPECTION | 2002-07-22 08:00 | 2002-07-26 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17678 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-09-18 08:00 | 2002-09-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17673 | LIB | TEXAS 2 | 7 | ENGINE SERVICE | 2002-02-06 08:00 | 2002-02-06 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17619 | LIB | TEXAS 2 | 7 | CONTROLS PM | 2002-03-11 07:30 | 2002-03-13 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17674 | LIB | TEXAS 2 | 7 | INSPECTION | 2002-06-24 08:00 | 2002-06-28 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17675 | LIB | TEXAS 2 | 7 | ENGINE SERVICE | 2002-07-30 08:00 | 2002-07-30 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17625 | LIB | TEXAS 2 | ALL | ANNUAL ESD | 2002-05-06 07:30 | 2002-05-11 16:00 | 5.4 | 15 | 80.6 | Annual ESD. |  |  | 0 | P