## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 29, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18245 | AMA | BEAVER 6 | 2 | 1500 HR. INSPECTION | 2002-02-20 10:00 | 2002-02-20 13:00 | 0.1 |  | OPS |  | 5 | 0.6 | 1500 hour inspection. |  |  |  | 0 | P | N | N
2 | 18262 | AMA | CANADIAN | 1 & 3 | REFLIEF VALVE TEST | 2002-03-12 08:00 | 2002-03-12 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual relief valve test. Station will be shut down. |  |  |  | 0 | P | N | N
3 | 18263 | AMA | CANADIAN | 1 & 3 | ANNUAL ESD | 2002-09-11 08:00 | 2002-09-11 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual ESD. |  |  |  | 0 | P | N | N
4 | 18338 | AMA | CLAUDE | 1 | ANNUAL ESD | 2002-05-14 09:00 | 2002-05-14 18:00 | 0.4 |  | OPS |  | 0 | 0 | Conducting annual ESD. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
5 | 18340 | AMA | CLAUDE | 1 | SAFETY DEVICES | 2002-10-08 09:00 | 2002-10-09 08:00 | 1 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
6 | 18247 | AMA | ELLIS 1 | 1 | 1500 HR. INSPECTION | 2002-02-12 09:00 | 2002-02-12 16:00 | 0.3 |  | OPS |  | 3 | 0.9 | 1500 hour inspection. |  |  |  | 0 | P | N | N
7 | 18248 | AMA | ELLIS 1 | 3 | 1500 HR. INSPECTION | 2002-02-13 09:00 | 2002-02-13 11:00 | 0.1 |  | OPS |  | 3 | 0.3 | 1500 hour inspection. |  |  |  | 0 | P | N | N
8 | 18249 | AMA | ELLIS 1 | 4 | 1500 HR. INSPECTION | 2002-02-14 09:00 | 2002-02-14 12:00 | 0.1 |  | OPS |  | 7 | 0.9 | 1500 hour inspection. |  |  |  | 0 | P | N | N
9 | 18258 | AMA | ELLIS 3 | 6 | 1500 HR INSPECTION | 2002-02-04 09:00 | 2002-02-04 12:00 | 0.1 |  | OPS |  | 4.2 | 0.5 | 1500 hour inspection |  |  |  | 0 | P | N | N
10 | 18261 | AMA | HEMPHILL 2 | ANNUAL ESD | ANNUAL ESD | 2002-09-10 08:00 | 2002-09-10 16:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
11 | 18260 | AMA | HEMPHILL 3 | ANNUAL ESD | ANNUAL ESD | 2002-09-09 08:00 | 2002-09-09 16:00 | 0.3 |  | OPS |  | 1.4 | 0.5 | Annual ESD. |  |  |  | 0 | P | N | N
12 | 18264 | AMA | HEMPHILL 4 | ALL | ANNUAL ESD | 2002-09-12 08:00 | 2002-09-12 09:00 | 0 |  | OPS |  | 1.4 | 0.1 | Annual ESD. |  |  |  | 0 | P | N | N
13 | 18331 | AMA | P3 | ALL | SURGE CONTROL TIE-IN | 2002-03-05 08:00 | 2002-03-06 16:00 | 1.3 |  | OPS |  | 100 | 133.3 | We will need to remove some material that we are going to reuse and test it before we can make our tie-ins. (They will be able to by-pass the station to make some deliveries). |  |  |  | 0 | P | N | N
14 | 18337 | AMA | P3 | ALL | ANNUAL ESD | 2002-04-17 08:00 | 2002-04-17 18:00 | 0.4 |  | OPS |  | 150 | 62.5 | Conducting annual ESD at the P3 station. |  |  |  | 0 | P | N | N
15 | 18332 | AMA | P3 | 1 | SAFETY DEVICES | 2002-04-23 08:00 | 2002-04-24 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
16 | 18333 | AMA | P3 | 2 | SAFETY DEVICES | 2002-05-08 08:00 | 2002-05-09 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
17 | 18334 | AMA | P3 | 3 | SAFETY DEVICES | 2002-05-22 08:00 | 2002-05-23 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
18 | 18336 | AMA | P3 | 5 | SAFETY DEVICES | 2002-06-18 08:00 | 2002-06-20 18:00 | 2.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
19 | 18335 | AMA | P3 | 4 | SAFETY DEVICES | 2002-08-22 08:00 | 2002-08-23 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
20 | 18339 | AMA | PAMPA | 1 | ESD & SAFETY DEVICES | 2002-04-08 08:00 | 2002-04-09 18:00 | 1.4 |  | OPS |  | 0 | 0 | Conducting annual ESD test and calibrating safety devices. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
21 | 17016 | AMA | ROGER MILLS | 5 | MECHNICAL FAILURE | 2001-09-19 16:00 | 2002-03-30 16:00 | 192 |  | OPS |  | 0 | 0 | They had a mechnical failure on unit #5. Not sure of the exact completion. (Completion date moved into March 2002). |  | 2001-09-19 16:00 |  | 0 | U | N | N
22 | 18238 | AMA | SUNRAY | 4 | RH 3&4 CYLINDER | 2001-11-30 08:00 | 2002-06-01 16:00 | 183.3 |  | OPS |  | 0 | 0 | The rings are out on the RH 3&4 cylinder. (Waiting for clearence to overhaul unit). |  | 2001-11-30 08:00 |  | 0 | U | N | N
23 | 18239 | AMA | SUNRAY | 5 | CRACKED HEAD | 2001-12-22 08:00 | 2002-06-03 16:00 | 163.3 |  | OPS |  | 0 | 0 | LH #3 head is cracked- It will require a complete overhaul on the LH side. (This work is subject to approval). |  | 2001-12-22 08:00 |  | 0 | U | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 29, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18245 | AMA | BEAVER 6 | 2 | 1500 HR. INSPECTION | 2002-02-20 10:00 | 2002-02-20 13:00 | 0.1 |  | OPS |  | 5 | 0.6 | 1500 hour inspection. |  |  |  | 0 | P | N | N
2 | 18262 | AMA | CANADIAN | 1 & 3 | REFLIEF VALVE TEST | 2002-03-12 08:00 | 2002-03-12 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual relief valve test. Station will be shut down. |  |  |  | 0 | P | N | N
3 | 18263 | AMA | CANADIAN | 1 & 3 | ANNUAL ESD | 2002-09-11 08:00 | 2002-09-11 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual ESD. |  |  |  | 0 | P | N | N
4 | 18338 | AMA | CLAUDE | 1 | ANNUAL ESD | 2002-05-14 09:00 | 2002-05-14 18:00 | 0.4 |  | OPS |  | 0 | 0 | Conducting annual ESD. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
5 | 18340 | AMA | CLAUDE | 1 | SAFETY DEVICES | 2002-10-08 09:00 | 2002-10-09 08:00 | 1 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
6 | 18247 | AMA | ELLIS 1 | 1 | 1500 HR. INSPECTION | 2002-02-12 09:00 | 2002-02-12 16:00 | 0.3 |  | OPS |  | 3 | 0.9 | 1500 hour inspection. |  |  |  | 0 | P | N | N
7 | 18248 | AMA | ELLIS 1 | 3 | 1500 HR. INSPECTION | 2002-02-13 09:00 | 2002-02-13 11:00 | 0.1 |  | OPS |  | 3 | 0.3 | 1500 hour inspection. |  |  |  | 0 | P | N | N
8 | 18249 | AMA | ELLIS 1 | 4 | 1500 HR. INSPECTION | 2002-02-14 09:00 | 2002-02-14 12:00 | 0.1 |  | OPS |  | 7 | 0.9 | 1500 hour inspection. |  |  |  | 0 | P | N | N
9 | 18258 | AMA | ELLIS 3 | 6 | 1500 HR INSPECTION | 2002-02-04 09:00 | 2002-02-04 12:00 | 0.1 |  | OPS |  | 4.2 | 0.5 | 1500 hour inspection |  |  |  | 0 | P | N | N
10 | 18261 | AMA | HEMPHILL 2 | ANNUAL ESD | ANNUAL ESD | 2002-09-10 08:00 | 2002-09-10 16:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
11 | 18260 | AMA | HEMPHILL 3 | ANNUAL ESD | ANNUAL ESD | 2002-09-09 08:00 | 2002-09-09 16:00 | 0.3 |  | OPS |  | 1.4 | 0.5 | Annual ESD. |  |  |  | 0 | P | N | N
12 | 18264 | AMA | HEMPHILL 4 | ALL | ANNUAL ESD | 2002-09-12 08:00 | 2002-09-12 09:00 | 0 |  | OPS |  | 1.4 | 0.1 | Annual ESD. |  |  |  | 0 | P | N | N
13 | 18331 | AMA | P3 | ALL | SURGE CONTROL TIE-IN | 2002-03-05 08:00 | 2002-03-06 16:00 | 1.3 |  | OPS |  | 100 | 133.3 | We will need to remove some material that we are going to reuse and test it before we can make our tie-ins. (They will be able to by-pass the station to make some deliveries). |  |  |  | 0 | P | N | N
14 | 18337 | AMA | P3 | ALL | ANNUAL ESD | 2002-04-17 08:00 | 2002-04-17 18:00 | 0.4 |  | OPS |  | 150 | 62.5 | Conducting annual ESD at the P3 station. |  |  |  | 0 | P | N | N
15 | 18332 | AMA | P3 | 1 | SAFETY DEVICES | 2002-04-23 08:00 | 2002-04-24 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
16 | 18333 | AMA | P3 | 2 | SAFETY DEVICES | 2002-05-08 08:00 | 2002-05-09 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
17 | 18334 | AMA | P3 | 3 | SAFETY DEVICES | 2002-05-22 08:00 | 2002-05-23 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
18 | 18336 | AMA | P3 | 5 | SAFETY DEVICES | 2002-06-18 08:00 | 2002-06-20 18:00 | 2.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
19 | 18335 | AMA | P3 | 4 | SAFETY DEVICES | 2002-08-22 08:00 | 2002-08-23 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
20 | 18339 | AMA | PAMPA | 1 | ESD & SAFETY DEVICES | 2002-04-08 08:00 | 2002-04-09 18:00 | 1.4 |  | OPS |  | 0 | 0 | Conducting annual ESD test and calibrating safety devices. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
21 | 17016 | AMA | ROGER MILLS | 5 | MECHNICAL FAILURE | 2001-09-19 16:00 | 2002-03-30 16:00 | 192 |  | OPS |  | 0 | 0 | They had a mechnical failure on unit #5. Not sure of the exact completion. (Completion date moved into March 2002). |  | 2001-09-19 16:00 |  | 0 | U | N | N
22 | 18238 | AMA | SUNRAY | 4 | RH 3&4 CYLINDER | 2001-11-30 08:00 | 2002-06-01 16:00 | 183.3 |  | OPS |  | 0 | 0 | The rings are out on the RH 3&4 cylinder. (Waiting for clearence to overhaul unit). |  | 2001-11-30 08:00 |  | 0 | U | N | N
23 | 18239 | AMA | SUNRAY | 5 | CRACKED HEAD | 2001-12-22 08:00 | 2002-06-03 16:00 | 163.3 |  | OPS |  | 0 | 0 | LH #3 head is cracked- It will require a complete overhaul on the LH side. (This work is subject to approval). |  | 2001-12-22 08:00 |  | 0 | U | N | N