## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Beatrice Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 29, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18299 | BEA | BEATRICE | 24 | OVERHAUL #12 CYLINDER | 2002-01-22 07:00 | 2002-01-28 15:30 | 6.3 |  | OPS |  | 0 | 0 | Overhaul #12 power cylinder replace compressor valve replace hydraulic lifters etc. |  | 2002-01-22 07:00 |  | 0 | P | N | N
2 | 17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
3 | 17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
4 | 17154 | BEA | CUNNINGHAM | 5 | OVERHAUL | 2002-04-01 07:00 | 2002-04-22 15:30 | 21.3 |  | OPS |  | 0 | 0 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (Flow affect will depends the needs on the pipeline). Unit pumps about 75 mmcfd. |  |  |  | 0 | P | N | N
5 | 18328 | BEA | PALMYRA | 18 | PULLING PISTON | 2002-01-28 07:30 | 2002-01-29 16:00 | 1.4 |  | OPS |  | 0 | 0 | Pulling the piston on #11 cylinder. Bearing checks on #1 & #3 power cylinders. |  |  |  | 0 | U | N | N
6 | 17166 | BEA | PALMYRA | 21 | OVERHAUL | 2002-05-06 08:00 | 2002-05-31 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
7 | 17167 | BEA | PALMYRA | 22 | OVERHAUL | 2002-05-27 08:00 | 2002-06-14 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
8 | 17168 | BEA | PALMYRA | 23 | OVERHAUL | 2002-06-17 08:00 | 2002-07-05 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
9 | 17169 | BEA | PALMYRA | 24 | OVERHAUL | 2002-07-08 08:00 | 2002-07-19 16:00 | 11.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
10 | 17170 | BEA | PALMYRA | 25 | OVERHAUL | 2002-07-22 08:00 | 2002-08-02 16:00 | 11.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
11 | 16327 | BEA | SO OMAHA | CREEK XING | OMAHA 3RD BL | 2002-07-15 08:00 | 2002-07-15 16:00 | 0.3 |  | 453 | C.014544 | 0 | 0 | Replace and lower approximately 200 feet of the 16" Omaha 3rd branch line at MP 16.86. |  |  |  | 0 | P | N | N
12 | 18324 | BEA | TESCOTT | ESD STATION | ESD STATION | 2002-01-25 08:00 | 2002-01-25 16:00 | 0.3 |  | OPS |  | 0 | 0 | We need to remove the ESD station with the new gate installation. We estimate this will take 4 to 6 hours. (Will have to work with Gas Control to schedule this outage). |  |  |  | 0 | U | N | N
13 | 17172 | BEA | TESCOTT | 2 | OVERHAUL | 2002-08-05 08:00 | 2002-08-30 16:00 | 25.3 |  | OPS |  | 0 | 0 | Turbine overhaul on a GE Frame III based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
14 | 17174 | BEA | TESCOTT | 4 | OVERHAUL | 2002-09-02 08:00 | 2002-09-27 16:00 | 25.3 |  | OPS |  | 0 | 0 | Turbine overhaul on a GE Frame III based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
15 | 17173 | BEA | TESCOTT | 3 | OVERHAUL | 2002-09-30 08:00 | 2002-10-25 16:00 | 25.3 |  | OPS |  | 0 | 0 | Turbine overhaul on a GE Frame III based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Beatrice Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 29, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18299 | BEA | BEATRICE | 24 | OVERHAUL #12 CYLINDER | 2002-01-22 07:00 | 2002-01-28 15:30 | 6.3 |  | OPS |  | 0 | 0 | Overhaul #12 power cylinder replace compressor valve replace hydraulic lifters etc. |  | 2002-01-22 07:00 |  | 0 | P | N | N
2 | 17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
3 | 17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
4 | 17154 | BEA | CUNNINGHAM | 5 | OVERHAUL | 2002-04-01 07:00 | 2002-04-22 15:30 | 21.3 |  | OPS |  | 0 | 0 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (Flow affect will depends the needs on the pipeline). Unit pumps about 75 mmcfd. |  |  |  | 0 | P | N | N
5 | 18328 | BEA | PALMYRA | 18 | PULLING PISTON | 2002-01-28 07:30 | 2002-01-29 16:00 | 1.4 |  | OPS |  | 0 | 0 | Pulling the piston on #11 cylinder. Bearing checks on #1 & #3 power cylinders. |  |  |  | 0 | U | N | N
6 | 17166 | BEA | PALMYRA | 21 | OVERHAUL | 2002-05-06 08:00 | 2002-05-31 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
7 | 17167 | BEA | PALMYRA | 22 | OVERHAUL | 2002-05-27 08:00 | 2002-06-14 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
8 | 17168 | BEA | PALMYRA | 23 | OVERHAUL | 2002-06-17 08:00 | 2002-07-05 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
9 | 17169 | BEA | PALMYRA | 24 | OVERHAUL | 2002-07-08 08:00 | 2002-07-19 16:00 | 11.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
10 | 17170 | BEA | PALMYRA | 25 | OVERHAUL | 2002-07-22 08:00 | 2002-08-02 16:00 | 11.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
11 | 16327 | BEA | SO OMAHA | CREEK XING | OMAHA 3RD BL | 2002-07-15 08:00 | 2002-07-15 16:00 | 0.3 |  | 453 | C.014544 | 0 | 0 | Replace and lower approximately 200 feet of the 16" Omaha 3rd branch line at MP 16.86. |  |  |  | 0 | P | N | N
12 | 18324 | BEA | TESCOTT | ESD STATION | ESD STATION | 2002-01-25 08:00 | 2002-01-25 16:00 | 0.3 |  | OPS |  | 0 | 0 | We need to remove the ESD station with the new gate installation. We estimate this will take 4 to 6 hours. (Will have to work with Gas Control to schedule this outage). |  |  |  | 0 | U | N | N
13 | 17172 | BEA | TESCOTT | 2 | OVERHAUL | 2002-08-05 08:00 | 2002-08-30 16:00 | 25.3 |  | OPS |  | 0 | 0 | Turbine overhaul on a GE Frame III based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
14 | 17174 | BEA | TESCOTT | 4 | OVERHAUL | 2002-09-02 08:00 | 2002-09-27 16:00 | 25.3 |  | OPS |  | 0 | 0 | Turbine overhaul on a GE Frame III based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
15 | 17173 | BEA | TESCOTT | 3 | OVERHAUL | 2002-09-30 08:00 | 2002-10-25 16:00 | 25.3 |  | OPS |  | 0 | 0 | Turbine overhaul on a GE Frame III based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N