## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Midland Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 29, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18227 | MID | KERMIT | 1 | FUEL VALVES | 2002-01-08 08:00 | 2002-02-11 16:00 | 34.3 |  | OPS |  | 0 | 0 | They need the fuel valves repaired. They will take them off and send them in for repairs. Also the will do anual maintenance on the unit while it is down. 01/25/02 (Outage extended due to waiting for valve to return). |  | 2002-01-08 09:00 |  | 0 | P | N | N
2 | 18325 | MID | PLAINS | 1 | ANNUAL ESD | 2002-03-19 08:00 | 2002-03-20 18:00 | 1.4 |  | OPS |  | 100 | 141.7 | Annual ESD & calibrate transmitters. Test all shut downs devices put in new battery charge. (Will put on @ 18:00 03/19/02 and take back down on 3/20/02 if needed). Will see if El Paso can work with us on the outage. |  |  |  | 0 | P | N | N
3 | 17150 | MID | SEMINOLE | 1 | OVERHAUL | 2002-09-02 08:00 | 2002-09-30 16:00 | 28.3 |  | OPS |  | 0 | 0 | Complete disassembly and overhaul of gas producer and power turbine. |  |  |  | 0 | P | N | N
4 | 18319 | MID | SPRAYBERRY | ESD | ANNUAL ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 |  | OPS |  | 280 | 93.3 | Annual ESD and maintenance. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Midland Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 29, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18227 | MID | KERMIT | 1 | FUEL VALVES | 2002-01-08 08:00 | 2002-02-11 16:00 | 34.3 |  | OPS |  | 0 | 0 | They need the fuel valves repaired. They will take them off and send them in for repairs. Also the will do anual maintenance on the unit while it is down. 01/25/02 (Outage extended due to waiting for valve to return). |  | 2002-01-08 09:00 |  | 0 | P | N | N
2 | 18325 | MID | PLAINS | 1 | ANNUAL ESD | 2002-03-19 08:00 | 2002-03-20 18:00 | 1.4 |  | OPS |  | 100 | 141.7 | Annual ESD & calibrate transmitters. Test all shut downs devices put in new battery charge. (Will put on @ 18:00 03/19/02 and take back down on 3/20/02 if needed). Will see if El Paso can work with us on the outage. |  |  |  | 0 | P | N | N
3 | 17150 | MID | SEMINOLE | 1 | OVERHAUL | 2002-09-02 08:00 | 2002-09-30 16:00 | 28.3 |  | OPS |  | 0 | 0 | Complete disassembly and overhaul of gas producer and power turbine. |  |  |  | 0 | P | N | N
4 | 18319 | MID | SPRAYBERRY | ESD | ANNUAL ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 |  | OPS |  | 280 | 93.3 | Annual ESD and maintenance. |  |  |  | 0 | P | N | N